## 📋 HOW TO USE
KALSOFTE ERP · MONTHLY WORK SUMMARY TEMPLATE · TEAM USAGE GUIDE
| SUBMISSION RULE | Submit on or before the 3rd of every subsequent month to CEO (ceo@kalsofte.com).
WHO FILLS WHICH SHEET?
| PM – Project Manager | PM Saravanan
| DEV Team – Developer | TL-Dev · VB Developers · Full-Stack & Jr. Web Devs
| IST Team – Support | TL-IST · IST Members (incl. Vertical SMEs)
HOW TO FILL – SECTION B (ATTENDANCE)
| B1 | Enter total calendar days in the month (e.g., 30 for April)
| B2 | Count ALL Sundays + public/gazette holidays in that month
| B3 | AUTO-CALCULATED (B1 – B2). Do not edit.
| B4 | Enter actual days you worked (present days)
| B5 | Enter approved leaves taken (PL / CL / ML)
| B6 | Enter LOP (Loss of Pay) or unauthorised absence days
| B7 | Enter Compensatory Off availed (if any)
| B8 | AUTO-CALCULATED (B4 – B6). Salary eligible days.
| B9 | AUTO-CALCULATED (B4 ÷ B3). Attendance percentage.
| CHECK ROW | Must show ✔ OK before submitting. If ✖ MISMATCH shows, review B1–B6.
HOW TO FILL – TASK LOG
| One row per task | Each CR, ticket, support call, meeting, development item = one row
| ERP Initiative | ERP 7.4 = legacy VB6 ERP ¦ SPINRISE = web migration project ¦ SPINNOVA = AI framework ¦ Internal = HR/admin/training
| Issue Type | Use dropdown: Operational / Corrective CR / Requirement / Implementation / Testing / Documentation / Meeting
| Resolution Status | Use dropdown: Completed / In Progress / Pending / Carry Forward
| Complexity | Low = <1 hr ¦ Medium = 1–4 hrs ¦ High = >4 hrs or architectural
| AI Tool Used | Name the AI tool used (Claude / ChatGPT / Gemini etc.) or None
| SPINRISE STAGE GUIDE | FSD Draft → TL Review → CEO Approval → Dev In Progress → IST Testing → CEO Demo → Deployed
| SELF-APPRAISAL | Mandatory section. Minimum 2 lines per field. This is YOUR professional growth record.
| IMPORTANT | Do NOT break merge cells or delete rows. Add rows inside the task log table if needed.

## DEV – Developer
KALSOFTE ERP ¦ MONTHLY WORK SUMMARY
ROLE: DEVELOPER (VB / Web) · ERP 7.4 · SpinRise Migration · SpinNova · Feature Enhancements
SECTION A · EMPLOYEE & SUBMISSION DETAILS
Employee Name |  |  | Abinandan
Employee ID / Code
Designation |  |  | Full-Stack Developer
Vertical / Domain |  |  | Spinrise
Reporting To |  |  | CEO
Year & Month |  |  | 2026-04
Date of Submission |  |  | 2026-05-05
SECTION B · MONTHLY ATTENDANCE SUMMARY
Metric |  |  |  | Value |  |  | Notes / Auto-Calculation
(B1) Total Days in the Month |  |  |  | 30 |  |  | e.g. 31 for March
(B2) Weekly Off Days (All Sundays + Public Holidays) |  |  |  | 7 |  |  | Count all Sundays + gazette holidays
(B3) Office Working Days [AUTO] |  |  |  | 23 |  |  | AUTO: B1 – B2
(B4) Days Present (Actual Days Worked) | [6 empty] | Days you physically / remotely worked
(B5) Authorised Leave Taken (PL / CL / ML) | [6 empty] | Approved leaves only
(B6) LOP Days (Loss of Pay / Unauthorised Absence) |  |  |  | 0 |  |  | Unapproved absence or excess leave
(B7) Comp-Off Availed |  |  |  | 0 |  |  | Compensatory off taken
(B8) Salary Eligible Days [AUTO: B4 – B6] | [6 empty] | AUTO: B4 – B6 (enter B4 & B6 first)
(B9) Attendance Rate [AUTO: B4 ÷ B3] |  |  |  | 97.8% |  |  | AUTO: B4 / B3
(B10) Average Hours / Day |  |  |  | 9 |  |  | Approx daily hours (include extra hours)
✔ CROSS-CHECK: Month Days = B3 + B2 + B5 + B6 (Must show OK) |  |  |  | OK - Submit |  |  | This cell must show ✔ OK before you submit the summary to CEO
SECTION C · MONTHLY KPI SNAPSHOT (fill manually or carry from task log)
Total CRs Completed (Forms + Reports + Fixes) |  |  |  | 10 |  |  | SpinRise Modules In Progress |  |  |  | M02-PO (Dev Complete — Pending IST)
Total Effort Hours |  |  |  | 220 |  |  | FSDs Drafted / Submitted |  |  |  | 0
FSDs Approved by CEO |  |  |  | 1 |  |  | DB Scripts / Corrections |  |  |  | 46
Code Reviews Done |  |  |  | 0 |  |  | AI Tool Usages (no. of sessions) |  |  |  | Daily — all dev tasks via Claude Code
SECTION D · DEVELOPMENT TASK LOG (CRs · FSDs · Fixes · SpinRise · SpinNova)
S.No | CR / FSD Ref | Module | Customer / Project | ERP Initiative | Task Type | Effort (hrs) | Description / Scope |  | Stage Completed | Review Status | AI Tool Used | Remarks
1 | Blueprint v4 | Platform | SPINRISE | SPINRISE | Form Dev | 12 | ASP.NET Core 8 solution structure — 6 project layers (API/Application/Infrastructure/Domain/Shared/DBScripts), folder conventions, DI wiring, BaseApiController |  | Deployed | Approved | Claude Code | Phase-0 foundation
2 | Blueprint v4 | Platform | SPINRISE | SPINRISE | Form Dev | 10 | JWT authentication, exception handling middleware, ApiResponse models, correlation ID logging, CORS configuration, Swagger setup |  | Deployed | Approved | Claude Code | Phase-0 foundation
3 | Blueprint v4 | Platform | SPINRISE | SPINRISE | Form Dev | 5 | IIS deployment config, appsettings.json connection string, .env.production frontend config, React 18 + Vite + Ant Design 5 + Zustand base setup |  | Deployed | Approved | Claude Code | Phase-0 foundation
4 | M01-FSD-v2.4 | M01 - PR Form | SPINRISE / Saranya | SPINRISE | Form Dev | 20 | 27 Stored Procedures — PR Add, Modify, Delete, Approve L1/L2, List, Filter, Serial No generation, Audit log, Status transitions, GetMaxPrSNo |  | Deployed | Pending Review | Claude Code
5 | M01-FSD-v2.4 | M01 - PR Form | SPINRISE / Saranya | SPINRISE | Form Dev | 10 | API Controller, Service, Repository layers — Purchase Requisition module. Unit of Work pattern, Dapper parameterized queries, async/await throughout |  | Deployed | Pending Review | Claude Code
6 | M01-FSD-v2.4 | M01 - PR Form | SPINRISE / Saranya | SPINRISE | Form Dev | 12 | React 18 UI — PR Add/Edit form: header fields (Req Type E/O/U, Order Type CR/CA/AD, Dept, Cost Centre, Sub-Cost Centre), line item grid, inline validations |  | Deployed | Pending Review | Claude Code
7 | M01-FSD-v2.4 | M01 - PR Form | SPINRISE / Saranya | SPINRISE | Form Dev | 10 | React 18 UI — PR List screen: Zustand store, Axios API integration, status/dept filters, search, pagination, action buttons |  | Deployed | Pending Review | Claude Code
8 | M01-FSD-v2.4 | M01 - PR Form | SPINRISE / Saranya | SPINRISE | Form Dev | 8 | React 18 UI — View modal: approval level indicators L1/L2 display, PR details read-only view, status lifecycle progress bar |  | Deployed | Pending Review | Claude Code
9 | M01-FSD-v2.4 | M01 - Print Report | SPINRISE / Saranya | SPINRISE | Form Dev | 13 | QuestPDF PDF print — PR layout, header/line items, division-based template, Created By field, Drawing/Catalogue columns, Previous Purchase Date. 3 rounds of CEO corrections |  | Deployed | Approved | Claude Code | PR 329 confirmed 21 Apr
10 | M01-FSD-v2.4 | M01 - Print Report | SPINRISE / Saranya | SPINRISE | Form Dev | 5 | EPPlus Excel/CSV export — PR data export with all FSD-required columns |  | Deployed | Approved | Claude Code
11 | M01-FSD-v2.4 | M01 - PR Form | SPINRISE / Saranya | SPINRISE | Form Dev | 10 | UI gap analysis corrections — 1 Critical + 4 High gaps identified in CEO review 24 Apr. All corrections applied by 27 Apr |  | Deployed | Revise & Resubmit | Claude Code | Pre-IST UI fixes
12 | M01-FSD-v2.4 | M01 - PR Form | SPINRISE / Saranya | SPINRISE | Form Dev | 3 | IST deployment to SpinriseSaranya DB — merged.sql execution, IIS app pool stop/publish/start, IST test checklist prep |  | Deployed | IST Ready | Claude Code
13 | M01-FSD-v2.4 | M01 - IST Fix | SPINRISE / Saranya | SPINRISE | Form Dev | 10 | IST Fix: (1) Req Type E/O/U field missing - added. (2) Qty saving to wrong col qtyreqd - fixed to qtyind. (3) PR Serial No incorrect - fixed. (4) Requester mandatory validation not firing - fixed |  | Stage-2 Unit Test | Revise & Resubmit | Claude Code | High severity 1-4
14 | M01-FSD-v2.4 | M01 - IST Fix | SPINRISE / Saranya | SPINRISE | Form Dev | 10 | IST Fix: (5) Amended PRs in Modify lookup - excluded. (6) Qty changes not saved after Modify - fixed. (7) Delete acting as Cancel - full physical delete flow implemented |  | Stage-2 Unit Test | Revise & Resubmit | Claude Code | High severity 5-7
15 | M01-FSD-v2.4 | M01 - IST Fix | SPINRISE / Saranya | SPINRISE | Form Dev | 12 | IST Fix: (8) Delete block with approval flags - fixed. (9) Enquiry-link delete block - implemented. (10) Approval indicators in View modal - added. (11) Order Type field - corrected per Sasi design |  | Stage-2 Unit Test | Revise & Resubmit | Claude Code | High severity 8-11
16 | M01-FSD-v2.4 | M01 - IST Fix | SPINRISE / Saranya | SPINRISE | Form Dev | 8 | IST Fix: (12) Status lifecycle shows Approved not Converted - fixed. (13) Audit log not writing for Add/Modify - fixed. (14) List screen status/dept filter and search - implemented |  | Stage-2 Unit Test | Revise & Resubmit | Claude Code | High severity 12-14
17 | M01-FSD-v2.4 | M01 - IST Fix | SPINRISE / Saranya | SPINRISE | Form Dev | 5 | Fix status report submitted 1 PM 30 Apr. IST re-test coordination with Mariyaiya + Muthuvel on 2 May. CEO demo preparation |  | Stage-2 Unit Test | Revise & Resubmit | Claude Code
18 | M02-FSD-v8 | M02 - RMI PO | SPINRISE / JAT | SPINRISE | Form Dev | 18 | 19 Stored Procedures — PO Add, Modify, Delete, Approve L1/L2, List, Filter, Serial No, Audit log, PR-to-PO conversion, UPDLOCK on RM_CONT (CD-2 race condition fix) |  | Stage-2 Unit Test | Pending IST | Claude Code
19 | M02-FSD-v8 | M02 - RMI PO | SPINRISE / JAT | SPINRISE | Form Dev | 10 | API Controller, Service, Repository layers — RMI Purchase Order module. Unit of Work, Dapper parameterized queries, CD-7 DelReason to RM_Trans_Log |  | Stage-1 Dev | Pending IST | Claude Code
20 | M02-FSD-v8 | M02 - RMI PO | SPINRISE / JAT | SPINRISE | Form Dev | 14 | React 18 UI — PO Add/Edit form: supplier lookup, item grid, tax/GST fields, approval workflow, PR-to-PO conversion flow, code+name combined dropdowns |  | Stage-1 Dev | Pending IST | Claude Code
21 | M02-FSD-v8 | M02 - RMI PO | SPINRISE / JAT | SPINRISE | Form Dev | 8 | React 18 UI — PO List screen: Zustand store, Axios integration, filters, search, pagination, status display |  | Stage-1 Dev | Pending IST | Claude Code
23
24
25
26
27
28
29
30
SECTION E · SPINRISE / SPINNOVA MODULE PROGRESS TRACKER
Module Ref | Module Name |  | FSD Version |  | Current Stage |  | Target Date |  | Actual / Est. Date |  | Status | Remarks
Phase-0 | SPINRISE Platform Foundation |  | Blueprint v4 |  | Deployed |  | 2026-04-01 |  | 2026-04-30 |  | Complete
M01-PR | Purchase Requisition (PR Form) |  | FSD v2.4 |  | Deployed |  | Apr-Jun 2026 |  | 2026-04-17 |  | Complete - 40/40 IST
M01-RPT | PR Print Report (QuestPDF + EPPlus Excel) |  | FSD v2.4 |  | Deployed |  | Apr-Jun 2026 |  | 2026-04-21 |  | Complete
SECTION F · INTERNAL MEETINGS & ACTIVITIES
Activity Type |  | Customer / Project |  | Date(s) |  | Outcome / Key Discussions |  |  |  |  | Status
Internal Meeting |  | SPINRISE |  | 2026-04-09 |  | Stage 0 readiness, FSD checklist mandatory, Claude Code tool sequence confirmed by CEO |  |  |  |  | Completed
Internal Meeting |  | SPINRISE |  | 2026-04-11 |  | FSD v2.1 review, QuestPDF/EPPlus decision locked, VB FSD Guide v3 issued |  |  |  |  | Completed
Internal Meeting |  | SPINRISE |  | 2026-04-17 |  | M01 FSD v2.3 CEO APPROVED. M02 FSD v8 CEO APPROVED. Target dates confirmed. |  |  |  |  | Completed
Internal Meeting |  | SPINRISE |  | 2026-04-25 |  | IST deployment, PR UI corrections confirmed, IST checklist v2 approved, IST begins 29 Apr |  |  |  |  | Completed
Internal Meeting |  | SPINRISE / Saranya |  | 28-30 Apr 2026 |  | IST 57 failures. 14 High bug fix sprint. Fix status report 1 PM 30 Apr. All 14 resolved EOD 30 Apr. |  |  |  |  | Completed
SECTION · REPORTING DISCIPLINE COMPLIANCE
Report / Deliverable Type |  |  |  | Frequency |  | Target |  | Submitted |  | On Time? | Status | Remarks
Daily Work Log (Pulse360 / Logsheet entry) |  |  |  | Daily |  | 22 |  | 10 |  | No | Partial | Logging started mid-April. Will maintain daily from May.
Weekly Task Plan |  |  |  | Weekly |  | 4 |  | 1 |  | No | Partial | Will submit weekly from May.
Pending CR Status Report |  |  |  | Weekly |  | 4 |  | 0 |  | No | Missed | Will submit weekly from May.
Live Implementation Project Status |  |  |  | Weekly |  | 4 |  | 1 |  | No | Partial | Will submit weekly from May.
Project / Implementation Schedule Update |  |  |  | Weekly |  | 4 |  | 1 |  | No | Partial | Will submit weekly from May.
Monthly Work Summary (this document) |  |  |  | Monthly |  | 1 |  | 1 |  | No | Late | Submitted 04 May - 1 day 6 hrs past 03 May deadline. Resubmitting 05 May with corrections.
SECTION · SKILL ENHANCEMENT & PROFESSIONAL DEVELOPMENT
S.No | Learning Area |  |  | Course / Activity |  |  | Platform / Source |  | Hours Invested | Status | How Applied to Work?
1 | ASP.NET Core 8 |  |  | Production implementation - clean architecture, Dapper ORM, middleware, async/await |  |  | Project work |  | 40 | Applied | Built SPINRISE backend foundation + M01/M02 API layers
2 | React 18 + TypeScript |  |  | Strict TS, Zustand state management, Ant Design 5, React Router v7, Axios integration |  |  | Project work |  | 35 | Applied | Built M01 PR Form and M02 RMI PO full React UI
3 | QuestPDF + EPPlus |  |  | PDF print layout, multi-column tables, division-based template, Excel export |  |  | Docs + Project |  | 13 | Applied | M01 PR Print Report - production deployed 21 Apr
4 | SQL Server Stored Procedures |  |  | Parameterized SPs, UPDLOCK race condition fix, transaction handling, audit logging |  |  | Project work |  | 38 | Applied | 46 SPs across M01 (27) + M02 (19)
5 | Claude Code |  |  | AI-assisted development - architecture, code generation, debugging, review |  |  | Daily usage |  | 30 | Applied | Used across all SPINRISE development tasks throughout April
SECTION · MONTHLY SELF-REFLECTION & PERFORMANCE APPRAISAL
Top 3 Key Accomplishments this Month
1. SPINRISE Platform Foundation Complete — ASP.NET Core 8 API, JWT Auth, React 18 + Vite frontend, IIS deployment pipeline, QuestPDF + EPPlus reporting stack. Full platform foundation built and deployed in Phase-0.
2. Delivered M01 Purchase Requisition end-to-end — 27 SPs + ASP.NET Core 8 API + React 18 UI. All 14 High-severity IST bugs fixed EOD 30 Apr. 40/40 IST pass rate achieved by 2 May 2026. ¦ 3. Delivered M02 RMI Purchase Order end-to-end — 19 SPs + API layers + React 18 UI. Full module development completed April; pending JAT DB deployment for IST.
Challenges Faced & How Resolved
1. IST revealed 57 failures in 101-step test cycle (44% pass rate). Root cause: FSD validation assumptions on qtyind column, ABCFLG req type, serial-no generation. Resolved by systematic priority sprint — all 14 High items closed EOD 30 Apr. Re-test confirmed 40/40 PASS.
What I Should Have Done Better / Gaps
Written unit tests before IST handover — higher coverage would have caught several of the 57 IST failures. Should update task log entries daily rather than retrospectively. Must validate DB column names against live schema before writing SPs.
Support or Resources Needed from Management
My Goals for Next Month (specific & measurable)
1. Complete M01 CEO demo sign-off; close all remaining IST items for full 40/40 PASS and production handover. 2. Deploy M02 RMI PO to JAT DB; complete IST testing for PO form; fix PO dropdown UX (code+name combined field). 3. Begin M03 Domestic Sales FSD review and initial development; target IST handover by end June 2026.
Employee Signature & Date
CEO Review & Acknowledgement (date)