## 📋 HOW TO USE
KALSOFTE ERP · MONTHLY WORK SUMMARY TEMPLATE · TEAM USAGE GUIDE
| SUBMISSION RULE | Submit on or before the 3rd of every subsequent month to CEO (ceo@kalsofte.com).
WHO FILLS WHICH SHEET?
| PM – Project Manager | PM Saravanan
| DEV Team – Developer | TL-Dev · VB Developers · Full-Stack & Jr. Web Devs
| IST Team – Support | TL-IST · IST Members (incl. Vertical SMEs)
HOW TO FILL – SECTION B (ATTENDANCE)
| B1 | Enter total calendar days in the month (e.g., 30 for April)
| B2 | Count ALL Sundays + public/gazette holidays in that month
| B3 | AUTO-CALCULATED (B1 – B2). Do not edit.
| B4 | Enter actual days you worked (present days)
| B5 | Enter approved leaves taken (PL / CL / ML)
| B6 | Enter LOP (Loss of Pay) or unauthorised absence days
| B7 | Enter Compensatory Off availed (if any)
| B8 | AUTO-CALCULATED (B4 – B6). Salary eligible days.
| B9 | AUTO-CALCULATED (B4 ÷ B3). Attendance percentage.
| CHECK ROW | Must show ✔ OK before submitting. If ✖ MISMATCH shows, review B1–B6.
HOW TO FILL – TASK LOG
| One row per task | Each CR, ticket, support call, meeting, development item = one row
| ERP Initiative | ERP 7.4 = legacy VB6 ERP ¦ SPINRISE = web migration project ¦ SPINNOVA = AI framework ¦ Internal = HR/admin/training
| Issue Type | Use dropdown: Operational / Corrective CR / Requirement / Implementation / Testing / Documentation / Meeting
| Resolution Status | Use dropdown: Completed / In Progress / Pending / Carry Forward
| Complexity | Low = <1 hr ¦ Medium = 1–4 hrs ¦ High = >4 hrs or architectural
| AI Tool Used | Name the AI tool used (Claude / ChatGPT / Gemini etc.) or None
| SPINRISE STAGE GUIDE | FSD Draft → TL Review → CEO Approval → Dev In Progress → IST Testing → CEO Demo → Deployed
| SELF-APPRAISAL | Mandatory section. Minimum 2 lines per field. This is YOUR professional growth record.
| IMPORTANT | Do NOT break merge cells or delete rows. Add rows inside the task log table if needed.

## PM – Project Manager
KALSOFTE ERP ¦ MONTHLY WORK SUMMARY
ROLE: PROJECT MANAGER · ERP Support · Implementation · BD · SpinRise · SpinNova
SECTION A · EMPLOYEE & SUBMISSION DETAILS
Employee Name
Employee ID / Code
Designation
Vertical / Domain |  |  | Spinning ERP / Paper Mill ERP / Both
Reporting To |  |  | CEO / PM Saravanan
Year & Month |  |  | YYYY-MM
Date of Submission |  |  | DD-MMM-YYYY (due: 3rd of next month)
SECTION B · MONTHLY ATTENDANCE SUMMARY
Metric |  |  |  | Value |  |  | Notes / Auto-Calculation
(B1) Total Days in the Month | [6 empty] | e.g. 31 for March
(B2) Weekly Off Days (All Sundays + Public Holidays) | [6 empty] | Count all Sundays + gazette holidays
(B3) Office Working Days [AUTO] | [6 empty] | AUTO: B1 – B2
(B4) Days Present (Actual Days Worked) | [6 empty] | Days you physically / remotely worked
(B5) Authorised Leave Taken (PL / CL / ML) | [6 empty] | Approved leaves only
(B6) LOP Days (Loss of Pay / Unauthorised Absence) | [6 empty] | Unapproved absence or excess leave
(B7) Comp-Off Availed | [6 empty] | Compensatory off taken
(B8) Salary Eligible Days [AUTO: B4 – B6] | [6 empty] | AUTO: B4 – B6 (enter B4 & B6 first)
(B9) Attendance Rate [AUTO: B4 ÷ B3] | [6 empty] | AUTO: B4 / B3
(B10) Average Hours / Day | [6 empty] | Approx daily hours (include extra hours)
✔ CROSS-CHECK: Month Days = B3 + B2 + B5 + B6 (Must show OK) |  |  |  | Fill B1 to B6 first |  |  | This cell must show ✔ OK before you submit the summary to CEO
SECTION C · MONTHLY KPI SNAPSHOT (fill manually or carry from task log)
Total Tickets / Tasks Managed | [6 empty] | No. of On-Site Visits (Customer)
Remote Demos / Pre-Sales Meetings | [6 empty] | Offers / Proposals Sent
New Leads Generated | [6 empty] | SpinRise Coordination Tasks
SpinNova Coordination Tasks | [6 empty] | Implementation Projects Active
SECTION D · CUSTOMER SUPPORT, IMPLEMENTATION & COORDINATION LOG
S.No | Customer / Project | Module | CR / Ticket No. | Issue / Task Type | ERP Initiative | Effort (hrs) | Description of Work Done (be specific) |  |  | Resolution Status | Complexity | AI Tool Used?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
0 tasks logged ¦ 0 Completed ¦ 0 Pending | [5 empty] | 0
SECTION E · ON-SITE VISITS & FIELD ACTIVITIES
Activity Type |  | Customer / Project |  | Date(s) |  | Outcome / Key Discussions |  |  |  |  | Status
SECTION · BUSINESS DEVELOPMENT & PRE-SALES ACTIVITY LOG
Prospect / Customer |  |  | Vertical | Activity Description |  |  | Stage |  | Offer Sent? | Demo Done? | Next Action | Status
SECTION · REPORTING DISCIPLINE COMPLIANCE
Report / Deliverable Type |  |  |  | Frequency |  | Target |  | Submitted |  | On Time? | Status | Remarks
Daily Work Log (Pulse360 / Logsheet entry) |  |  |  | Daily
Weekly Task Plan |  |  |  | Weekly
Pending CR Status Report |  |  |  | Weekly
Live Implementation Project Status |  |  |  | Weekly
Project / Implementation Schedule Update |  |  |  | Weekly
Monthly Work Summary (this document) |  |  |  | Monthly
SECTION · SKILL ENHANCEMENT & PROFESSIONAL DEVELOPMENT
S.No | Learning Area |  |  | Course / Activity |  |  | Platform / Source |  | Hours Invested | Status | How Applied to Work?
1
2
3
4
5
SECTION · MONTHLY SELF-REFLECTION & PERFORMANCE APPRAISAL
Top 3 Key Accomplishments this Month
Challenges Faced & How Resolved
What I Should Have Done Better / Gaps
Support or Resources Needed from Management
My Goals for Next Month (specific & measurable)
Employee Signature & Date
CEO Review & Acknowledgement (date)

## DEV – Developer
KALSOFTE ERP ¦ MONTHLY WORK SUMMARY
ROLE: DEVELOPER (VB / Web) · ERP 7.4 · SpinRise Migration · SpinNova · Feature Enhancements
SECTION A · EMPLOYEE & SUBMISSION DETAILS
Employee Name
Employee ID / Code
Designation
Vertical / Domain |  |  | Spinning ERP / Paper Mill ERP / Both
Reporting To |  |  | CEO / PM Saravanan
Year & Month |  |  | YYYY-MM
Date of Submission |  |  | DD-MMM-YYYY (due: 3rd of next month)
SECTION B · MONTHLY ATTENDANCE SUMMARY
Metric |  |  |  | Value |  |  | Notes / Auto-Calculation
(B1) Total Days in the Month | [6 empty] | e.g. 31 for March
(B2) Weekly Off Days (All Sundays + Public Holidays) | [6 empty] | Count all Sundays + gazette holidays
(B3) Office Working Days [AUTO] | [6 empty] | AUTO: B1 – B2
(B4) Days Present (Actual Days Worked) | [6 empty] | Days you physically / remotely worked
(B5) Authorised Leave Taken (PL / CL / ML) | [6 empty] | Approved leaves only
(B6) LOP Days (Loss of Pay / Unauthorised Absence) | [6 empty] | Unapproved absence or excess leave
(B7) Comp-Off Availed | [6 empty] | Compensatory off taken
(B8) Salary Eligible Days [AUTO: B4 – B6] | [6 empty] | AUTO: B4 – B6 (enter B4 & B6 first)
(B9) Attendance Rate [AUTO: B4 ÷ B3] | [6 empty] | AUTO: B4 / B3
(B10) Average Hours / Day | [6 empty] | Approx daily hours (include extra hours)
✔ CROSS-CHECK: Month Days = B3 + B2 + B5 + B6 (Must show OK) |  |  |  | Fill B1 to B6 first |  |  | This cell must show ✔ OK before you submit the summary to CEO
SECTION C · MONTHLY KPI SNAPSHOT (fill manually or carry from task log)
Total CRs Completed (Forms + Reports + Fixes) | [6 empty] | SpinRise Modules In Progress
Total Effort Hours | [6 empty] | FSDs Drafted / Submitted
FSDs Approved by CEO | [6 empty] | DB Scripts / Corrections
Code Reviews Done | [6 empty] | AI Tool Usages (no. of sessions)
SECTION D · DEVELOPMENT TASK LOG (CRs · FSDs · Fixes · SpinRise · SpinNova)
S.No | CR / FSD Ref | Module | Customer / Project | ERP Initiative | Task Type | Effort (hrs) | Description / Scope |  | Stage Completed | Review Status | AI Tool Used | Remarks
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
SECTION E · SPINRISE / SPINNOVA MODULE PROGRESS TRACKER
Module Ref | Module Name |  | FSD Version |  | Current Stage |  | Target Date |  | Actual / Est. Date |  | Status | Remarks
SECTION F · INTERNAL MEETINGS & ACTIVITIES
Activity Type |  | Customer / Project |  | Date(s) |  | Outcome / Key Discussions |  |  |  |  | Status
SECTION · REPORTING DISCIPLINE COMPLIANCE
Report / Deliverable Type |  |  |  | Frequency |  | Target |  | Submitted |  | On Time? | Status | Remarks
Daily Work Log (Pulse360 / Logsheet entry) |  |  |  | Daily
Weekly Task Plan |  |  |  | Weekly
Pending CR Status Report |  |  |  | Weekly
Live Implementation Project Status |  |  |  | Weekly
Project / Implementation Schedule Update |  |  |  | Weekly
Monthly Work Summary (this document) |  |  |  | Monthly
SECTION · SKILL ENHANCEMENT & PROFESSIONAL DEVELOPMENT
S.No | Learning Area |  |  | Course / Activity |  |  | Platform / Source |  | Hours Invested | Status | How Applied to Work?
1
2
3
4
5
SECTION · MONTHLY SELF-REFLECTION & PERFORMANCE APPRAISAL
Top 3 Key Accomplishments this Month
Challenges Faced & How Resolved
What I Should Have Done Better / Gaps
Support or Resources Needed from Management
My Goals for Next Month (specific & measurable)
Employee Signature & Date
CEO Review & Acknowledgement (date)

## IST – Support & Testing
KALSOFTE ERP ¦ MONTHLY WORK SUMMARY
ROLE: IST (Implementation · Support · Testing) · ERP 7.4 · SpinRise IST · SpinNova IST
SECTION A · EMPLOYEE & SUBMISSION DETAILS
Employee Name
Employee ID / Code
Designation
Vertical / Domain |  |  | Spinning ERP / Paper Mill ERP / Both
Reporting To |  |  | CEO / PM Saravanan
Year & Month |  |  | YYYY-MM
Date of Submission |  |  | DD-MMM-YYYY (due: 3rd of next month)
SECTION B · MONTHLY ATTENDANCE SUMMARY
Metric |  |  |  | Value |  |  | Notes / Auto-Calculation
(B1) Total Days in the Month | [6 empty] | e.g. 31 for March
(B2) Weekly Off Days (All Sundays + Public Holidays) | [6 empty] | Count all Sundays + gazette holidays
(B3) Office Working Days [AUTO] | [6 empty] | AUTO: B1 – B2
(B4) Days Present (Actual Days Worked) | [6 empty] | Days you physically / remotely worked
(B5) Authorised Leave Taken (PL / CL / ML) | [6 empty] | Approved leaves only
(B6) LOP Days (Loss of Pay / Unauthorised Absence) | [6 empty] | Unapproved absence or excess leave
(B7) Comp-Off Availed | [6 empty] | Compensatory off taken
(B8) Salary Eligible Days [AUTO: B4 – B6] | [6 empty] | AUTO: B4 – B6 (enter B4 & B6 first)
(B9) Attendance Rate [AUTO: B4 ÷ B3] | [6 empty] | AUTO: B4 / B3
(B10) Average Hours / Day | [6 empty] | Approx daily hours (include extra hours)
✔ CROSS-CHECK: Month Days = B3 + B2 + B5 + B6 (Must show OK) |  |  |  | Fill B1 to B6 first |  |  | This cell must show ✔ OK before you submit the summary to CEO
SECTION C · MONTHLY KPI SNAPSHOT (fill manually or carry from task log)
Total Tickets / Tasks Handled | [6 empty] | Total Tickets Resolved (Completed)
Carry Forward / Pending | [6 empty] | Total Effort Hours (approx.)
No. of On-Site Visits | [6 empty] | SpinRise IST Tasks
SpinNova IST Tasks | [6 empty] | Customers Served
SECTION D · ERP SUPPORT & IMPLEMENTATION TASK LOG
S.No | Customer / Project | Module | CR / Ticket No. | Issue / Task Type | ERP Initiative | Effort (hrs) | Description of Work Done (be specific) |  |  | Resolution Status | Complexity | AI Tool Used?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
0 tasks logged ¦ 0 Completed ¦ 0 Pending | [5 empty] | 0
SECTION E · SPINRISE / SPINNOVA MODULE PROGRESS TRACKER
Module Ref | Module Name |  | FSD Version |  | Current Stage |  | Target Date |  | Actual / Est. Date |  | Status | Remarks
SECTION F · ON-SITE VISITS & INTERNAL ACTIVITIES
Activity Type |  | Customer / Project |  | Date(s) |  | Outcome / Key Discussions |  |  |  |  | Status
SECTION · REPORTING DISCIPLINE COMPLIANCE
Report / Deliverable Type |  |  |  | Frequency |  | Target |  | Submitted |  | On Time? | Status | Remarks
Daily Work Log (Pulse360 / Logsheet entry) |  |  |  | Daily
Weekly Task Plan |  |  |  | Weekly
Pending CR Status Report |  |  |  | Weekly
Live Implementation Project Status |  |  |  | Weekly
Project / Implementation Schedule Update |  |  |  | Weekly
Monthly Work Summary (this document) |  |  |  | Monthly
SECTION · SKILL ENHANCEMENT & PROFESSIONAL DEVELOPMENT
S.No | Learning Area |  |  | Course / Activity |  |  | Platform / Source |  | Hours Invested | Status | How Applied to Work?
1
2
3
4
5
SECTION · MONTHLY SELF-REFLECTION & PERFORMANCE APPRAISAL
Top 3 Key Accomplishments this Month
Challenges Faced & How Resolved
What I Should Have Done Better / Gaps
Support or Resources Needed from Management
My Goals for Next Month (specific & measurable)
Employee Signature & Date
CEO Review & Acknowledgement (date)