## PR Form Pilot Tracker
SPINRISE ¦ M01 PR FORM — PILOT READY TRACKER ¦ JAT Spinning Mill ¦ Target: 31 May 2026 (Sunday)
Sprint: Mon 11 May – Sat 31 May 2026 ¦ Team: Abinandan + Hari (from 11 May) + Mariyaiya + Sasi + Palanivel + Muthuvel + Saravanan + CEO
# | Phase | Category | Task Description | Owner | Depends On | Start | Due Date | Days | Priority | Status | Notes / CEO Guidance
PHASE 1 — FOUNDATION ¦ Mon 11 – Wed 13 May
T01 | P1 | FSD & Blueprint | CEO countersign FSD v2.5 (Mariyaiya submits v2.5 tonight — 10 May) | CEO | — | Mon 11 May | Mon 11 May | 1 | CRITICAL | Pending CEO | V2.5 = v2.4 + 6 CEO corrections + Palanivel F-01 to F-14 + Seenivasan inputs + Scope/Sub-Cost Centre removal. Countersignature is the locked baseline. No new development starts before this.
T02 | P1 | FSD & Blueprint | Sasi: review Web Form Blueprint draft → submit to CEO (Abinandan submitted draft to Sasi on 09 May) | Sasi | T01 | Mon 11 May | Mon 11 May | 1 | CRITICAL | In Progress | Sasi reviews Blueprint Monday morning. Submits to CEO before noon. Blueprint defines: screen structure, font, font size, colour standard, SQL 2019 features, Kalsofte development standard. All form development is blocked until Blueprint is CEO-approved.
T03 | P1 | FSD & Blueprint | CEO approves Web Form Blueprint | CEO | T02 | Mon 11 May | Mon 11 May | 1 | CRITICAL | Not Started | CEO working session Monday afternoon. Blueprint approved = green light for all Phase 2 form development. If corrections needed, Abinandan revises and resubmits same day.
T04 | P1 | Open Defects | Abinandan: fix 2 remaining open M01 PR defects | Abinandan | T01 | Mon 11 May | Tue 12 May | 2 | CRITICAL | In Progress | 13 of 16 defects closed from 02 May re-test. 2 remain open. Fix target: Tuesday 12 May morning so Mariyaiya and Muthuvel can re-test Tuesday afternoon.
T05 | P1 | Open Defects | Mariyaiya + Muthuvel: re-test 2 open defects → confirm all 16/16 closed | Mariyaiya Muthuvel | T04 | Tue 12 May | Tue 12 May | 1 | CRITICAL | Not Started | Re-test Tuesday afternoon immediately after Abinandan's fix. Both must confirm PASS. Cumulative target: 16/16 defects fully closed.
T06 | P1 | Component | Sasi: review component library comparison → give formal technical decision to team (Abinandan submitted on 09 May) | Sasi | — | Mon 11 May | Tue 12 May | 2 | HIGH | Not Started | Comparison covers: grid performance, keyboard navigation, bundle size, licence terms. Sasi must give a formal decision on which grid component SPINRISE will use. This affects all form and list screen development.
T07 | P1 | Process | Abinandan: document AI (Claude) review process gate — define responsible owner and starting form | Abinandan | T03 | Tue 12 May | Wed 13 May | 2 | HIGH | Not Started | CEO/MoM action item. One-page process note: who submits to Claude before IST, which form it starts from, what the review output looks like. Submit to CEO for approval.
T08 | P1 | Filter Requirements | Palanivel + Seenivasan: filter requirements decision document for PR Form and PR List Screen (4 confirmed filters) | Palanivel Seenivasan | — | Mon 11 May | Wed 13 May | 3 | HIGH | Not Started | 4 confirmed filters: Approval Status multi-select, PR Date range (default current FY), Department, Requester. Formal document confirming these 4. Submit to CEO by Wednesday 13 May.
PHASE 2 — FORM BUILD ¦ Mon 11 – Fri 22 May
T09 | P2 | Login Screen | Abinandan: redesign login screen — all CEO demo corrections applied Hari: CSS and static layout | Abinandan Hari | T03 | Mon 11 May | Tue 12 May | 2 | CRITICAL | In Progress | Corrections required: date, time, company name, division name, PO name. Standard: CSM/Subam Portal reference. Hari handles CSS styling and static elements. Abinandan handles data binding and logic.
T10 | P2 | Login Screen | CEO review and approval: login screen (CEO working session) | CEO | T09 | Wed 13 May | Wed 13 May | 1 | CRITICAL | Not Started | CEO working session Wednesday 13 May. Abinandan presents on internal server 172.16.16.40:3000. Decisions made live. Corrections (if any) done same day by Abinandan.
T11 | P2 | PR Form — Layout | Abinandan: single-screen PR Form redesign — no vertical scroll, compact layout per Blueprint Hari: layout CSS, static components | Abinandan Hari | T03,T10 | Wed 13 May | Sat 16 May | 4 | CRITICAL | Not Started | Blueprint-driven redesign. Single screen. No vertical scroll. All fields visible without scrolling. Hari builds layout CSS and non-dynamic components in parallel. Abinandan builds form logic and field rules.
T12 | P2 | PR Form — KPI Strip | Abinandan: KPI Summary Strip — 5-card layout (1) Total Lines (2) Total Qty UOM-grouped (3) Approx Budget (4) Created By (5) Approval Status Add mode suppression rule | Abinandan | T11 | Wed 13 May | Thu 14 May | 2 | CRITICAL | Not Started | CEO Decision R2.0 items #17 and #29. KPI strip hidden in ADD mode — shown only after save or in VIEW/MODIFY mode. UOM grouping: show separate totals per UOM (e.g., 2 items in KG + 3 items in boxes = two totals).
T13 | P2 | PR Form — Fields | Abinandan: field-level corrections (all 5): — Decimal: Qty 3dp, Rate 4dp, Value 2dp — Unit price duplicate symbol fix — Sample field default = No — Value field width increase — PR Date: editable, auto-populate login date | Abinandan | T11 | Thu 14 May | Fri 15 May | 2 | CRITICAL | Not Started | CEO standard: Qty=3dp, Rate=4dp, Value/Amount=2dp. PR Date default = processing date but editable. CEO Decision R2.0 #10 and #13.
T14 | P2 | PR Form — Validation | Abinandan: tab sequence + focus-out validation — mandatory fields block tab if empty — universal rule: all 5 mandatory fields (PR Date, Dept Code, PR Type, Item Code, Qty Required) | Abinandan | T11 | Thu 14 May | Fri 15 May | 2 | CRITICAL | Not Started | Focus-out = server-side validation triggered on field exit. Universal rule applies to all SPINRISE transaction entry screens (CEO Correction 4 from FSD v2.5). Not just PR Form.
T15 | P2 | PR Form — Rate Selector | Abinandan: rate selector — 3-option toggle (1) Last PO Rate (2) Average Rate (3) Manual Entry + mandatory Justification field New DB: PO_PRL.RATE_SOURCE, PO_PRL.RATE_JUSTIFICATION | Abinandan | T11 | Fri 15 May | Mon 18 May | 2 | CRITICAL | Not Started | CEO Decision R2.0 #14. Replaces dead-code Rate_Find(). Justification mandatory when Manual Entry selected. API must save both new columns to DB.
T16 | P2 | PR Form — Item Thumbnail | Abinandan: item thumbnail in grid line and lookup modal Source: IN_ITEM.IMAGE Hari: builds image component | Abinandan Hari | T11 | Fri 15 May | Mon 18 May | 2 | HIGH | Not Started | CEO Decision R2.0 #11 and #12. Grid line: small thumbnail ~32×32px. Lookup modal: larger ~80×80px. Hari builds the reusable image component. Abinandan wires the data binding.
T17 | P2 | PR Form — Add Multiple | Abinandan: Add Multiple — 2 interaction modes (1) Multi-select lookup: tick items, insert all (2) Row-count insert: specify N rows, blank rows added Customer originators: Pallvaa Mills, SKS | Abinandan | T11 | Mon 18 May | Tue 19 May | 2 | HIGH | Not Started | CEO Decision R2.0 #15 and #16. Both modes required. Named customer originators must appear in code comment.
T18 | P2 | PR Form — Budget Category | Abinandan: Budget Category conditional field — visible only for paper mill Capital PRs — New DB column: PO_PRL.BUDGETCAT | Abinandan | T11 | Mon 18 May | Tue 19 May | 2 | HIGH | Not Started | CEO Decision R2.0 #27. Conditional: show only when PR Type = Capital AND mill type = Paper Mill. JAT is a spinning mill — this field will be hidden at JAT. But must be implemented per FSD.
T19 | P2 | PR Form — PR Type Default | Abinandan: PR Type configurable default — New: PO_PARA.DefaultPRType parameter | Abinandan | T11 | Mon 18 May | Tue 19 May | 2 | MEDIUM | Not Started | CEO Decision R2.0 #28. Read PO_PARA.DefaultPRType on form load. JAT to confirm their default PR Type for pilot configuration before T27.
T20 | P2 | PR List Screen | Abinandan: PR List Screen — full build Approval status badge colour-coding: Requested=Blue, First Level=Teal, Before Final=Amber Final=Green, PO Raised=Purple, Cancelled=Red 4 filters + Catalogue Number + Required Date columns Hari: colour badge components | Abinandan Hari | T08,T11 | Tue 19 May | Thu 21 May | 3 | CRITICAL | Not Started | Palanivel F-10 input. Added in FSD v2.5 Section 10. Primary navigation screen for all PR transactions. Must be production-quality for pilot. Hari builds the reusable colour badge component.
T21 | P2 | Printout | Abinandan: printout corrections (QuestPDF) — Total Value in footer — Date-time stamp in footer — PR Time adjacent to PR Date — No red form name label — Kalsofte header/footer standard Hari: QuestPDF PDF layout template | Abinandan Hari | T11 | Wed 20 May | Fri 22 May | 3 | HIGH | Not Started | QuestPDF is confirmed print technology (not Crystal Reports). Hari builds the PDF layout template. Abinandan wires data bindings and API endpoint POST /api/purchase-requisitions/{id}/print.
T22 | P2 | UI/UX Cycle | Saravanan: UI/UX approval cycle process template (Developer → IST → TL-IST → PM → CEO) Palanivel reviews | Saravanan Palanivel | — | Mon 11 May | Fri 15 May | 5 | HIGH | Not Started | MoM Action Item #11. Template must define: checklist per screen, review turnaround time, sign-off format. Applies to PR Form first, then all subsequent SPINRISE screens.
PHASE 3 — IST & CEO REVIEW ¦ Sat 23 – Wed 28 May
T23 | P3 | CEO Review | CEO full working session: complete PR Form review — all Phase 2 items must be done — live review on internal server | CEO Abinandan Mariyaiya Sasi | T09–T22 | Sat 23 May | Mon 25 May | 2 | CRITICAL | Not Started | CEO reviews complete build on 172.16.16.40:3000. All Phase 2 tasks must be deployed. Decisions made live in session. Abinandan acts on feedback same day or next morning. This is the internal acceptance gate.
T24 | P3 | IST Review | Muthuvel: full IST review of PR Form — using IST FSD Review Checklist v1.1 — review on internal server, not just FSD | Muthuvel | T23 | Mon 25 May | Tue 26 May | 2 | CRITICAL | Not Started | Domain-level IST review. Muthuvel tests on internal server: field behaviour, tab sequence, print output, approval workflow, filter behaviour. Raises findings using IST checklist. Target: all findings submitted to Palanivel by Tuesday 26 May evening.
T25 | P3 | TL-IST Review | Palanivel: TL-IST review — consolidate Muthuvel's findings — add TL-IST commentary — submit to CEO | Palanivel | T24 | Wed 27 May | Wed 27 May | 1 | CRITICAL | Not Started | Palanivel adds independent TL-IST commentary on critical findings. Confirms filter requirements document is resolved. Submits consolidated findings to CEO by Wednesday 27 May evening.
T26 | P3 | Defect Fixes | Abinandan + Hari: fix all IST findings — CRITICAL findings: same day — All others: by Thursday 28 May | Abinandan Hari | T25 | Wed 27 May | Thu 28 May | 2 | CRITICAL | Not Started | Target: zero open defects after IST round. CRITICAL findings fixed within hours of receipt. Non-critical fixed by Thursday 28 May morning. Mariyaiya confirms each fix before marking closed.
PHASE 4 — PILOT PREP ¦ Thu 29 – Sun 31 May
T27 | P4 | CEO Sign-off | CEO final sign-off: PR Form approved for pilot — review defect-fix build — authorise JAT deployment | CEO | T26 | Thu 29 May | Thu 29 May | 1 | CRITICAL | Not Started | CEO reviews Abinandan's defect-fix build on internal server. If zero critical defects: sign-off given same day. Pilot deployment to JAT authorised.
T28 | P4 | Pilot Prep | JAT Spinning Mill — pilot environment setup — server deployment or remote access setup — JAT master data load from Kalsofte ERP (suppliers, items, departments, cost centres, users) | Sasi Abinandan | T27 | Thu 29 May | Fri 30 May | 2 | CRITICAL | Not Started | Deployment to JAT's server or a dedicated SPINRISE pilot server accessible from JAT plant. Master data: load from JAT's live Kalsofte ERP database. User logins configured. Basic sanity test by Sasi before handover to Saravanan.
T29 | P4 | JAT Walkthrough | Saravanan + Muthuvel: JAT MD / key user walkthrough — PR Form live demonstration — structured feedback form collected | Saravanan Muthuvel | T28 | Fri 30 May | Fri 30 May | 1 | CRITICAL | Not Started | PM Saravanan presents. Muthuvel handles domain queries. Structured feedback form: UI, workflow, field names, print output, speed, missing requirements. Collect written feedback during session. JAT MD and at least 2 store staff must participate.
T30 | P4 | Pilot Feedback | CEO reviews JAT feedback — categorise: Critical Fix / Enhancement / Accepted — Critical fixes done same day if feasible | CEO Abinandan | T29 | Sat 31 May | Sat 31 May | 1 | CRITICAL | Not Started | CEO reviews JAT feedback on Saturday morning 31 May. Categorises each item. Critical fixes (if any): Abinandan acts same day. Enhancement log created for Sprint 2. Pilot Go/No-Go decision by 31 May 6 PM.
T31 | P4 | MILESTONE | 🎯 M01 PR FORM — PILOT READY Delivered to JAT Spinning Mill 31 May 2026 | CEO | T30 | Sat 31 May | Sat 31 May | 1 | CRITICAL | Not Started | Target milestone. PR Form live and validated at JAT Spinning Mill. First SPINRISE transaction in use at a customer site. Foundation for M01 full module delivery.
LEGEND
CRITICAL | Pilot delivery blocked if missed |  | HIGH | Important — plan specifically |  | MEDIUM | Value-add — include in sprint |  | Not Started
In Progress |  |  | Pending CEO | Awaiting CEO decision/approval |  | Done | Completed and verified |  | Blocked | Cannot proceed — escalate same day

## Weekly Sprint Plan
SPINRISE M01 PR Form ¦ Weekly Sprint Plan ¦ 11 May – 31 May 2026 ¦ Pilot Target: JAT Spinning Mill
# | Week / Days | Focus and Key Deliverables | Primary Owners | Gate Date | Status | CEO Action / Review Point
1 | Week 1 Mon 11 – Sat 16 May (6 working days) | T01 FSD v2.5 countersignature — CEO T02 Blueprint review — Sasi → submit to CEO T03 Blueprint CEO approval (Monday) T04 Fix 2 open defects — Abinandan (Mon–Tue) T05 Re-test 2 defects — Mariyaiya + Muthuvel (Tue) T06 Component library decision — Sasi (by Tue) T07 AI review process gate document — Abinandan (by Wed) T08 Filter requirements document — Palanivel + Seenivasan (by Wed) T09 Login screen redesign — Abinandan + Hari (Mon–Tue) T10 Login screen CEO review (Wed) T11 Single-screen PR Form layout redesign — Abinandan + Hari (Wed–Sat) T12 KPI Summary Strip — Abinandan (Thu–Fri) T22 UI/UX cycle process template — Saravanan (by Fri 15 May) | Abinandan (form dev) Hari (CSS, components) Sasi (decisions) Mariyaiya+Muthuvel (retest) CEO (T01,T03,T10) | Sat 16 May | Not Started | Mon 11 May: CEO working session — Blueprint approval (30 min) Wed 13 May: CEO working session — Login screen review (30 min) Sat 16 May: Weekly review meeting (5 PM). All Week 1 tasks must be DONE. Gate: Phase 1 complete. Blueprint approved. Login screen approved. Form layout started.
2 | Week 2 Mon 18 – Sat 23 May (6 working days) | T13 Field-level corrections (decimal, date, sample, value width) — Abinandan T14 Tab sequence + focus-out validation — Abinandan T15 Rate selector — 3 options + justification field — Abinandan T16 Item thumbnail in grid and modal — Abinandan + Hari T17 Add Multiple — 2 modes — Abinandan T18 Budget Category conditional field — Abinandan T19 PR Type configurable default — Abinandan T20 PR List Screen — full build with colour-coded badges — Abinandan + Hari T21 Printout corrections — QuestPDF — Abinandan + Hari | Abinandan (all form logic) Hari (thumbnail, badges, print template) | Sat 23 May | Not Started | CEO daily working sessions: 30 min each evening. Abinandan deploys to 172.16.16.40:3000 every evening before session. CEO reviews latest build — decisions made same day. Sat 23 May: Weekly review meeting (5 PM). All Phase 2 tasks must be DONE.
3 | Week 3 Mon 25 – Thu 28 May (4 working days) | T23 CEO full working session: complete form review (Mon 25 May) T24 Muthuvel: IST review using checklist v1.1 (Mon–Tue) T25 Palanivel: TL-IST consolidated findings → CEO (Wed) T26 Abinandan + Hari: fix all IST findings (Wed–Thu) | CEO (T23) Muthuvel (T24) Palanivel (T25) Abinandan+Hari (T26) | Thu 28 May | Not Started | Mon 25 May: CEO full form review session — 2 hours minimum. IST review starts ONLY after CEO sign-off from T23. Target: ZERO open defects by Thursday 28 May evening. Gate: Form accepted internally. Ready for customer deployment.
4 | Week 4 Fri 29 – Sat 31 May (2 working days + Sunday milestone) | T27 CEO final sign-off — authorise JAT deployment (Fri 29 May) T28 JAT environment setup — Sasi + Abinandan (Fri 29 May) T29 JAT MD + key user walkthrough — Saravanan + Muthuvel (Sat 30 May) T30 CEO reviews JAT feedback — categorise + critical fixes (Sat 30 May evening) T31 🎯 M01 PR FORM PILOT READY — JAT Spinning Mill (Sun 31 May) | CEO (T27,T30) Sasi+Abinandan (T28) Saravanan+Muthuvel (T29) | Sun 31 May | Not Started | Fri 29 May: CEO sign-off — if zero critical defects from IST. Sat 30 May: JAT walkthrough — minimum JAT MD + 2 store staff. Sat 30 May evening: CEO reviews feedback, categorises items. Sun 31 May: Pilot Go/No-Go decision by CEO. Target CONFIRMED DELIVERED.

## Team Responsibility Matrix
SPINRISE M01 PR Form ¦ Team Responsibility Matrix ¦ Sprint: Mon 11 May – Sun 31 May 2026
# | Team Member | Role in This Sprint | Abinandan | Hari | Mariyaiya | Sasi | Palanivel Muthuvel | Saravanan CEO
1 | Abinandan | Full-stack developer — exclusive SPINRISE. All form coding, API, DB, business logic. Primary delivery owner for 31 May pilot. | LEAD | ASSIGNS | REVIEWS | CONSULTS | INPUT | REPORTS TO
2 | Hari | Junior web developer — from Mon 11 May. UI tasks: CSS, thumbnail component, colour badges, QuestPDF print layout. Daily task list assigned by Abinandan. | ASSIGNS | LEAD | — | — | — | REPORTS TO
3 | Mariyaiya | Module developer and domain expert. FSD v2.5 maintenance. Defect re-test confirmation. Domain guidance in CEO working sessions. | SUPPORTS | — | LEAD | REVIEWS | INPUT | REPORTS TO
4 | Sasi | TL-Dev. Blueprint review and approval submission. Component library decision. Available for complex technical blockers. Not in daily development. | CONSULTS | — | — | LEAD | — | REPORTS TO
5 | Palanivel | TL-IST. Filter requirements document (T08). UI/UX cycle template review (T22). TL-IST review Week 3 (T25). Consolidated findings to CEO. | — | — | — | — | LEAD (TL-IST) | REPORTS TO
6 | Muthuvel | IST reviewer. Defect re-test Week 1 (T05). Full IST review Week 3 (T24). JAT walkthrough support (T29). | — | — | REVIEW | — | LEAD (IST) | REPORTS TO
7 | Saravanan | PM. UI/UX cycle template (T22). JAT walkthrough (T29). PM sign-off coordination. Daily progress tracking. | — | — | — | — | COORDINATES | LEAD (PM)
8 | CEO | Final authority. Blueprint approval (Mon 11 May). Daily 30-min working sessions (Weeks 1–2). Full review session (Mon 25 May). Final sign-off (Fri 29 May). JAT pilot Go/No-Go (Sat/Sun 30–31 May). | DIRECTS | DIRECTS | DIRECTS | DIRECTS | DIRECTS | LEAD (CEO)
SPINRISE Project ¦ Kalpatharu Software Ltd ¦ CONFIDENTIAL ¦ Target: Pilot Ready JAT Spinning Mill — 31 May 2026