## 01.04.25
Daily Work Plan - 01.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKY | Knsales | Stock updation query preparation
2 |  | Bannari | PPC | YR report correction
3 |  | Bannari Wvg | Sales | Packing entry and sale day book Issue
4 |  | SSVDB | FA | Internay CR points
5 |  | SKS | FA | Pending CR points |  | Completed
6 |  | Kumaragiri | Payroll | AUDIT FINDINGS 1. Attendance to be marked as present on the date of joining. 2. In the wage statement, Per day Wage / Monthly wage as in Payslip to be included in the report. 3. Wage statement , Attendance, time card , Payslip - Designation wise , Department wise filter option is required.
7 |  | Blue Weaves |  | Year end support for Yinvy and sales |  | Completed
1 | Annamalai | SCMtS | D Sales | Opening stock updation
2 |  | SKS | SPG | Reports-->Periodical-->Production-->Framewise customized option new format report to be needed as per their below mentioned format
3 |  | SKS | SPG | Reports-->Periodical-->Stoppage-->Loss in utilisation-->Customised option to be needed for Date wise and Machine wise report as per below mentioned format
4 |  | VTS | SPG | CR points
5 |  | Cheran | D Sales | Bar code scanning issue |  | Completed
6 |  | Pallavaa | Post Spg | Machine duplicatio issue
7 |  | SKS | QC | Operational CR points
1 | Maari | SKS | RMI | Transactions-->Freight Purchase bill entry form the following changes to be needed
2 |  | SKS | RMI | COTTON JOB WORK FORM REQUIRED. CR to be taken after finaisation.
3 |  | SSVDB | Import | SSVDB Import & RMI Module Corrective CR_28.03.2025 - reg - c)Supplier Weight Entry: i.Enable manual entry of Supplier Weight. ii.Add validation to ensure that Supplier Weight does not exceed Invoice Quantity. iii.Remove Container No coulmn.
4 |  | SSVDB | Import | SSVDB Import & RMI Module Corrective CR_28.03.2025 - reg - b)Variety Lookup Update: When selecting the variety lookup, display only the total quantity and bale count, not container-wise.
5 |  | SSVDB | Import | SSVDB Import & RMI Module Corrective CR_28.03.2025 - reg - 1.Transactions - RMI Receipt a)Change listing functionality: Switch from Container-based listing to Trailer-based listing.
6 |  | Subam | Invy | Stores Inventory - Job Order – Delivery Challan – Reg.
1 | Mariya | Space textile | CSM | Consolidated Report - Yarn stock |  | Completed
2 |  | Space textile | CSM | Work order to Sale order convert API creation
3 |  | SKS |  | IRN generation support
4 |  | Cherfan |  | IRN generation support
5 |  | Bannari HT |  | Year end process support
1 | Udhay | SKS | Scrap | Transactions-->Scrap Out pass transaction print the following changed to be needed |  | Completed | Form correction required
2 |  | SKS | Payroll | Reports - Personal Information Reports correction
3 |  | Blue Weaves | Wvg Sales | Packing slip correction
4 |  | Admin |  | Admin work |  | Completed
1 | Siranjeevi | Space textile | CSM | CSM - MIS - Sale Order Status - Internal CR 28 - Reg - 2.Need provision to download this report in a PDF format. |  | Inprogress
2 |  | Space textile | CSM | Order Completion Report (OCR) |  | Inprogress
3 |  | Space textile | CSM | CSM - MIS - Sale Order Status - Internal CR 28 - Reg - a.Need to add Order Ref No. in Sale Contract Selection look up. b.Next to finance details, need to add Payment Details with the following fields |  | Inprogress
4 |  | Pallavaa | Web Approval | User Rights - Web approval for new user |  | Completed
5 |  | Space textile |  | Feedback corrections
1 | Seeni | Chrean | Lsales | Invoice entry coordination and pending CR points completion |  | Partially Completed
2 |  | SCM Goupp |  | Domestic sales latest testing and updation for SCM Spinners unit-2, JAT, SCM Mills
3 |  | Gomathi | Invy | Sign off should be completed
4 |  | SCMTS | Lsales | Opening stock updation
5 |  | SSVDB | Invy | Entry support to Karthikeyan |  | Completed
6 |  | Blue Weaves | Canteen | Canteen report not open issue
7 |  | All |  | Year end process support |  | Completed
1 | Vignesh | Space textile |  | Implementation support
2 |  | VTS | Post Spg | Autoconer VS RG1 report coordination and completion
3 |  | Bannari | PPC | YR Coordination and completion and implementation |  | Inprogress
4 |  | Pallavaa |  | Operational issue completion
5 |  | SKS | QC | Productopn and QC CR coordination and completion.
|  |  | Prodn | Year end process support |  | Completed
1 | Muthuvel | SSVDB |  | Onsite Visit
|  | All |  | Year end process support
1 | Palanivel | SkS |  | Onsite Visit
|  | All |  | Year end process support
1 | KarthiKeyan | SSVDB |  | Onsite Visit
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi | 7 | 2 | 5
|  |  | 2 | Annamalai | 7 | 1 | 6
|  |  | 3 | Maari | 6 |  | 6
|  |  | 4 | Mariya | 5 | 1 | 4
|  |  | 5 | Udhay | 4 | 2 | 2
|  |  | 6 | Siranjeevi | 5 | 1 | 4
|  |  | 7 | Seeni | 7 | 2 | 5
|  |  | 8 | Muthuvel | 2 | 2 | 0
|  |  | 9 | Vignesh | 5 | 1 | 4
|  |  | 10 | Palanivel | 2 | 2 | 0
|  |  | 11 | KarthiKeyan | 1 | 1 | 0
|  |  |  | Total CR Points | 51 | 15 | 36

## 02.04.25
Daily Work Plan - 02.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKY | Knsales | Stock updation query preparation
2 |  | Bannari | PPC | YR report correction |  | Completed
3 |  | Bannari Wvg | Sales | Packing entry and sale day book Issue
4 |  | SSVDB | FA | Internay CR points
6 |  | Kumaragiri | Payroll | AUDIT FINDINGS 1. Attendance to be marked as present on the date of joining. 2. In the wage statement, Per day Wage / Monthly wage as in Payslip to be included in the report. 3. Wage statement , Attendance, time card , Payslip - Designation wise , Department wise filter option is required. |  | Inprogress
|  | Bannari Wvg | Yinvy | year end process |  | Completed | Unplanned
|  | Poongodhai |  | year end process |  | Completed | Unplanned
|  | SCMTS | RMI | RMI stock issue |  | Inprogress | Unplanned
1 | Annamalai | SCMtS | D Sales | Opening stock updation |  | Partially Completed
2 |  | SKS | SPG | Reports-->Periodical-->Production-->Framewise customized option new format report to be needed as per their below mentioned format
3 |  | SKS | SPG | Reports-->Periodical-->Stoppage-->Loss in utilisation-->Customised option to be needed for Date wise and Machine wise report as per below mentioned format
4 |  | VTS | SPG | CR points
6 |  | Pallavaa | Post Spg | Machine duplicatio issue
7 |  | Pallavaa | Spg | MIS - Upto date Actual UKG is showing wrong for SCSL3 - In production MIS report
1 | Maari | SKS | RMI | Transactions-->Freight Purchase bill entry form the following changes to be needed
3 |  | SSVDB | Import | SSVDB Import & RMI Module Corrective CR_28.03.2025 - reg - c)Supplier Weight Entry: i.Enable manual entry of Supplier Weight. ii.Add validation to ensure that Supplier Weight does not exceed Invoice Quantity. iii.Remove Container No coulmn.
4 |  | SSVDB | Import | SSVDB Import & RMI Module Corrective CR_28.03.2025 - reg - b)Variety Lookup Update: When selecting the variety lookup, display only the total quantity and bale count, not container-wise.
5 |  | SSVDB | Import | SSVDB Import & RMI Module Corrective CR_28.03.2025 - reg - 1.Transactions - RMI Receipt a)Change listing functionality: Switch from Container-based listing to Trailer-based listing.
6 |  | Subam | Invy | Stores Inventory - Job Order – Delivery Challan – Reg.
7 |  | SSVDB | GMS | SSVDB - Gate Movements Internal CR - 1 |  | Completed
8 |  | Pallavaa | Invy | Stock issue correction |  | Completed | Unplanned
9 |  | Shiva II | Invy | Consumption value not match with stock report |  | Completed
10 |  | SCMTS | RMI | PO - import gst calculation issue |  | Completed
11 |  | Pallavaa | PO | Parameter po approval modification issue |  | Completed
1 | Mariya | Space textile | CSM | Work order to Sale order convert API creation |  | Partially Completed
2 |  | SKS |  | IRN generation support |  | Completed
3 |  | Cherfan |  | IRN generation support |  | Completed
4 |  | Bannari HT |  | Year end process support
1 | Udhay | SKS | Payroll | Reports - Personal Information Reports correction |  |  | Form correction required
2 |  | Blue Weaves | Wvg Sales | Packing slip correction |  | Closed
3 |  | Motherland |  | Salary Statement - Printing out side of the paper-Reg |  | Completed
4 |  | SRG |  | RMI - ISSUSE report ERROR. |  | Completed
1 | Siranjeevi | Space textile | CSM | CSM - MIS - Sale Order Status - Internal CR 28 - Reg - 2.Need provision to download this report in a PDF format. |  | Completed
2 |  | Space textile | CSM | Order Completion Report (OCR) |  | Completed
3 |  | Space textile | CSM | CSM - MIS - Sale Order Status - Internal CR 28 - Reg - a.Need to add Order Ref No. in Sale Contract Selection look up. b.Next to finance details, need to add Payment Details with the following fields
5 |  | Space textile |  | Feedback corrections |  | Completed
1 | Seeni | Chrean | Lsales | Invoice entry coordination and pending CR points completion |  | Completed
2 |  | SCM Goupp |  | Domestic sales latest testing and updation for SCM Spinners unit-2, JAT, SCM Mills
3 |  | Gomathi | Invy | Sign off should be completed |  | Completed
4 |  | SCMTS | Lsales | Opening stock updation |  | Partially Completed
6 |  | Blue Weaves | Canteen | Canteen report not open issue
|  | All |  | Year end process support for not completed customers
1 | Vignesh | Space textile |  | Implementation support
2 |  | VTS | Post Spg | Autoconer VS RG1 report coordination and completion
3 |  | Bannari | PPC | YR Coordination and completion and implementation |  | Completed
4 |  | Pallavaa |  | Operational issue completion
6 |  |  | Prodn | Year end process support
1 | Muthuvel | SSVDB |  | Onsite Visit |  | Completed
|  | All |  | Year end process support |  | Inprogress
1 | Palanivel | SkS |  | Onsite Visit |  | Completed
|  | All |  | Year end process support |  | Inprogress
1 | KarthiKeyan | SSVDB |  | Onsite Visit |  | Completed
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi
|  |  | 2 | Annamalai
|  |  | 3 | Maari
|  |  | 4 | Mariya
|  |  | 5 | Udhay
|  |  | 6 | Siranjeevi
|  |  | 7 | Seeni
|  |  | 8 | Muthuvel
|  |  | 9 | Vignesh
|  |  | 10 | Palanivel
|  |  | 11 | KarthiKeyan
Total CR Points

## 03.04.25
Daily Work Plan - 04.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKY | Knsales | Stock updation query preparation
3 |  | Bannari Wvg | Sales | Packing entry and sale day book Issue
4 |  | SSVDB | FA | Internay CR points
5 |  | Kumaragiri | Payroll | AUDIT FINDINGS 1. Attendance to be marked as present on the date of joining. 2. In the wage statement, Per day Wage / Monthly wage as in Payslip to be included in the report. 3. Wage statement , Attendance, time card , Payslip - Designation wise , Department wise filter option is required. |  | Inprogress
6 |  | SCMTS | RMI | RMI stock issue |  | Completed | Unplanned
7 |  | SKS |  | SKS Mills - FA - Customer CR 020425 |  | Completed
8 |  | Poongodhai | Yinvy | Year end process |  | Completed
1 | Annamalai | SCMtS | D Sales | Opening stock updation for trading division |  | Completed
2 |  | SKS | SPG | Reports-->Periodical-->Production-->Framewise customized option new format report to be needed as per their below mentioned format
3 |  | SKS | SPG | Reports-->Periodical-->Stoppage-->Loss in utilisation-->Customised option to be needed for Date wise and Machine wise report as per below mentioned format
4 |  | VTS | SPG | CR points
6 |  | Pallavaa | Post Spg | Machine duplicatio issue
7 |  | Pallavaa | Spg | MIS - Upto date Actual UKG is showing wrong for SCSL3 - In production MIS report
1 | Maari | SKS | RMI | Transactions-->Freight Purchase bill entry form the following changes to be needed
2 |  | SSVDB | RMI | The validation to be place while saving the record if the mill weight is empty. Presently the validation showing irrelevant and becomes trouble for data entry |  | Completed
3 |  | SSVDB | RMI | In modification - need to modify the Bill No field and TDS Type modification in case of Wrong TDS selection, befor approval. |  | Completed
4 |  | SSVDB | Import | SSVDB Import & RMI Module Corrective CR_28.03.2025 - reg - 1.Transactions - RMI Receipt a)Change listing functionality: Switch from Container-based listing to Trailer-based listing.
5 |  | ALL |  | Operational issue completion then and there - SKY and SRG invy opeining stock issue completed |  | Completed
1 | Mariya | Space textile | CSM | Work order to Sale order convert API creation |  | Completed
2 |  | Cheran |  | Barcode scanning
3 |  | Bannari HT |  | Year end process support
1 | Udhay | SKS | Payroll | Reports - Personal Information Reports correction |  |  | Form correction required
2 |  | SSVDB | RMI | 1. Transactions - Receipt Waster Paper and Fuel report correction |  | Completed
3 |  | SSVDB | RMI | Transactions - Paper Invoice and Fuel Invoice print correction |  | Completed
4 |  | SSVDB | RMI | 1. Reports - Stock Statement
1 | Siranjeevi | Space textile | CSM | CSM - MIS - Sale Order Status - Internal CR 28 - Reg - a.Need to add Order Ref No. in Sale Contract Selection look up. b.Next to finance details, need to add Payment Details with the following fields
2 |  | SSVDB | Web Approval | Import PO correction in approval |  | Completed
3 |  | Subam |  | Automail issue |  | Completed
4 |  | Space textile | CSM | OCR report feedback corrections
1 | Seeni | SCMTS | Lsales | Opening stock updation |  | Completed
2 |  | SCM Goupp |  | Domestic sales latest testing and updation for SCM Spinners unit-2, JAT, SCM Mills
3 |  | Gomathi | Invy | Sign off should be completed
4 |  | Blue Weaves | Canteen | Canteen report not open issue |  | Completed
5 |  | Bannari Wvg | Stores | Year end process |  | Completed
6 |  | Blue Weaves | Stores | stores and canteen
7 |  | All |  | Year end process support for not completed customers
1 | Vignesh | Space textile |  | Implementation support
2 |  | VTS | Post Spg | Autoconer VS RG1 report coordination and completion
3 |  | Bannari | PPC | YR Coordination and completion and implementation |  | Completed
4 |  | Pallavaa |  | Operational issue completion
5 |  |  | Prodn | Year end process support |  | Completed
6 |  | Marketing |  | Stataus prepartion |  | Completed
1 | Muthuvel | SSVDB |  | Onsite Visit |  | Completed
2 |  | All |  | Year end process support |  | Inprogress
1 | Palanivel | SkS |  | Onsite Visit |  | Completed
2 |  | All |  | Year end process support |  | Inprogress
1 | KarthiKeyan | SSVDB |  | Onsite Visit |  | Completed
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi | 8 | 4 | 4
|  |  | 2 | Annamalai | 7 | 1 | 6
|  |  | 3 | Maari | 5 | 3 | 2
|  |  | 4 | Mariya | 3 | 1 | 2
|  |  | 5 | Udhay | 4 | 2 | 2
|  |  | 6 | Siranjeevi | 4 | 4 | 0
|  |  | 7 | Seeni | 7 | 3 | 4
|  |  | 8 | Muthuvel | 2 | 1 | 1
|  |  | 9 | Vignesh | 6 | 3 | 3
|  |  | 10 | Palanivel | 2 | 1 | 1
|  |  | 11 | KarthiKeyan | 1 | 1 | 0
|  |  |  | Total CR Points | 49 | 24 | 25

## 04.04.25
Daily Work Plan - 04.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKS | FA | Payment request - TDS provision |  | Inprogress
2 |  | Cheran | Payroll | Incentive issue |  | Completed
3 |  | Kumargiri | Payroll | The below security Token number 5315 belongs to general shit (08:00 Am to 05:00 PM) whereas his attendance shows night shift only . (10 PM to 06 AM).For the Jan'25 & Mar'25 it shows for general shift rest all other months it is for night shift. Requirement is General shift except on NFH day
4 |  | SSVDB | FA | Internay CR points
5 |  | Kumaragiri | Payroll | AUDIT FINDINGS 1. Attendance to be marked as present on the date of joining. 2. In the wage statement, Per day Wage / Monthly wage as in Payslip to be included in the report. 3. Wage statement , Attendance, time card , Payslip - Designation wise , Department wise filter option is required. |  | Inprogress
6 |  | SSVDB | RMI | In the SSVDB RMI Module, the Housekeeping FA-related Parameter (TC='79') is facing an issue where the Coal Purchase GL and Freight GL codes are unable to be mapped
1 | Annamalai | SCMtS | D Sales | Opening stock updation feedback corrections if any |  | Completed
2 |  | SSVDB | Paper Sales | Discount corrections |  | Completed
3 |  | SKS | Lsales | Invoice print - Pack No print correction. |  | Completed
4 |  | VTS | SPG | CR points
5 |  | Pallavaa | Post Spg | Machine duplicatio issue
6 |  | Pallavaa | Spg | MIS - Upto date Actual UKG is showing wrong for SCSL3 - In production MIS report
1 | Maari | SKS | RMI | Transactions-->Freight Purchase bill entry form the following changes to be needed
2 |  | Shivamill |  | Inventory - settings - Report Footer not opened - Reg - Report footer not opened please check and correct as soon as possible
3 |  | SSVDB | Import | SSVDB Import & RMI Module Corrective CR_28.03.2025 - reg - 1.Transactions - RMI Receipt a)Change listing functionality: Switch from Container-based listing to Trailer-based listing. |  | Completed
4 |  | SSVDB | Import | SSVDB Import module_Corrective CR_02.04.2025 - reg - 2. Transactions - Purchase Order - Find option- Rename Sales Contract Listing to Purchase Order Listing.
5 |  | SSVDB | Import | Transactions - Purchase Order - Find option- Rename Sales Contract Listing to Purchase Order Listing
6 |  | SSVDB | GMS | Pending CR points
7 |  | ALL |  | Stock diffrence correction based on year end process |  | Completed
1 | Mariya | Cheran |  | Barcode scanning and Pre despatch advice entry |  | Inprogress
2 |  | Bannari HT |  | Year end process support HT1 |  | Completed
1 | Udhay | SKS | Payroll | Reports - Personal Information Reports correction |  |  | Form correction required
2 |  | SKS | QC | SKS - QC - Internal CR- 28.03.25 - Reg - 2.Reports -> Periodical -> Carding -> Wrapping -> Hank Standard value is printed in the Cv value need to correct this.
3 |  | SKS | QC | Carding waste - Line waste total mistake
4 |  | SKS | QC | Crading cleaning efficency Crystal report conversion.
5 |  | VTS | SPG | VTS - Post Spinning - Customer CR 01 - Reg - 1.Reports -> Periodical -> Autoconer vs RG1 Report -> Need to change the report format based on customer requirement.
6 |  | SSVDB | RMI | SSVDB RMI Corrective CR_22.03.2025 - CR No:23 pending points
1 | Siranjeevi | Space textile | CSM | CSM - MIS - Sale Order Status - Internal CR 28 - Reg - a.Need to add Order Ref No. in Sale Contract Selection look up. b.Next to finance details, need to add Payment Details with the following fields |  | Completed
2 |  | SSVDB | Web Approval | Digital Signature & Auto Mail for PO & Import PO Approval |  | Inprogress
3 |  | Space textile |  | OCR Form & report feedback corrections & improvements - In Progress |  | Inprogress
1 | Seeni | SCM Goupp |  | Domestic sales latest testing and updation for SCM Spinners unit-2, JAT, SCM Mills
2 |  | SLVSM | Invy | Year end process
3 |  | Poongodhai | Stores | Year end process
4 |  | Blue Weaves | Stores | Canteen report not open issue |  | Completed
5 |  | SSVDB | Stores | Opening stock upload.
6 |  | All |  | Year end process support for not completed customers( Giri synthectis, GMP wvg, PK Lakshmi)
1 | Vignesh | Space textile |  | Implementation support
2 |  | VTS | Post Spg | Autoconer VS RG1 report coordination and completion
4 |  | Pallavaa |  | Operational issue completion
5 |  |  | Prodn | Year end process support |  | Completed
6 |  | Marketing |  | Prospect Plan for new business updation |  | Completed
1 | Muthuvel | SSVDB |  | Onsite Visit |  | Completed
2 |  | All |  | Year end process support |  | Inprogress
1 | Palanivel | SkS |  | Onsite Visit |  | Completed
2 |  | All |  | Year end process support |  | Inprogress
1 | KarthiKeyan | SSVDB |  | Onsite Visit |  | Completed
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi | 6 | 1 | 5
|  |  | 2 | Annamalai | 6 | 3 | 3
|  |  | 3 | Maari | 7 | 2 | 5
|  |  | 4 | Mariya | 2 | 1 | 1
|  |  | 5 | Udhay | 6 | 0 | 6 | 1
|  |  | 6 | Siranjeevi | 3 | 1 | 2
|  |  | 7 | Seeni | 6 | 1 | 5
|  |  | 8 | Muthuvel | 2 | 1 | 1
|  |  | 9 | Vignesh | 5 | 2 | 3
|  |  | 10 | Palanivel | 2 | 1 | 1
|  |  | 11 | KarthiKeyan | 1 | 1 | 0
|  |  |  | Total CR Points | 46 | 14 | 32

## 05.04.25
Daily Work Plan - 05.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKS | FA | Payment request - TDS provision |  | Inprogress
2 |  | Kumaragiri | Payroll | AUDIT FINDINGS 1. Attendance to be marked as present on the date of joining. 2. In the wage statement, Per day Wage / Monthly wage as in Payslip to be included in the report. 3. Wage statement , Attendance, time card , Payslip - Designation wise , Department wise filter option is required. 4. In the Payslip, earnings break up for all categories. - Top most urgent |  | Inprogress
3 |  | Kumargiri | Payroll | The below security Token number 5315 belongs to general shit (08:00 Am to 05:00 PM) whereas his attendance shows night shift only . (10 PM to 06 AM).For the Jan'25 & Mar'25 it shows for general shift rest all other months it is for night shift. Requirement is General shift except on NFH day
4 |  | SSVDB | FA | Internay CR points
5 |  | SSVDB | RMI | In the SSVDB RMI Module, the Housekeeping FA-related Parameter (TC='79') is facing an issue where the Coal Purchase GL and Freight GL codes are unable to be mapped
1 | Annamalai | Pallavaa | PPC | Kindly check on the physical stock entry, where the mix count MTEN is showing duplicate, Also the Closing stock - 1356.30 Kgs(of Feb-25) is showing as 678.15(Mar-25) as Opening
2 |  | SCMTS | KnSales | As discussed, we have raised Jobwork (docno 21) in the name of Tribal Clothing for a quantity of 2400 (40 bags).we need to request a correction as this jobwork should actually be raised in the name of Warrior Clothing Company.
3 |  | SKS | Lsales | TransactionsDespatch advice with PO & Without PO form Pack Entry & Stock details selection Gross_wt column to be needed
4 |  | VTS | SPG | VTS - Post Spinning - Customer CR 01 - Reg - 1.Reports -> Periodical -> Autoconer vs RG1 Report -> Need to change the report format based on customer requirement.
5 |  | Pallavaa | Post Spg | Machine duplicatio issue
6 |  | Pallavaa | Spg | MIS - Upto date Actual UKG is showing wrong for SCSL3 - In production MIS report
|  | SSVDB | Paper Sales | Additional Rate column validated for Sale order and Customer Rate master |  | Completed
|  | SKS | D Sales | Invoice print correction |  | Completed
|  | SHIVA II | D Sales | Job Work Yarn Receipt process support |  | Completed
|  | Shiva II | D Sales | Lot no issues for invoice |  | Completed
|  | Ashok Textile | D Sales | Repack transaction entry support |  | Completed
1 | Maari | SSVDB | RMI | SSVDB RMI Module_Corrective CR_02.04.2025 - feedback corrections.
2 |  | Pallavaa | Invy | Year end process stock diff
4 |  | Shivamill |  | Inventory - settings - Report Footer not opened - Reg - Report footer not opened please check and correct as soon as possible |  | Completed
5 |  | SSVDB | Import | SSVDB Import & RMI Module Corrective CR_28.03.2025 - reg - 1.Transactions - RMI Receipt a)Change listing functionality: Switch from Container-based listing to Trailer-based listing.
6 |  | SSVDB | Import | SSVDB Import module_Corrective CR_02.04.2025 - reg - 2. Transactions - Purchase Order - Find option- Rename Sales Contract Listing to Purchase Order Listing.
7 |  | SSVDB | Import | Transactions - Purchase Order - Find option- Rename Sales Contract Listing to Purchase Order Listing
Inprogress
1 | Mariya | Cheran |  | Barcode scanning and Pre despatch advice entry
2 |  | Bannari HT |  | Year end process support for HT2
|  | Shivatex |  | In WebMIS waste sales day book not working. Error screenshot attached for your reference |  | Completed
|  | Bannari Spg |  | Depot Sales – Sales return credit note not listing |  | Completed
|  | SSVDB |  | E-invoice – Invoice number format, GSTR1, and GSTR2B |  | Completed
1 | Udhay | SKS | Scrap Sales | TransactionsàScrap Invoice transaction print the following changed to be needed |  |  | Form correction required
2 |  | VTS | SPG | VTS - Post Spinning - Customer CR 01 - Reg - 1.Reports -> Periodical -> Autoconer vs RG1 Report -> Need to change the report format based on customer requirement.
3 |  | SSVDB | RMI | SSVDB RMI Corrective CR_22.03.2025 - CR No:23 pending points
4 |  | SKS | Payroll | Reports - Personal Information Reports correction
5 |  | SKS | QC | Pending CR
1 | Siranjeevi | SSVDB | Web Approval | Digital Signature & Auto Mail for PO & Import PO Approval |  | Inprogress
2 |  | Space textile |  | OCR Form & report feedback corrections & improvements - In Progress |  | Inprogress
3 |  | SSVDB |  | SSVDB Domestic Sales module - Sales Customer Rate approval showing an error while click the print |  | Completed
1 | Seeni | SCM Goupp |  | Domestic sales latest testing and updation for SCM Spinners unit-2, JAT, SCM Mills
2 |  | SLVSM | Invy | Year end process |  | Completed
3 |  | Poongodhai | Stores | Year end process |  | Completed
5 |  | SSVDB | Stores | Opening stock upload.
6 |  | All |  | Year end process support for not completed customers( Giri synthectis, GMP wvg, PK Lakshmi)
1 | Vignesh | SKS |  | Onsite Visit |  | Completed
2 |  | ALL |  | Production module year end process
1 | Muthuvel | SSVDB |  | Onsite Visit |  | Completed
2 |  | Sivadharsini | FA | Kindly enable the FA Module year end process for payment entry,cash entry and bill entries |  | Inprogress
1 | Palanivel | SkS |  | Onsite Visit |  | Completed
2 |  | All |  | Year end process support |  | Inprogress
1 | KarthiKeyan | SSVDB |  | Onsite Visit |  | Completed
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi
|  |  | 2 | Annamalai
|  |  | 3 | Maari
|  |  | 4 | Mariya
|  |  | 5 | Udhay
|  |  | 6 | Siranjeevi
|  |  | 7 | Seeni
|  |  | 8 | Muthuvel
|  |  | 9 | Vignesh
|  |  | 10 | Palanivel
|  |  | 11 | KarthiKeyan
Total CR Points

## 07.04.25
Daily Work Plan - 07.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKS | FA | Payment request - TDS provision |  | Inprogress
2 |  | Kumaragiri | Payroll | AUDIT FINDINGS 1. Attendance to be marked as present on the date of joining. 2. In the wage statement, Per day Wage / Monthly wage as in Payslip to be included in the report. 3. Wage statement , Attendance, time card , Payslip - Designation wise , Department wise filter option is required. 4. In the Payslip, earnings break up for all categories. - Top most urgent |  | Complted
3 |  | Kumargiri | Payroll | The below security Token number 5315 belongs to general shit (08:00 Am to 05:00 PM) whereas his attendance shows night shift only . (10 PM to 06 AM).For the Jan'25 & Mar'25 it shows for general shift rest all other months it is for night shift. Requirement is General shift except on NFH day |  | Complted
4 |  | SSVDB | FA | Internay CR points
5 |  | SSVDB | RMI | In the SSVDB RMI Module, the Housekeeping FA-related Parameter (TC='79') is facing an issue where the Coal Purchase GL and Freight GL codes are unable to be mapped
1 | Annamalai | Pallavaa | PPC | Kindly check on the physical stock entry, where the mix count MTEN is showing duplicate, Also the Closing stock - 1356.30 Kgs(of Feb-25) is showing as 678.15(Mar-25) as Opening
2 |  | SCMTS | KnSales | As discussed, we have raised Jobwork (docno 21) in the name of Tribal Clothing for a quantity of 2400 (40 bags).we need to request a correction as this jobwork should actually be raised in the name of Warrior Clothing Company. |  | Closed
3 |  | SKS | Lsales | TransactionsDespatch advice with PO & Without PO form Pack Entry & Stock details selection Gross_wt column to be needed
4 |  | VTS | SPG | VTS - Post Spinning - Customer CR 01 - Reg - 1.Reports -> Periodical -> Autoconer vs RG1 Report -> Need to change the report format based on customer requirement.
5 |  | Pallavaa | Post Spg | Machine duplicatio issue |  | Complted
6 |  | Pallavaa | Spg | MIS - Upto date Actual UKG is showing wrong for SCSL3 - In production MIS report |  | Complted
Production entry locking issue
1 | Maari | SSVDB | RMI | SSVDB RMI Module_Corrective CR_02.04.2025 - feedback corrections.
2 |  | SSVDB | Import | SSVDB Import & RMI Module Corrective CR_28.03.2025 - reg - 1.Transactions - RMI Receipt a)Change listing functionality: Switch from Container-based listing to Trailer-based listing.
3 |  | SSVDB | Import | SSVDB Import module_Corrective CR_02.04.2025 - reg - 2. Transactions - Purchase Order - Find option- Rename Sales Contract Listing to Purchase Order Listing.
4 |  | SSVDB | Import | Transactions - Purchase Order - Find option- Rename Sales Contract Listing to Purchase Order Listing
5 |  | SSVDB | GMS | SSVDB - Gate Movements Internal CR - 1 - CR Point No: 4
1 | Mariya | Cheran |  | Barcode scanning and Pre despatch advice entry
2 |  | Bannari HT |  | Year end process support for HT2
1 | Udhay | SKS | Scrap Sales | TransactionsàScrap Invoice transaction print the following changed to be needed |  |  | Form correction required
2 |  | VTS | SPG | VTS - Post Spinning - Customer CR 01 - Reg - 1.Reports -> Periodical -> Autoconer vs RG1 Report -> Need to change the report format based on customer requirement.
3 |  | SSVDB | RMI | SSVDB RMI Corrective CR_22.03.2025 - CR No:23 pending points
4 |  | SKS | Payroll | Reports - Personal Information Reports correction
5 |  | SKS | QC | Pending CR
1 | Siranjeevi | SSVDB | Web Approval | Digital Signature & Auto Mail for PO & Import PO Approval |  | Completed
2 |  | Space textile |  | OCR Form & report feedback corrections & improvements - In Progress
Pallavaa automail
1 | Seeni | Cheran |  | Onsite Visit
1 | Vignesh | SKS |  | Onsite Visit
1 | Muthuvel |  |  | Leave
1 | Palanivel | SkS |  | Onsite Visit
2 |  | All |  | Year end process support
1 | KarthiKeyan | SSVDB |  | Onsite Visit
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi
|  |  | 2 | Annamalai
|  |  | 3 | Maari
|  |  | 4 | Mariya
|  |  | 5 | Udhay
|  |  | 6 | Siranjeevi
|  |  | 7 | Seeni
|  |  | 8 | Muthuvel
|  |  | 9 | Vignesh
|  |  | 10 | Palanivel
|  |  | 11 | KarthiKeyan
Total CR Points

## 08.04.25
Daily Work Plan - 08.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKS | FA | Payment request - TDS provision
2 |  | Kumaragiri | Payroll | AUDIT FINDINGS 1. In the Payslip, earnings break up for all categories. - Top most urgent |  | Completed
3 |  | SSVDB | FA | Internay CR points
4 |  | Bannari Wvg | Payroll | Attendance issue - In the daily attendance records, one employee's days are incorrectly marked as both "Full-day present" and "Absent." Due to this discrepancy, their salary is not being calculated correctly. Also, days are calculated than the month
1 | Annamalai | Pallavaa | PPC | Kindly check on the physical stock entry, where the mix count MTEN is showing duplicate, Also the Closing stock - 1356.30 Kgs(of Feb-25) is showing as 678.15(Mar-25) as Opening
2 |  | Pallavaa | Spg | MIS - Upto date Actual UKG is showing wrong for SCSL3 - In production MIS report EB unit Upto date issue |  | Partially Completed
3 |  | SKS | SPG | ReportsPeriodicalStoppageLoss in utilisationCustomised option to be needed for Date wise and Machine wise report as per below mentioned format. |  | Completed | Exe to be sent
4 |  | SSVDB | Paper Sales | Previous date production provision for separte exe.
5 |  | SKS | Lsales | TransactionsDespatch advice with PO & Without PO form Pack Entry & Stock details selection Gross_wt column to be needed
6 |  | VTS | SPG | VTS - Post Spinning - Customer CR 01 - Reg - 1.Reports -> Periodical -> Autoconer vs RG1 Report -> Need to change the report format based on customer requirement.
|  | SKS | Post Spg | Autoconer production entry issue rectified. Permanent solution to be provided. |  | Completed
|  | Cheran | Lsales | Repacking and conversion entry supported to Seeni |  | Completed
1 | Maari | SSVDB | RMI | In the SSVDB RMI Module, the Housekeeping FA-related Parameter (TC='79') is facing an issue where the Coal Purchase GL and Freight GL codes are unable to be mapped |  | Completed
2 |  | SSVDB | RMI | Re: SSVDB RMI Module_Corrective CR_02.04.2025 - re -In both the Paper Invoice and Fuel Invoice screens, test entries are available in our database. When modifying the bills and selecting the TDS type, the system does not allow re-selection of the TDS type within the same transaction. |  | Completed
3 |  | SSVDB | RMI | Item selection correction in Receipt(Feedback corrections - SSVDB RMI Module_Corrective CR_02.04.2025)
4 |  | SSVDB | Import | SSVDB Import & RMI Module Corrective CR_28.03.2025 - reg - 1.Transactions - RMI Receipt a)Change listing functionality: Switch from Container-based listing to Trailer-based listing. |  | Completed | Exe to be sent
5 |  | SSVDB | Import | SSVDB Import module_Corrective CR_02.04.2025 - reg - 2. Transactions - Purchase Order - Find option- Rename Sales Contract Listing to Purchase Order Listing. |  | Completed
6 |  | SSVDB | Import | Transactions - Purchase Order - Find option- Rename Sales Contract Listing to Purchase Order Listing |  | Completed
7 |  | SSVDB | GMS | SSVDB - Gate Movements Internal CR - 1 - CR Point No: 4 vehcile outward correction
8 |  | KLM | Stores | Stock diff |  | Completed
1 | Mariya | Cheran |  | Barcode scanning and Pre despatch advice entry |  | Partially Completed
2 |  | Space textile | CSM | Feedback points
1 | Udhay | SKS | Scrap Sales | TransactionsàScrap Invoice transaction print the following changed to be needed |  | Completed | Form correction required
2 |  | SSVDB | GMS | Print correction - CR No:1 &2.
3 |  | ScMTS | RMI | RMI variety wise stock statment sales data need to be dsiplted separtely as per exsiting format.
4 |  | SKS | Payroll | Reports - Personal Information Reports correction
5 |  | SKS | QC | Operational CR
|  | SCMTS | Lsales | Customer wise sales report abstract issue corrected. |  | Completed
1 | Siranjeevi | Space textile |  | OCR Form & report feedback corrections & improvements - In Progress |  | Completed
2 |  | Pallavaa |  | Pallavaa automail |  | Completed
1 | Seeni | SCM Goupp |  | Domestic sales latest testing and updation for SCM Spinners unit-2, JAT, SCM Mills
5 |  | SSVDB | Stores | Opening stock upload.
|  | Cheran |  | Yarn Stock to be tallied.
6 |  | All |  | Year end process support for not completed customers( Giri synthectis,, PK Lakshmi)
1 | Vignesh | SKS |  | Onsite Visit
2 |  | ALL |  | Production module year end process
1 | Muthuvel |  |  | Leave
2
1 | Palanivel |  |  | WFH
2
1 | KarthiKeyan | SSVDB |  | Onsite Visit
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi | 4 | 1 | 3
|  |  | 2 | Annamalai | 6 | 1 | 5 | 2
|  |  | 3 | Maari | 8 | 6 | 2
|  |  | 4 | Mariya | 2 | 0 | 2
|  |  | 5 | Udhay | 5 | 1 | 4 | 1
|  |  | 6 | Siranjeevi | 2 | 1 | 1
|  |  | 7 | Seeni | 2 | 2 | 0
|  |  | 8 | Muthuvel | 1 | 1 | 0
|  |  | 9 | Vignesh | 1 | 1 | 0
|  |  | 10 | Palanivel |  |  | 0
|  |  | 11 | KarthiKeyan | 1 | 1 | 0
|  |  |  | Total CR Points | 32 | 15 | 17 | 3

## 09.04.25
Daily Work Plan - 09.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKS | FA | Payment request - TDS provision
2 |  | SSVDB | FA | Internay CR points
3 |  | Bannari Wvg | Payroll | Attendance issue - In the daily attendance records, one employee's days are incorrectly marked as both "Full-day present" and "Absent." Due to this discrepancy, their salary is not being calculated correctly. Also, days are calculated than the month
4 |  | Kumaragiri | Payroll | Audit report feedback corrections if any. |  | Completed
|  | SCM Mill | FA | AR not tallied for 5 customers |  | Completed
1 | Annamalai | Pallavaa | PPC | Kindly check on the physical stock entry, where the mix count MTEN is showing duplicate, Also the Closing stock - 1356.30 Kgs(of Feb-25) is showing as 678.15(Mar-25) as Opening |  | Completed
2 |  | Pallavaa | Spg | MIS - Upto date Actual UKG is showing wrong for SCSL3 - In production MIS report EB unit Upto date issue |  | Completed
3 |  | SSVDB | Paper Sales | Previous date production provision for separte exe. |  | Completed
4 |  | SKS | Lsales | TransactionsDespatch advice with PO & Without PO form Pack Entry & Stock details selection Gross_wt column to be needed
5 |  | VTS | SPG | VTS - Post Spinning - Customer CR 01 - Reg - 1.Reports -> Periodical -> Autoconer vs RG1 Report -> Need to change the report format based on customer requirement. |  | Completed
6 |  | SKS | QC | Operation issue points
1 | Maari | SSVDB | RMI | Item selection correction in Receipt(Feedback corrections - SSVDB RMI Module_Corrective CR_02.04.2025) |  | Completed
2 |  | SSVDB | Import | Entry date and time capturing in import PO |  | Completed
3 |  | SRG | RMI | Lot Allowance enrty problem.reg - As discussed RMI Lot allowance trash calculates error pls correct |  | Closed
4 |  | SSVDB | GMS | SSVDB - Gate Movements Internal CR - 1 - CR Point No: 4 vehcile outward correction
5 |  | Pallavaa | Power | SR-2429 // SCSL-I // POWER ACCOUNTING // HT METER REPORT - EB Units in the HT Meter Reading report of SCSL- I is showing wrong. Kindly check and correct the same.
6 |  | SRG | RMI | LIST OF ISSUSE ERROR.REG - Pls Check and correct |  | Completed
7 |  | SSVDB | SSVDB | Service PO correction
1 | Mariya | Cheran |  | Barcode scanning and Pre despatch advice entry |  | Partially Completed
2 |  | Space textile | CSM | Stock ageing report
|  | Space textile | CSM | Customer API intgeration
|  | Bannari HT | Sales | E-way b ill support |  | Completed
1 | Udhay | SSVDB | GMS | Print correction - CR No:1 &2.
2 |  | ScMTS | RMI | RMI variety wise stock statment sales data need to be dsiplted separtely as per exsiting format.
3 |  | SKS | Payroll | Reports - Personal Information Reports correction
4 |  | SKS | QC | Operational CR
5 |  | SCMTS | Lsales | Customer wise sales report abstract issue corrected.
1 | Siranjeevi | Space textile | CSM | Re: Space Textiles - CSM - Enquiry List report - Internal CR 20 - reg
2 |  | Space textile | CSM | Re: Space Textiles - CSM - Sale Contract List report - Internal CR 21 - reg
3 |  | Space textile | CSM | Re: Fwd: Space Textiles - CSM - List Price - Internal CR 13 - reg
4 |  | Subam | Automail | Subam AutoMail -DailyMIS
1 | Seeni | SCM Goupp |  | Domestic sales latest testing and updation for SCM Spinners unit-2, JAT, SCM Mills
2 |  | SCM Spinners | Lsales | Latest version updation script generation
3 |  | SCM Spinners -2 | EMS | Imlementation completion and onsite visit to plan on next day for project completion
4 |  | All |  | Pending testing points completion
5 |  | All |  | Year end process support for not completed customers( Giri synthectis,, PK Lakshmi) |  | Completed
1 | Vignesh | Space textile |  | OCR report UAT signoff & Implementation support
2 |  | VTS | Post Spg | Autoconer VS RG1 report coordination and completion
3 |  | Pallavaa |  | Operational issue completion |  | Completed
4 |  |  | Prodn | Year end process support
5 |  | Marketing |  | Lead generation |  | Completed
|  | Armstrong | QC | Module training given.
1 | Muthuvel |  |  | Onsite Visit |  | Completed
2 |  |  |  | Year end process support for not completed customers( Giri synthectis,, PK Lakshmi)
1 | Palanivel |  |  | Leave
2
1 | KarthiKeyan | SSVDB |  | Onsite Visit |  | Completed
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi
|  |  | 2 | Annamalai
|  |  | 3 | Maari
|  |  | 4 | Mariya
|  |  | 5 | Udhay
|  |  | 6 | Siranjeevi
|  |  | 7 | Seeni
|  |  | 8 | Muthuvel
|  |  | 9 | Vignesh
|  |  | 10 | Palanivel
|  |  | 11 | KarthiKeyan
Total CR Points

## 10.04.25
Daily Work Plan - 10.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKS | FA | Payment request - TDS provision |  | Partially Completed
2 |  | SSVDB | FA | Internay CR points |  | Partially Completed
3 |  | Bannari Wvg | Payroll | Attendance issue - In the daily attendance records, one employee's days are incorrectly marked as both "Full-day present" and "Absent." Due to this discrepancy, their salary is not being calculated correctly. Also, days are calculated than the month
|  | Virtushaa | FA | TB not tallied issue |  | Completed
|  | Subam | FA | AR not tallied issue data generated |  | Completed
1 | Annamalai | SKS | Lsales | TransactionsDespatch advice with PO & Without PO form Pack Entry & Stock details selection Gross_wt column to be needed
2 |  | SKS | QC | Operation issue points
3 |  | SKS | Spg | Frame wise production report feedback corrections
4 |  | SkS | Pre Spg | SKS - Pre Spinning - Customer CR -08.04.2025 - Reg( No of Points:4)
5 |  | Subam | Paper Sales | QR code size correction.
6 |  | Subam | Paper Sales | Sales Module Errors rectifications - Reg - PFA of Sales Sale order and Work order errors list for your reference.
7 |  | Ashoke Textile | Wsales | WASTE SALES - Viscose division --> Transaction --> Despatch Advice --> Not Saved |  | Completed
|  | Pallavaa | SPG | Production entry form correction |  | Completed | Unplanned
|  | Cheran | Lsales | Agent master form correction |  | Completed | Unplanned
|  | Shiva II | Lsales | Invoice Form correction |  | Completed | Unplanned
1 | Maari | SSVDB | GMS | SSVDB - Gate Movements Internal CR - 1 - CR Point No: 4 vehcile outward correction
2 |  | Pallavaa | Power | SR-2429 // SCSL-I // POWER ACCOUNTING // HT METER REPORT - EB Units in the HT Meter Reading report of SCSL- I is showing wrong. Kindly check and correct the same. |  | Completed
3 |  | SSVDB | SSVDB | Service PO correction
4 |  | NKCM | Invy | Opening stock mismatch issue |  | Completed
5 |  | Gomathi | Invy | Opening stock mismatch issue |  | Completed
6 |  | Shivatex | MmS | MMS Schedule issue Reg, - Drawframe number 11 has not generated the next schedule, although the same schedule is appearing in the daily schedule report
1 | Mariya | Cheran |  | Barcode scanning and Pre despatch advice entry |  | Completed
2 |  | Space textile | CSM | Customer API intgeration
3 |  | Subam | Paper Sales | Or code scanning provision in Tab
|  | Kumaragiri | FA | GSTR 1 Json upload issue |  | Partially Completed
1 | Udhay | SSVDB | GMS | Print correction - CR No:1 &2.
2 |  | ScMTS | RMI | RMI variety wise stock statment sales data need to be dsiplted separtely as per exsiting format.
3 |  | SKS | Payroll | Reports - Personal Information Reports correction
4 |  | SKS | QC | Operational CR
5 |  | SCMTS | Lsales | Customer wise sales report abstract issue correction
1 | Siranjeevi | Space textile | CSM | Re: Space Textiles - CSM - Enquiry List report - Internal CR 20 - reg
2 |  | Space textile | CSM | Re: Space Textiles - CSM - Sale Contract List report - Internal CR 21 - reg
3 |  | Space textile | CSM | Re: Fwd: Space Textiles - CSM - List Price - Internal CR 13 - reg
4 |  | Subam | Automail | Subam AutoMail -DailyMIS
5 |  | Subam | Web Approvl | Subam Customer Rate Approval Print Corrction
1 | Seeni | SCM Goupp |  | Domestic sales latest testing and updation for SCM Spinners unit-2, JAT, SCM Mills
2 |  | SCM Spinners | Lsales | Latest version updation script generation
3 |  | SCM Spinners -2 | EMS | Imlementation completion and onsite visit to plan on next day for project completion
4 |  | All |  | Pending testing points completion
5 |  | All |  | Year end process support for not completed customers( Gomathi, NKCM, Poomer, SMPT, Kirthika, GMP Weaving) |  | Completed
1 | Vignesh | Space textile |  | OCR report UAT signoff & Implementation support
2 |  | VTS | Post Spg | Autoconer VS RG1 report coordination and completion
3 |  | VTS | QC | Module support and script generation
4 |  | Marketing |  | Website optimisation meeting and action plan prepared |  | Completed
1 | Muthuvel |  |  | Onsite Visit
2 |  |  |  | Year end process support for not completed customers( Giri synthectis,, PK Lakshmi)
1 | Palanivel |  |  | Onsite Visit
2 |  |  |  | Year end process support for not completed customers( Giri synthectis,, PK Lakshmi)
1 | KarthiKeyan | SSVDB |  | Onsite Visit
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi | 3 | 0 | 3 | 2
|  |  | 2 | Annamalai | 7 | 1 | 6 | 3
|  |  | 3 | Maari | 6 | 3 | 3
|  |  | 4 | Mariya | 3 | 1 | 2
|  |  | 5 | Udhay |  |  | 0
|  |  | 6 | Siranjeevi |  |  | 0
|  |  | 7 | Seeni | 5 | 1 | 4
|  |  | 8 | Muthuvel | 1 | 1 | 0
|  |  | 9 | Vignesh |  |  | 0
|  |  | 10 | Palanivel | 1 | 1 | 0
|  |  | 11 | KarthiKeyan | 1 | 1 | 0
|  |  |  | Total CR Points | 27 | 9 | 18 | 5

## 11.04.25
Daily Work Plan - 11.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKS | FA | Payment request - TDS provision |  | Partially Completed
2 |  | SSVDB | FA | Internay CR points |  | Completed
3 |  | Bannari Wvg | Payroll | Attendance issue - In the daily attendance records, one employee's days are incorrectly marked as both "Full-day present" and "Absent." Due to this discrepancy, their salary is not being calculated correctly. Also, days are calculated than the month
4 |  | Blueweavs |  | Sizing consumption report
1 | Annamalai | SKS | Lsales | TransactionsDespatch advice with PO & Without PO form Pack Entry & Stock details selection Gross_wt column to be needed
2 |  | SKS | QC | Operation issue points
3 |  | SKS | Spg | Frame wise production report feedback corrections |  | Completed
4 |  | SkS | Pre Spg | SKS - Pre Spinning - Customer CR -08.04.2025 - Reg( No of Points:4) |  | Completed
5 |  | Subam | Paper Sales | QR code size correction.
6 |  | Subam | Paper Sales | Sales Module Errors rectifications - Reg - PFA of Sales Sale order and Work order errors list for your reference.
|  | SKS | Post Spg | Autoconer drum issue in add mode |  | Completed
1 | Maari | SKS | RMI | Transactions-->Freight Purchase bill entry form the following changes to be needed
2 |  | SSVDB | GMS | SSVDB - Gate Movements Pending CR points |  | Completed
3 |  | SSVDB | SSVDB | Service PO correction |  | Completed
4 |  | Shivatex | MmS | MMS Schedule issue Reg, - Drawframe number 11 has not generated the next schedule, although the same schedule is appearing in the daily schedule report
5 |  | SSVDB | RMI | Feedback correction for receipt entry |  | Completed
1 | Mariya | Cheran |  | Barcode scanning and Pre despatch advice entry |  | Inprogress
2 |  | Space textile | CSM | Customer API intgeration
3 |  | Subam | Paper Sales | Or code scanning provision in Tab |  | Inprogress
|  | Kumaragiri | FA | GSTR 1 Json upload issue |  | Closed
1 | Udhay | SKS | PO | PO and Service PO print correction |  | Completed
2 |  | SSVDB | RMI | In the Daily Reports of the RMI Module for SSVDB, please increase the column width/length for the Closing Value field in the following reports: Waste Paper Stock Fuel Stock |  | Completed
3 |  | SKS | Payroll | Reports - Personal Information Reports correction
4 |  | SKS | QC | Operational CR
5 |  | ScMTS | RMI | RMI variety wise stock statment sales data need to be dsiplted separtely as per exsiting format.
|  | SSVDB | Paper Sales | Barcode sticker development |  | Completed
|  | SSVDB | PO | Remarks added.
1 | Siranjeevi | Space textile | CSM | Re: Space Textiles - CSM - Enquiry List report - Internal CR 20 - reg
2 |  | Space textile | CSM | Re: Space Textiles - CSM - Sale Contract List report - Internal CR 21 - reg
3 |  | Space textile | CSM | Re: Fwd: Space Textiles - CSM - List Price - Internal CR 13 - reg
4 |  | Subam | Automail | Subam AutoMail -DailyMIS
5 |  | Subam | Web Approvl | Subam Customer Rate Approval Print Corrction |  | Inprogress
1 | Seeni | SCM Spinners -2 |  | Onsite Visit |  | Completed
5 |  | All |  | Year end process support for not completed customers( SMPT, Kirthika, GMP Weaving)
1 | Vignesh | Space textile |  | OCR report UAT signoff & Implementation support
2 |  | VTS | Post Spg | Autoconer VS RG1 report coordination and completion |  | Inprogress
3 |  | VTS | QC | Module support and script generation |  | Completed
|  | Marketing |  | Prospect list preparation |  | Inprogress
1 | Muthuvel |  |  | Onsite Visit |  | Completed
2
1 | Palanivel |  |  | Onsite Visit |  | Completed
2 |  |  |  | Year end process support for not completed customers( PKPN, Jayavilas, Rohit)
1 | KarthiKeyan | SSVDB |  | Onsite Visit |  | Completed
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi
|  |  | 2 | Annamalai
|  |  | 3 | Maari
|  |  | 4 | Mariya
|  |  | 5 | Udhay
|  |  | 6 | Siranjeevi
|  |  | 7 | Seeni
|  |  | 8 | Muthuvel
|  |  | 9 | Vignesh
|  |  | 10 | Palanivel
|  |  | 11 | KarthiKeyan
Total CR Points

## 12.04.25
Daily Work Plan - 12.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKS | FA | Payment request - TDS provision |  | Partially Completed
2 |  | Bannari Wvg | Payroll | Attendance issue - In the daily attendance records, one employee's days are incorrectly marked as both "Full-day present" and "Absent." Due to this discrepancy, their salary is not being calculated correctly. Also, days are calculated than the month
3 |  | Blueweavs |  | Sizing consumption report
4 |  | SSVDB | FA | Pending FA CR points
5 |  | SCMTS | Kn sales | Order transfer provision for jobwork, they need to raise the invocie tomorrow.
6 |  | Kumaragiri | FA | MIS report - Sales data adding option to be finalised.
1 | Annamalai | SKS | Lsales | TransactionsDespatch advice with PO & Without PO form Pack Entry & Stock details selection Gross_wt column to be needed
2 |  | SKS | QC | Operation issue points
5 |  | Subam | Paper Sales | QR code size correction.
6 |  | Subam | Paper Sales | Sales Module Errors rectifications - Reg - PFA of Sales Sale order and Work order errors list for your reference.
|  | SKS | Lsales | Job work report CR
|  | Pallavaa | Pre Spg | Kindly check and do the necessary, often we are experiencing the similar error
1 | Maari | SKS | RMI | Transactions-->Freight Purchase bill entry form the following changes to be needed
2 |  | Shivatex | MmS | MMS Schedule issue Reg, - Drawframe number 11 has not generated the next schedule, although the same schedule is appearing in the daily schedule report
3 |  | Kirthika | Stores | Year end differecne
4 |  | Pallavaa | Power | For SCSL-II the HT Meter reading of Unit A is not taking into account for the Daily Production Report from April 2 to April 5.
5 |  | SSVDB | Import | Pending CR points(CHA, CFS, Transprot)
1 | Mariya | Cheran |  | Barcode scanning and Pre despatch advice entry
2 |  | Space textile | CSM | Customer API intgeration
3 |  | Subam | Paper Sales | Or code scanning provision in Tab
4 |  | SSVDB | MIS | FG stock report correctiuo as per mill requiremet.
1 | Udhay | SKS | Payroll | Reports - Personal Information Reports correction
|  | SKS | QC | Operational CR
3 |  | ScMTS | RMI | RMI variety wise stock statment sales data need to be dsiplted separtely as per exsiting format.
4 |  | Ashok Textile | Wsales | Waste Sales --> Report --> Periodical --> Sales Day Book --> Customer Wise --> Crystal Report --> Not Open ,Please check and rectify this issue..
1 | Siranjeevi | Space textile | CSM | Re: Space Textiles - CSM - Enquiry List report - Internal CR 20 - reg
2 |  | Space textile | CSM | Re: Space Textiles - CSM - Sale Contract List report - Internal CR 21 - reg
3 |  | Space textile | CSM | Re: Fwd: Space Textiles - CSM - List Price - Internal CR 13 - reg
4 |  | Subam | Automail | Subam AutoMail -DailyMIS
5 |  | Subam | Web Approvl | Subam Customer Rate Approval Print Corrction
1 | Seeni | Cheran |  | Onsite Visit
5 |  | All |  | Year end process support for not completed customers( SMPT, Kirthika, GMP Weaving)
1 | Vignesh | SKS |  | Onsite Visit
1 | Muthuvel |  |  | Onsite Visit
2
1 | Palanivel |  |  | Onsite Visit
2 |  |  |  | Year end process support for not completed customers( PKPN, Jayavilas, Rohit)
1 | KarthiKeyan | SSVDB |  | Onsite Visit |  | Completed
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi
|  |  | 2 | Annamalai
|  |  | 3 | Maari
|  |  | 4 | Mariya
|  |  | 5 | Udhay
|  |  | 6 | Siranjeevi
|  |  | 7 | Seeni
|  |  | 8 | Muthuvel
|  |  | 9 | Vignesh
|  |  | 10 | Palanivel
|  |  | 11 | KarthiKeyan
Total CR Points

## 25.04.25
Daily Work Plan - 25.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKS | FA | ReportsDailyPaymentsPayment covering letter format to be needed same like SCMTS Payment Advice Format. - SQL Script Correction |  | InProgress | Procedure created Reprot need to develop
2 |  | SKS | FA | Payment request - Cut Sheet Format - SQL Script Correction |  | Completed
3 |  | SKS | Payroll | ReportMonthlyAgent commission report slab to be changed, Applicable worked days above 24 days.If worker worked 8 Hours per day – Rs.20-If worker worked 12 hours per day – Rs.30 |  | InProgress
4 |  | SKS | Payroll | Attendance incentive & Week off worked salary report option to be added same like ‘SCM Mills”. |  | Pending
6 |  | SKS | Payroll | -5.NFH Days applicable only for “Staff” Category, For worker category NFH days not applicable If worker worked in NFH days it to be treated as Worked days. For Staff worked in NFH days extra one day wage to be added in salary. |  | Pending
1 | Annamalai | SKS | D Sales | Job Work statement and Form Correction |  | InProgress
2 |  | SKS | QC | SKS - QC - Internal CR- 28.03.25 - Reg - 1.Reports -> Daily -> Rewinding Breakage Study: a.Breaks / Lac metre value is not matching. |  | Pending
3 |  | SKS | QC | SKS - QC - Customer CR -07.04.2025 - Reg - As this Change Request is essential for implementation at the customer end, I kindly request your approval to proceed. |  | Pending
4 |  | SKS | Post Spg | The report format has been modified to align with our existing Spinning Abstract format. The revised version is now based on Autoconer Make-wise – Count-wise details.Additionally, the following columns need to capture the report as requested: |  | Pending
5 |  | Cheran | D Sales | Customer CR points |  | Pending
6 |  | SKS | Pre Spg | Queries - Machine wise and reason wise stoppage |  | Completed | unplanned
1 | Maari | SKS | PO | Internal CR points |  | Partially Completed | Report points are pending
2 |  | SKS | Power | Reports Periodical Power Consumption Crystal Above mentioned data need to capture below mentioned (Image2)i)Add “Day Total Distribution Loss Units” after the “Day Total”ii)Add “Grand Total Distribution Loss Units” after the “Grand Day Total” |  | Pending
3 |  | SKS | Invy | Internal CR points |  | Partially Completed | Report points are pending
4 |  | SSVDB | Import | Internal CR points |  | Pending
5 |  | STYL | MMS | Issue points |  | InProgress
1 | Udhay | SKS | FA | .ReportsDailyRCMJournal RCM Invoice report Division unit name “Unit of Sharadha terry products private limited “ to be added and Service/Goods column name to be changed as Mechanism & Report half page needed. |  | Pending
2 |  | SKS | FA | ReportsDailyDebit/Credit Note transaction print to be needed as per below mentioned format. |  | Pending
3 |  | SKS | FA | Payment request - Cut Sheet Format |  | Completed
4 |  | Cheran | D Sales | Sale invoice Print correction |  | InProgress | Sale Order point completed
5 |  | Space Testile | CSM | Report Alignment points |  | Pending
6 |  | SKS | Power | Reports Periodical Power Consumption Crystal Above mentioned data need to capture below mentioned (Image2)i)Add “Day Total Distribution Loss Units” after the “Day Total”ii)Add “Grand Total Distribution Loss Units” after the “Grand Day Total” |  | Pending
7 |  | SKS | PO | REG: SKS Mills - Purchase Order - Customer CR 150325 - 1.TransactionsPR To Purchase orderPO transaction print the following changes to be needed a.PR No & PR Date column to be needed. b.Last PO No column to be needed (Approved PO No). |  | Completed
8 |  | SSVDB | FA | Cheque alignment correction |  | Completed | Unplanned
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi | 5 | 1 | 4
|  |  | 2 | Annamalai | 5 |  | 5 | 1
|  |  | 3 | Maari | 5 |  | 5
|  |  | 4 | Udhay | 7 | 3 | 4 | 1
Total CR Points

## 26.04.25
Daily Work Plan - 26.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKS | Payroll | ReportMonthlyAgent commission report slab to be changed, Applicable worked days above 24 days.If worker worked 8 Hours per day – Rs.20-If worker worked 12 hours per day – Rs.30 |  | Pending
2 |  | SKS | Payroll | Attendance incentive & Week off worked salary report option to be added same like ‘SCM Mills”. |  | Pending
3 |  | SKS | Payroll | -5.NFH Days applicable only for “Staff” Category, For worker category NFH days not applicable If worker worked in NFH days it to be treated as Worked days. For Staff worked in NFH days extra one day wage to be added in salary. |  | Pending
4 |  | SKS | FA | CR points- 25.04.25 |  | Partially Completed | BRS Entry completed
5 |  | SCMTS | FA | Party wise receipt details report |  | In Progress
6 |  | Cheran | D Sales | Kalsofte to Tally correction
7 |  | SKS | FA | P and L Report |  | Completed
1 | Annamalai | SSVDB | D Sales | Internal CR points |  | Pending
2 |  | SKS | QC | SKS - QC - Internal CR- 28.03.25 - Reg - 1.Reports -> Daily -> Rewinding Breakage Study: a.Breaks / Lac metre value is not matching. |  | Completed
3 |  | SKS | QC | SKS - QC - Customer CR -07.04.2025 - Reg - As this Change Request is essential for implementation at the customer end, I kindly request your approval to proceed. |  | Pending
4 |  | SKS | Post Spg | The report format has been modified to align with our existing Spinning Abstract format. The revised version is now based on Autoconer Make-wise – Count-wise details.Additionally, the following columns need to capture the report as requested: |  | Pending
5 |  | Cheran | D Sales | Customer CR points - Support |  | Pending
6 |  | Pallavaa | SPG | PRODUCTION STATEMENT // FORMAT CHANGE REQUIREMENT |  | In Progress
1 | Maari | SKS | PO | Service PO Budget |  | In Progress
2 |  | SKS | Power | Reports Periodical Power Consumption Crystal Above mentioned data need to capture below mentioned (Image2)i)Add “Day Total Distribution Loss Units” after the “Day Total”ii)Add “Grand Total Distribution Loss Units” after the “Grand Day Total” |  | In Progress
3 |  | SKS | Invy | Issue requisition value column need to add |  | In Progress
4 |  | SSVDB | Import | Internal CR points |  | Pending
5 |  | BlueWeaves | Invy | scrap Issue return entry process not working |  | Pending
1 | Udhay | SKS | FA | .ReportsDailyRCMJournal RCM Invoice report Division unit name “Unit of Sharadha terry products private limited “ to be added and Service/Goods column name to be changed as Mechanism & Report half page needed. |  | Pending
2 |  | SKS | FA | ReportsDailyDebit/Credit Note transaction print to be needed as per below mentioned format. |  | Pending
3 |  | Space Testile | CSM | Report Alignment pooints |  | Completed
4 |  | SKS | Power | Reports Periodical Power Consumption Crystal Above mentioned data need to capture below mentioned (Image2)i)Add “Day Total Distribution Loss Units” after the “Day Total”ii)Add “Grand Total Distribution Loss Units” after the “Grand Day Total” |  | Pending
5 |  | SKS | PO | REG: SKS Mills - Purchase Order - Customer CR 150325 - 1.TransactionsPR To Purchase orderPO transaction print the following changes to be needed a.PR No & PR Date column to be needed. b.Last PO No column to be needed (Approved PO No). |  | Pending
6 |  | SKS | RMI | Report correction |  | Inprogress
7 |  | Bananri | FA | Cheque Print Correction |  | Completed | Unplanned
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi | 6 | 1
|  |  | 2 | Annamalai | 6 | 1
|  |  | 3 | Maari | 5
|  |  | 4 | Udhay | 6 | 1 |  | 1
Total CR Points

## 28.04.25
Daily Work Plan - 28.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKS | Payroll | ReportMonthlyAgent commission report slab to be changed, Applicable worked days above 24 days.If worker worked 8 Hours per day – Rs.20-If worker worked 12 hours per day – Rs.30 |  | Pending
2 |  | SKS | Payroll | Attendance incentive & Week off worked salary report option to be added same like ‘SCM Mills”. |  | Pending
3 |  | SKS | Payroll | -5.NFH Days applicable only for “Staff” Category, For worker category NFH days not applicable If worker worked in NFH days it to be treated as Worked days. For Staff worked in NFH days extra one day wage to be added in salary. |  | Pending
4 |  | SKS | FA | CR points- 25.04.25 |  | In progress
5 |  | Bannari Wvg | Y invy | Cost Sheet Correction |  | In progress
6 |  | BlueWeaves | Wvg Prep | Sizing Consumption Report related correction |  | Pending
7 |  | SKS | FA | P and L Report - If feedback any |  | In progress
8 |  | SCMTS | FA | Party wise receceipt details and confirmation of balance |  | Completed
1 | Annamalai | SSVDB | D Sales | Internal CR points |  | Pending
2 |  | SKS | QC | SKS - QC - Customer CR -07.04.2025 - Reg - As this Change Request is essential for implementation at the customer end, I kindly request your approval to proceed. |  | Pending
3 |  | SKS | Post Spg | The report format has been modified to align with our existing Spinning Abstract format. The revised version is now based on Autoconer Make-wise – Count-wise details.Additionally, the following columns need to capture the report as requested: |  | Pending
4 |  | Cheran | D Sales | Customer CR points - Support |  | Completed
5 |  | Bannari Spg | Wsales | Sales Day book and Stock ageing |  | In progress
1 | Maari | SKS | PO | Service PO Budget |  | Completed
2 |  | SKS | Invy | Issue requisition value column need to add |  | In progress
3 |  | SSVDB | Import | Internal CR points |  | In progress
4 |  | SKS | RMI | Freight Bill Entry correction |  | Pending
5 |  | SKS | Invy | Freight Bill Entry correction |  | Pending
1 | Udhay | SKS | FA | .ReportsDailyRCMJournal RCM Invoice report Division unit name “Unit of Sharadha terry products private limited “ to be added and Service/Goods column name to be changed as Mechanism & Report half page needed. |  | Completed
2 |  | SKS | FA | ReportsDailyDebit/Credit Note transaction print to be needed as per below mentioned format. |  | In progress
3 |  | SKS | PO | REG: SKS Mills - Purchase Order - Customer CR 150325 - 1.TransactionsPR To Purchase orderPO transaction print the following changes to be needed a.PR No & PR Date column to be needed. b.Last PO No column to be needed (Approved PO No). |  | Completed
4 |  | SKS | RMI | Report correction |  | Completed
5 |  | Cheran | D Sales | Out pass print correction |  | Closed
6 |  | Bannari Wvg | Y invy | Cost Sheet Correction |  | In progress
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi | 8 | 1
|  |  | 2 | Annamalai | 5 | 1
|  |  | 3 | Maari | 5 | 1
|  |  | 4 | Udhay | 6 | 3
Total CR Points

## 29.04.25
Daily Work Plan - 29.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKS | Payroll | ReportMonthlyAgent commission report slab to be changed, Applicable worked days above 24 days.If worker worked 8 Hours per day – Rs.20-If worker worked 12 hours per day – Rs.30 |  | Pending
2 |  | SKS | Payroll | Attendance incentive & Week off worked salary report option to be added same like ‘SCM Mills”. |  | Completed
3 |  | SKS | Payroll | -5.NFH Days applicable only for “Staff” Category, For worker category NFH days not applicable If worker worked in NFH days it to be treated as Worked days. For Staff worked in NFH days extra one day wage to be added in salary. |  | In progress
4 |  | SKS | FA | 3.Transactions → Payment → Payment, when using Addition Mode, if a payment is made without an advance payment request (i.e., by selecting the option "Others"), the system does not allow entry of Sub Ledger details. |  | Pending
5 |  | BlueWeaves | Wvg Prep | Sizing Consumption Report related correction |  | Pending
6 |  | SKS | FA | P and L Report - If feedback any |  | In progress
1 | Annamalai | SSVDB | D Sales | Internal CR points |  | Pending
2 |  | SKS | QC | SKS - QC - Customer CR -07.04.2025 - Reg - As this Change Request is essential for implementation at the customer end, I kindly request your approval to proceed. |  | Pending
3 |  | SKS | Post Spg | The report format has been modified to align with our existing Spinning Abstract format. The revised version is now based on Autoconer Make-wise – Count-wise details.Additionally, the following columns need to capture the report as requested: |  | Completed
4 |  | Cheran | D Sales | Customer CR points - Support |  | Closed
5 |  | Poongodhai SPG | Spg | Daily MIS Report |  | Pending
6 |  | SKS | D Sales | Waste Kgs Entry: The waste (in Kgs) should be recorded against the respective selected product on |  | In progress
1 | Maari | SKS | RMI | Freight Bill Entry correction |  | Pending
2 |  | SKS | Invy | Freight Bill Entry correction |  | Pending
3 |  | SSVDB | Import | Internal CR points |  | Pending
4 |  | SKS | PO | Budget Utilized Report |  | Pending
5 |  | SKS | Invy | 2.TransactionsPurchase BillPurchase bill freight postingSupplier name details to be loaded from MRN Entry instead of Purchase Bill Entry and also Transporter name Lookup to be loaded from “C4 – Creditors Expenses”. |  | In progress
6 |  | SKS | Invy | ReportsPeriodicalMaterial Issue ListDate wise form approved and Un approved selection option to be needed and also Customized report format to be needed as per below mentioned format. |  | In progress
1 | Udhay | SKS | FA | ReportsDailyDebit/Credit Note transaction print to be needed as per below mentioned format. |  | Pending
2 |  | SKS | Payroll | Agent Commission |  | Pending
3 |  | Shiva | Invy | Gate Pass Print correction |  | Pending
4 |  | SSVDB | PO | 4. Transaction – Service Order – Crystal |  | Pending
4 |  | SSVDB | PO | Transaction – PR to Purchase Order – Crystal Report - |  | Pending
5 |  | SKS | PostSpg | Machinewise Production |  | In progress
6 |  | SKS | Power | Power consumption report |  | Completed | Unassigned
7 |  | SKS | RMI | Report feedback correction |  | Completed | Unassigned
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi | 6 | 1 | 5
|  |  | 2 | Annamalai | 6 | 1 | 5
|  |  | 3 | Maari | 6 | 0 | 6
|  |  | 4 | Udhay | 5 | 0 | 5 | 2
Total CR Points

## 30.04.25
Daily Work Plan - 30.04.2025
S.No. | Engg. | Customer | Module | Points | Type | Status | Remarks
1 | Sasi | SKS | Payroll | ATTENDANCE INCENTIVES AND WEEK OFF WORKING SALARY TO BE ADDED |  | Completed
2 |  | SKS | FA | P and L Report -customization |  | In-Progress
3 |  | SKS | Payroll | -5.NFH Days applicable only for “Staff” Category, For worker category NFH days not applicable If worker worked in NFH days it to be treated as Worked days. For Staff worked in NFH days extra one day wage to be added in salary. |  | In-Progress
4 |  | SKS | FA | 3.Transactions → Payment → Payment, when using Addition Mode, if a payment is made without an advance payment request (i.e., by selecting the option "Others"), the system does not allow entry of Sub Ledger details. |  | In-Progress
5 |  | SKS | Payroll | COMP OFF ENTRY MODULE REQUIRED |  | Pending | Spec needed
1 | Annamalai | SKS | D Sales | The Job Work statement needs to be tallied, and an Excel abstract option is required . |  | In-Progress
2 |  | SKS | D Sales | Invisible losses and gains column to be added in Job work Report |  | Pending
3 |  | SKS | D Sales | Confirmation of Yarn stock figures to be obtained from Sales team today. |  | Pending
4 |  | SKS | D Sales | A report is required to show lot-wise stock details for a specific count, primarily for viewing seconds stock |  | Pending
5 |  | SKS | QC | SKS - QC - Customer CR -07.04.2025 - Reg - As this Change Request is essential for implementation at the customer end, I kindly request your approval to proceed. |  | Pending
6 |  | SKS | SPG | Internal CR points |  | Pending
1 | Maari | SKS | RMI | Freight Bill Entry correction |  | Pending
2 |  | SKS | Invy | Freight Bill Entry correction |  | In-Progress
3 |  | SKS | Payroll | ReportMonthlyAgent commission report slab to be changed, Applicable worked days above 24 days.If worker worked 8 Hours per day – Rs.20-If worker worked 12 hours per day – Rs.30 |  | In-Progress
4 |  | SKS | PO | Budget Utilized Report |  | Pending
5 |  | SKS | Invy | 2.TransactionsPurchase BillPurchase bill freight postingSupplier name details to be loaded from MRN Entry instead of Purchase Bill Entry and also Transporter name Lookup to be loaded from “C4 – Creditors Expenses”. |  | Completed
6 |  | SKS | Invy | ReportsPeriodicalMaterial Issue ListDate wise form approved and Un approved selection option to be needed and also Customized report format to be needed as per below mentioned format. |  | Completed
1 | Udhay | SKS | FA | ReportsDailyDebit/Credit Note transaction print to be needed as per below mentioned format.
2 |  | SKS | D Sales | A report is required to show lot-wise stock details for a specific count, primarily for viewing seconds stock |  | In-Progress
3 |  | SKS | D Sales | Invisible losses and gains column to be added in Job work Report |  | Pending | Need to Add new fields
4 |  | SSVDDB | RMI | Fuel receipt list issue |  | Completed
5 |  | Shiva | Invy | Gate Pass Print correction |  | Pending
6 |  | SKS | Post Spg | Auto Coner – Machine wise Production Report. |  | Completed
7 |  | SKS | RMI | Report feedback correction |  | Completed
|  |  | S.No. | Name | Assigned | Completed | Pending | Unassigned
|  |  | 1 | Sasi | 5 | 2 | 3
|  |  | 2 | Annamalai | 6 |  | 6
|  |  | 3 | Maari | 6 | 2 | 4
|  |  | 4 | Udhay | 5 | 3 | 2
Total CR Points

## 02-04-25
Daily Action Plan - 02-05-2025
S.No. | Engg. Name | Ticket No. | Customer Name | Module | Description | Type | Status | Remarks
1 | Sasi | 2025-11725 | SKS | Payroll | P and L Report -customization |  | In-Progress
2 |  | 2025-11688 | SKS | Payroll | -5.NFH Days applicable only for “Staff” Category, For worker category NFH days not applicable If worker worked in NFH days it to be treated as Worked days. For Staff worked in NFH days extra one day wage to be added in salary. |  | Completed
3 |  | 2025-11815 | SKS | FA | 3.Transactions → Payment → Payment, when using Addition Mode, if a payment is made without an advance payment request (i.e., by selecting the option "Others"), the system does not allow entry of Sub Ledger details. |  | Pending
4 |  | 2025-10135 | SKS | Payroll | COMP OFF ENTRY MODULE REQUIRED |  | Pending
|  | 2025-11690 | SKS | Payroll | 7.ReportMonthlyAgent commission report slab to be changed, Applicable worked days above 24 days.If worker worked 8 Hours per day – Rs.20-If worker worked 12 hours per day – Rs.30 |  | Pending
5 |  | 2025-11879 | SSVDB | FA | It is requested to modify this to display a Bill-wise Voucher Print instead.This enhancement will helps to verify and approve invoice-wise split-ups more clearly and efficiently. |  | Pending | Spec needed
1 | Annamalai | 2025-11720 | SKS | D Sales | The Job Work statement needs to be tallied, and an Excel abstract option is required . |  | Pending
2 |  | 2025-11905 | SKS | D Sales | Invisible losses and gains column to be added in Job work Report |  | In-Progress
3 |  | 2025-11608 | SKS | D Sales | Confirmation of Yarn stock figures to be obtained from Sales team today. |  | Pending
4 |  | 2025-11904 | SKS | D Sales | A report is required to show lot-wise stock details for a specific count, primarily for viewing seconds stock |  | Pending
5 |  | 2025-11554 | SKS | QC | SKS - QC - Customer CR -07.04.2025 - Reg - As this Change Request is essential for implementation at the customer end, |  | Pending
6 |  | 2025-11762 | SKS | SPG | Internal CR points |  | In-Progress
1 | Maari | 2025-11329 | SKS | RMI | Freight Bill Entry correction |  | Pending
2 |  | 2025-11830 | SKS | Invy | Freight Bill Entry correction |  | In-Progress
3 |  | 2025-11736 | SKS | PO | Budget Utilized Report |  | Pending
4 |  |  | SSVDB | RMI | Coal Purchase :Debit note Correction |  | In-Progress
5 |  |  | SKS | PO | Feedback correction |  | In-Progress
1 | Udhay | 2025-11904 | SKS | D Sales | Invisible losses and gains column to be added in Job work Report |  | Pending
2 |  | 2025-11536 | Shiva | Invy | Gate Pass Print correction |  | Pending
3 |  | 2025-11736 | SKS | PO | Budget Utilized Report |  | Pending
|  | 2025-11879 | SSVDB | FA | 1.Transactions - Receipts - Bill Wise Transaction Print Correction. |  | In-Progress
4 |  |  | Kalsofte HR | Admin | Staff Logsheet prepare |  | In-Progress
S.No. | Name | Assigned | Completed | Pending | Remarks
1 | SasiKumar | 5 | 1 | 4
2 | Annamalai | 6 |  | 6
3 | Mariyaiya | 5 |  | 5
4 | UdhayaKumar | 3 |  | 3
Total

## 03-04-25
Daily Action Plan - 03-05-2025
S.No. | Engg. Name | Ticket No. | Customer Name | Module | Description | Type | Status | Remarks
1 | Sasi | 2025-11725 | SKS | Payroll | P and L Report -customization |  | Completed
2 |  | 2025-11688 | SKS | Payroll | -5.NFH Days applicable only for “Staff” Category, For worker category NFH days not applicable If worker worked in NFH days it to be treated as Worked days. For Staff worked in NFH days extra one day wage to be added in salary. |  | Completed
3 |  | 2025-11815 | SKS | FA | 3.Transactions → Payment → Payment, when using Addition Mode, if a payment is made without an advance payment request (i.e., by selecting the option "Others"), the system does not allow entry of Sub Ledger details. |  | InProgress
4 |  | 2025-10135 | SKS | Payroll | COMP OFF ENTRY MODULE REQUIRED |  | Pending
|  | 2025-11690 | SKS | Payroll | 7.ReportMonthlyAgent commission report slab to be changed, Applicable worked days above 24 days.If worker worked 8 Hours per day – Rs.20-If worker worked 12 hours per day – Rs.30 |  | Pending
5 |  | 2025-11879 | SSVDB | FA | It is requested to modify this to display a Bill-wise Voucher Print instead.This enhancement will helps to verify and approve invoice-wise split-ups more clearly and efficiently. |  | Pending | Spec needed
1 | Annamalai | 2025-11720 | SKS | D Sales | The Job Work statement needs to be tallied, and an Excel abstract option is required . |  | Pending
2 |  | 2025-11905 | SKS | D Sales | Invisible losses and gains column to be added in Job work Report |  | Pending
3 |  | 2025-11608 | SKS | D Sales | Confirmation of Yarn stock figures to be obtained from Sales team today. |  | Closed
4 |  | 2025-11904 | SKS | D Sales | A report is required to show lot-wise stock details for a specific count, primarily for viewing seconds stock |  | Pending
5 |  | 2025-11554 | SKS | QC | SKS - QC - Customer CR -07.04.2025 - Reg - As this Change Request is essential for implementation at the customer end, |  | Pending
6 |  | 2025-11762 | SKS | SPG | Internal CR points |  | Pending
1 | Maari | 2025-11329 | SKS | RMI | Freight Bill Entry correction |  | Pending
2 |  | 2025-11830 | SKS | PO | Feedback correction |  | Completed
3 |  | 2025-11830 | SKS | Invy | Freight Bill Entry corrections |  | Pending
4 |  | 2025-11690 | SKS | Payroll | ReportMonthlyAgent commission report slab to be changed, Applicable worked days above 24 days.If worker worked 8 Hours per day – Rs.20-If worker worked 12 hours per day – Rs.30 |  | Pending
1 | Udhay | 2025-11904 | SKS | D Sales | Invisible losses and gains column to be added in Job work Report |  | Pending
2 |  | 2025-11910 | BlueWeaves | PO | purchase order and service order - we need to remove the weaving division text in service order and purchase order. |  | Pending
3 |  | 2025-11478 | Shivamills | Waste Sales | Waste Sales invoice Customer Po No and Date Print is required - Reg |  | Pending
4 |  | 2025-11919 | SSVDB | PO | Re: SSVDB - PO Module - Internal CR - 2 |  | Pending
|  | 2025-11880 | SSVDB | Invy | SSVDB - Stores Inventory - Internal CR-1 |  | Pending
S.No. | Name | Assigned | Completed | Pending | Remarks
1 | SasiKumar | 5 | 2 | 3
2 | Annamalai | 6 |  | 6
3 | Mariyaiya | 5 | 1 | 4
4 | UdhayaKumar | 3 |  | 3
Total

## 05.05.25
Daily Action Plan - 05-05-2025
S.No. | Engg. Name | Ticket No. | Customer Name | Module | Description | Type | Status | Remarks
1 | Sasi | 2025-11815 | SKS | FA | 3.Transactions → Payment → Payment, when using Addition Mode, if a payment is made without an advance payment request (i.e., by selecting the option "Others"), the system does not allow entry of Sub Ledger details. |  | Pending
2 |  | 2025-11690 | SKS | Payroll | 7.ReportMonthlyAgent commission report slab to be changed, Applicable worked days above 24 days.If worker worked 8 Hours per day – Rs.20-If worker worked 12 hours per day – Rs.30 |  | Pending
3 |  | 2025-11879 | SSVDB | FA | It is requested to modify this to display a Bill-wise Voucher Print instead.This enhancement will helps to verify and approve invoice-wise split-ups more clearly and efficiently. |  | Pending
4 |  | 2025-11879 | SSVDB | Payroll | 2.Setup - Petrol Allowance (New Form) and Paycalculation correction |  | Pending
5 |  | 2025-11566 | Subam | D Sales | Local Sales - Queries - Division wise Turn over and Outstanding Report - reg - In Local Sales Module – New Query Report Division wise and Month wise Turn over Quantity and Turn over Value- Division wise and Month wise Outstanding Amount with below Slab |  | Pending
1 | Annamalai | 2025-11720 | SKS | D Sales | The Job Work statement needs to be tallied, and an Excel abstract option is required . |  | Pending
2 |  | 2025-11905 | SKS | D Sales | Invisible losses and gains column to be added in Job work Report |  | Pending
3 |  | 2025-11904 | SKS | D Sales | A report is required to show lot-wise stock details for a specific count, primarily for viewing seconds stock
4 |  | 2025-11554 | SKS | QC | SKS - QC - Customer CR -07.04.2025 - Reg - As this Change Request is essential for implementation at the customer end, |  | Pending
5 |  | 2025-11782 | Subam | D Sales | If Cancel or Delete any Invoice in Local sales module, it should be changed after completion of dual level approval.Kindly give dual level approval in Web application page. |  | Pending
6 |  |  | W sales | W Sales | Stock Difference |  | In-Progress
1 | Maari | 2025-11329 | SKS | RMI | Freight Bill Entry correction |  | Pending
2 |  | 2025-11934 | SSVDB | Invy | As per Mr. Sakkarai Sir’s request, the Material Receipt Note (MRN) print format under the Store Inventory module – Transactions requires an enhancement to include Value and Tax details. This update is essential for management approval and reference purposes. |  | Pending
3 |  | 2025-11830 | SKS | Invy | Freight Bill Entry corrections |  | Pending
4 |  |  | SSVDB | Invy | SSVDB Store Inventory_Material Receipt Note changes - As per Mr. Sakkarai Sir’s request, the Material Receipt Note (MRN) print format under the Store Inventory module – Transactions requires an enhancement to include Value and Tax details. This update is essential for management approval and reference purposes. |  | Pending
5 |  | 2025-11690 | SSVDB | RMI | Coal Purchase :Debit note Correction |  | In-Progress
1 | Udhay | 2025-11904 | SKS | D Sales | Invisible losses and gains column to be added in Job work Report |  | Pending | Leave
2 |  | 2025-11910 | BlueWeaves | PO | purchase order and service order - we need to remove the weaving division text in service order and purchase order. |  | Pending
3 |  | 2025-11478 | Shivamills | Waste Sales | Waste Sales invoice Customer Po No and Date Print is required - Reg |  | Pending
4 |  | 2025-11919 | SSVDB | PO | Re: SSVDB - PO Module - Internal CR - 2 |  | Pending
|  | 2025-11880 | SSVDB | Invy | SSVDB - Stores Inventory - Internal CR-1 |  | Pending
S.No. | Name | Assigned | Completed | Pending | Remarks
1 | SasiKumar | 5 | 0 | 5
2 | Annamalai | 6 | 0 | 6
3 | Mariyaiya | 5 | 0 | 5
4 | UdhayaKumar | 4 | 0 | 4
| Total | 20 |  | 20

## 06.05.25
Daily Action Plan - 06-05-2025
S.No. | Engg. Name | Ticket No. | Customer Name | Module | Description | Type | Status | Remarks
1 | Sasi | 2025-11815 | SKS | FA | 3.Transactions → Payment → Payment, when using Addition Mode, if a payment is made without an advance payment request (i.e., by selecting the option "Others"), the system does not allow entry of Sub Ledger details. |  | Pending
2 |  | 2025-11690 | SKS | Payroll | 7.ReportMonthlyAgent commission report slab to be changed, Applicable worked days above 24 days.If worker worked 8 Hours per day – Rs.20-If worker worked 12 hours per day – Rs.30 |  | Pending
3 |  | 2025-11879 | SSVDB | FA | It is requested to modify this to display a Bill-wise Voucher Print instead.This enhancement will helps to verify and approve invoice-wise split-ups more clearly and efficiently. |  | In Progress
4 |  | 2025-11879 | SSVDB | Payroll | 2.Setup - Petrol Allowance (New Form) and Paycalculation correction |  | In Progress
5 |  | 2025-11566 | Subam | D Sales | Local Sales - Queries - Division wise Turn over and Outstanding Report - reg - In Local Sales Module – New Query Report Division wise and Month wise Turn over Quantity and Turn over Value- Division wise and Month wise Outstanding Amount with below Slab |  | Pending
6 |  |  | BlueWeaves | Wvg Prep | Sizing Yarnreconciliation |  | Pending
1 | Annamalai | 2025-11720 | SKS | D Sales | The Job Work statement needs to be tallied, and an Excel abstract option is required . |  | Pending
2 |  | 2025-11905 | SKS | D Sales | Invisible losses and gains column to be added in Job work Report |  | Pending
3 |  | 2025-11904 | SKS | D Sales | A report is required to show lot-wise stock details for a specific count, primarily for viewing seconds stock |  | Pending
4 |  | 2025-11554 | SKS | QC | SKS - QC - Customer CR -07.04.2025 - Reg - As this Change Request is essential for implementation at the customer end, |  | Pending
5 |  | 2025-11782 | Subam | D Sales | If Cancel or Delete any Invoice in Local sales module, it should be changed after completion of dual level approval.Kindly give dual level approval in Web application page. |  | Pending
1 | Maari | 2025-11329 | SKS | RMI | Freight Bill Entry correction |  | Pending
2 |  | 2025-11934 | SSVDB | Invy | As per Mr. Sakkarai Sir’s request, the Material Receipt Note (MRN) print format under the Store Inventory module – Transactions requires an enhancement to include Value and Tax details. This update is essential for management approval and reference purposes. |  | Pending
3 |  | 2025-11830 | SKS | Invy | Freight Bill Entry corrections |  | Pending
4 |  |  | SSVDB | Invy | SSVDB Store Inventory_Material Receipt Note changes - As per Mr. Sakkarai Sir’s request, the Material Receipt Note (MRN) print format under the Store Inventory module – Transactions requires an enhancement to include Value and Tax details. This update is essential for management approval and reference purposes. |  | Pending
5 |  |  | Cheran | Invy | Kalsofte to tally export correction |  | Pending
|  |  | SSVDB | RMI | Coal purchae order correction |  | Completed | Unplanned
|  |  | Pallavaa | Invy | Job order issue correction |  | Completed | Unplanned
|  |  | Pallavaa | Invy | Service bill entry correction |  | Completed | Unplanned
1 | Udhay | 2025-11904 | SKS | D Sales | Invisible losses and gains column to be added in Job work Report |  | Leave
2 |  | 2025-11910 | BlueWeaves | PO | purchase order and service order - we need to remove the weaving division text in service order and purchase order.
3 |  | 2025-11478 | Shivamills | Waste Sales | Waste Sales invoice Customer Po No and Date Print is required - Reg
4 |  | 2025-11919 | SSVDB | PO | Re: SSVDB - PO Module - Internal CR - 2
|  | 2025-11880 | SSVDB | Invy | SSVDB - Stores Inventory - Internal CR-1
S.No. | Name | Assigned | Completed | Pending | Remarks | UnPlanned
1 | SasiKumar | 5 |  | 5
2 | Annamalai | 6 |  | 6
3 | Mariyaiya | 5 |  | 5 |  | 3
4 | UdhayaKumar | 4 |  | 4
| Total | 20 |  | 20

## 07.05.25
Daily Action Plan - 07-05-2025
S.No. | Engg. Name | Ticket No. | Customer Name | Module | Description | Type | Status | Remarks
1 | Sasi | 2025-11725 | SKS | FA | P and L Report Reconcile support if needed | In Progress
2 |  | 2025-11879 | SSVDB | FA | It is requested to modify this to display a Bill-wise Voucher Print instead.This enhancement will helps to verify and approve invoice-wise split-ups more clearly and efficiently. | In Progress
3 |  | 2025-11879 | SSVDB | Payroll | 2.Setup - Petrol Allowance (New Form) and Paycalculation correction | Pending
4 |  | 2025-11566 | Subam | D Sales | Local Sales - Queries - Division wise Turn over and Outstanding Report - reg - In Local Sales Module – New Query Report Division wise and Month wise Turn over Quantity and Turn over Value- Division wise and Month wise Outstanding Amount with below Slab | Pending
|  |  | JAT | Payroll | Employee In-Office Report form correction | Completed
5 |  |  | JAT | Payroll | OT Entry form not shown in Final Login | Completed
1 | Annamalai | 2025-11720 | SKS | D Sales | The Job Work statement needs to be tallied, and an Excel abstract option is required . | Pending
2 |  | 2025-11905 | SKS | D Sales | Invisible losses and gains column to be added in Job work Report | Pending
3 |  | 2025-11904 | SKS | D Sales | A report is required to show lot-wise stock details for a specific count, primarily for viewing seconds stock | In Progress
4 |  | 2025-11902 | SSVDB | D Sales | SSVDB Domestic Sales_Customer CR_29.04.2025 - reg - As per Sales team request, Need transaction print in the Sale Order Approval Form for verify the discount details. | Pending
5 |  | 2025-10830 | Subam | D Sales | Sales – Invoice Entry Invoice Type – to select automatically instead of user selection. | Pending
6 |  |  | Poongodhai | SPG | Daily MIS Production Report | Completed |  | UnPlanned
1 | Maari | 2025-11329 | SKS | RMI | Freight Bill Entry correction | Pending
2 |  | 2025-11865 | SSVDB | RMI | SSVDB FA Module Corrective CR_28.04.2025 - reg - 1.TransactionsPaymentsPayment request & Payment entry Outstanding Bill details need to be shown based on Payment due date bills only not for all Bills.2.Need Credit Days column. | In Progress |  | Paper :Credit Days Entry option in Bill entry and should post to Payable Table
3 |  | 2025-11865 | SSVDB | RMI | SSVDB FA Module Corrective CR_28.04.2025 - reg - 1.TransactionsPaymentsPayment request & Payment entry Outstanding Bill details need to be shown based on Payment due date bills only not for all Bills.2.Need Credit Days column. | Pending |  | Fuel:Credit Days Entry option in Bill entry and should post to Payable Table
4 |  |  | SSVDB | Invy | SSVDB Store Inventory_Material Receipt Note changes - As per Mr. Sakkarai Sir’s request, the Material Receipt Note (MRN) print format under the Store Inventory module – Transactions requires an enhancement to include Value and Tax details. This update is essential for management approval and reference purposes. | Pending
5 |  | 2025-11690 | SKS | Payroll | 7.ReportMonthlyAgent commission report slab to be changed, Applicable worked days above 24 days.If worker worked 8 Hours per day – Rs.20-If worker worked 12 hours per day – Rs.30 | In Progress
1 | Udhay | 2025-11904 | SKS | D Sales | Invisible losses and gains column to be added in Job work Report | Pending
2 |  | 2025-11902 | SSVDB | D Sales | SSVDB Domestic Sales_Customer CR_29.04.2025 - reg - As per Sales team request, Need transaction print in the Sale Order Approval Form for verify the discount details. | Pending
3 |  | 2025-11478 | Shivamills | Waste Sales | Waste Sales invoice Customer Po No and Date Print is required - Reg | Pending
4 |  | 2025-11879 | SSVDB | FA | SSVDB FA Customer CR_29.04.2025 - reg - It is requested to modify this to display a Bill-wise Voucher Print instead.This enhancement will helps to verify and approve invoice-wise split-ups more clearly and efficiently. | Pending
S.No. | Name | Assigned | Completed | Pending | Remarks | UnPlanned
1 | SasiKumar | 5 | 2 | 3
2 | Annamalai | 5 |  | 5 |  | 1
3 | Mariyaiya | 5 |  | 5
4 | UdhayaKumar | 4 |  | 4
Total

## 08.05.25
Daily Action Plan - 08-05-2025
S.No. | Engg. Name | Ticket No. | Customer Name | Module | Description | Type | Status | Remarks
1 | Sasi | 2025-11725 | SKS | FA | P and L Report Reconcile support if needed |  | In progress
2 |  | 2025-11879 | SSVDB | FA | It is requested to modify this to display a Bill-wise Voucher Print instead.This enhancement will helps to verify and approve invoice-wise split-ups more clearly and efficiently. |  | In progress
3 |  | 2025-11879 | SSVDB | Payroll | 2.Setup - Petrol Allowance (New Form) and Paycalculation correction |  | In progress
4 |  | 2025-11566 | Subam | D Sales | Local Sales - Queries - Division wise Turn over and Outstanding Report - reg - In Local Sales Module – New Query Report Division wise and Month wise Turn over Quantity and Turn over Value- Division wise and Month wise Outstanding Amount with below Slab |  | Pending
5 |  |  | BlueWeaves | Wvg Prep | Sizing Yarn Stock – Implementation required |  | Pending
6 |  |  | SSVDB |  | Coal Biull Entry - Debit Note Posting verification |  | In progress
7 |  |  | SCM | FA | PJV Print - Data Filter option |  | Completed
8 |  |  | SKS | FA | Journal Entry - Cost Center selection issue correction |  | Completed
1 | Annamalai | 2025-11720 | SKS | D Sales | The Job Work statement Excel abstract option is required . |  | In progress
2 |  | 2025-11905 | SKS | D Sales | Invisible losses and gains column to be added in Job work Report |  | Completed
3 |  | 2025-11904 | SKS | D Sales | A report is required to show lot-wise stock details for a specific count, primarily for viewing seconds stock |  | In progress
4 |  | 2025-11902 | SSVDB | D Sales | SSVDB Domestic Sales_Customer CR_29.04.2025 - reg - As per Sales team request, Need transaction print in the Sale Order Approval Form for verify the discount details. |  | In progress
5 |  | 2025-10830 | Subam | D Sales | Sales – Invoice Entry Invoice Type – to select automatically instead of user selection. |  | Pending
|  |  | Pallavaa | Spg | Productrion Report Scrip update support |  | Completed | Unplanned
|  |  | Bannari | Waste Sales | Stock Report tallied correction |  | Completed | Unplanned
1 | Maari | 2025-10688 | Sivadharshini |  | Boiler entry customisation |  | Pending
2 |  | 2025-11865 | SSVDB | RMI | SSVDB FA Module Corrective CR_28.04.2025 - reg - 1.TransactionsPaymentsPayment request & Payment entry Outstanding Bill details need to be shown based on Payment due date bills only not for all Bills.2.Need Credit Days column. |  | Completed | Paper :Credit Days Entry option in Bill entry and should post to Payable Table
3 |  | 2025-11865 | SSVDB | RMI | SSVDB FA Module Corrective CR_28.04.2025 - reg - 1.TransactionsPaymentsPayment request & Payment entry Outstanding Bill details need to be shown based on Payment due date bills only not for all Bills.2.Need Credit Days column. |  | Completed | Fuel:Credit Days Entry option in Bill entry and should post to Payable Table
4 |  |  | Southern | Invy | Mateiral Request List supplierwise |  | Completed | Unplanned
1 | Udhay | 2025-11904 | SKS | D Sales | Invisible losses and gains column to be added in Job work Report |  | Completed
2 |  | 2025-11902 | SSVDB | D Sales | SSVDB Domestic Sales_Customer CR_29.04.2025 - reg - As per Sales team request, Need transaction print in the Sale Order Approval Form for verify the discount details. |  | In progress
3 |  | 2025-11478 | Shivamills | Waste Sales | Waste Sales invoice Customer Po No and Date Print is required - Reg |  | Completed
4 |  | 2025-11879 | SSVDB | FA | SSVDB FA Customer CR_29.04.2025 - reg - It is requested to modify this to display a Bill-wise Voucher Print instead.This enhancement will helps to verify and approve invoice-wise split-ups more clearly and efficiently. |  | Completed
1 | PremKumar |  | SSVDB | Invy | SSVDB Store Inventory_Material Receipt Note changes - As per Mr. Sakkarai Sir’s request, the Material Receipt Note (MRN) print format under the Store Inventory module – Transactions requires an enhancement to include Value and Tax details. This update is essential for management approval and reference purposes.
2 |  | 2025-11902 | SSVDB | Payroll | SSVDB Payroll module Customer CR_01.05.2025 - reg |  | In progress
3 |  | 2025-11478 | SSVDB | Payroll | SSVDB Payroll Module Salary Statement - Reg |  | Completed
S.No. | Name | Assigned | Completed | Pending | Remarks | UnPlanned
1 | SasiKumar | 5 |  |  |  | 2
2 | Annamalai | 5 |  |  |  | 3
3 | Mariyaiya | 5 | 2 |  |  | 1
4 | UdhayaKumar | 4 | 3
5 | PremKumar | 3 | 1
| Total | 22 | 6 |  |  | 6

## 09.05.25
Daily Action Plan - 09-05-2025
S.No. | Engg. Name | Ticket No. | Customer Name | Module | Description | Type | Status | Remarks
1 | Sasi | 2025-11725 | SKS | FA | P and L Report Reconcile |  | Inprogress
2 |  | 2025-11879 | SSVDB | FA | It is requested to modify this to display a Bill-wise Voucher Print instead.This enhancement will helps to verify and approve invoice-wise split-ups more clearly and efficiently. |  | Completed
3 |  | 2025-11566 | Subam | D Sales | Local Sales - Queries - Division wise Turn over and Outstanding Report - reg - In Local Sales Module – New Query Report Divisionwise and Month wise Turn over Quantity and Turn over Value- Division wise and Month wise Outstanding Amount with below Slab |  | Pending
4 |  |  | BlueWeaves | Wvg Prep | Sizing Yarn Stock – Implementation required |  | Inprogress
5 |  |  | SKS | FA | Payment , receipt , Journal -Costcentre Lookup Correction |  | Completed
6 |  |  | Pallavaa | FA | Advance Payment : PO Not showing for selection |  | Completed | No issue in ERP
1 | Annamalai | 2025-11720 | SKS | D Sales | The Job Work statement Excel abstract option is required . |  | Inprogress
2 |  | 2025-11904 | SKS | D Sales | A report is required to show lot-wise stock details for a specific count, primarily for viewing seconds stock |  | Completed
3 |  | 2025-10830 | Subam | D Sales | Sales – Invoice Entry Invoice Type – to select automatically instead of user selection. |  | Pending
4 |  |  | Subam | D Sales | Sales Discounts - Reg. |  | Pending
5 |  |  | Pallavaa | QC | SR-3235 // PTL1 // QA // MIS - DAILY QUALITY REPORT // REPORT CORRECTION |  | Pending
1 | Maari | 2025-11656 | Gomathi | Invy | Debit Note / Credit Note – Print correction pending for AMC collection. |  | Pending
2 |  | 2025-11336 | Subam | D Sales | Work order Report in Excel format - reg |  | Inprogress
3 |  | 2025-12033 | BlueWeaves | Invy | COMPELED POINTS ERORR - if he returns the same item, kindly correct this. |  | Pending
4 |  | 2025-11656 | Gomathi | Invy | NO TAX BILL - WHEN I PRINT THE PURCHASE BILL IN DOT MATRIX PRINTER THERE IS NO TAX , IT SHOULD BE WITH TAX SIR THEN SERVICE BILL ALSO NO PRINT IN DOT MATRIX PRINTER |  | Pending
|  | 2025-12004 | SSVDB | Import | Weight Sortage Entry issue |  | Completed
|  | 2025-11729 | SKS | Power | Reg - SKS Mills - Power - Customer CR 21042025 -Reports Periodical Power Consumption Crystal Above mentioned data need to capture below mentioned (Image2)i)Add “Day Total Distribution Loss Units” after the “Day Total”ii)Add “Grand Total Distribution Loss Units” after the “Grand Day Total” |  | Inprogress
1 | Udhay | 2025-11904 | Sivadharshini | Prod. | Boiler entry customisation |  | Pending
2 |  | 2025-11902 | SSVDB | D Sales | SSVDB Domestic Sales_Customer CR_29.04.2025 - reg - As per Sales team request, Need transaction print in the Sale Order Approval Form for verify the discount details. |  | Completed
3 |  | 2025-11478 | JAT | Invy | JAT - Store Inventory - Customer CR 160425 - 1.TransactionsMaterial Receipt NoteMaterial Receipt With PO & Without PO transaction print to be needed same like SCMTS with Item Images |  | Inprogress
4 |  |  | SSVDB | Invy | SSVDB Store Inventory_Material Receipt Note changes - As per Mr. Sakkarai Sir’s request, the Material Receipt Note (MRN) print format under the Store Inventory module – Transactions requires an enhancement to include Value and Tax details. This update is essential for management approval and reference purposes. |  | Closed
5 |  | 2025-12019 | SSVDB | Import | SSVDB Import Corrective CR_07.05.2025 - reg - 1.Transactions - Purchase Order |  | Pending
|  | 2025-11904 | SKS | D Sales | A report is required to show lot-wise stock details for a specific count, primarily for viewing seconds stock |  | Completed | Report Design Completed
Authorized Signatory's digital signature is not showing in the Transaction Print after MD Approval.
1 | PremKumar | 2025-12013 | SSVDB | Scrap Sales | SSVDB Scrap Sales module Corrective CR_06.05.2025 - reg - 5.Reports - sales Day book |  | Inprogress
2 |  | 2025-12012 | SSVDB | Scrap Sales | SSVDB Scrap Sales module Corrective CR_06.05.2025 - reg - 4.Reports - Covering Lettert |  | Completed
3 |  | 2025-12016 | SSVDB | Scrap Sales | SSVDB Scrap Sales module Corrective CR_06.05.2025 - reg - 8.Reports - Delivery Challan |  | Completed
4 |  | 2025-12026 | Blueweaves | Canteen | CANTEEN ADJUSTMENT - Canteen adjustment entry value shown stock statement report. |  | Inprogress
|  | 2025-11478 | SSVDB | Payroll | SSVDB Payroll Module Salary Statement - Reg .Feedback correction |  | Inprogress
S.No. | Name | Assigned | Completed | Pending | Remarks | UnPlanned
1 | SasiKumar | 4 | 1 | 3 |  | 2
2 | Annamalai | 5 | 1 | 4
3 | Mariyaiya | 4 | 1 | 3
4 | UdhayaKumar | 5 | 1 | 4 |  | 1
5 | PremKumar | 4 | 2 | 2
| Total | 22 | 6 | 16 |  | 3

## 10-05-25
Daily Action Plan - 09-05-2025
S.No. | Engg. Name | Ticket No. | Customer Name | Module | Description | Type | Status | Remarks
1 | Sasi | 2025-11725 | SKS | FA | P and L Report Reconcile |  | InProgress
2 |  | 2025-11879 | SSVDB | FA | It is requested to modify this to display a Bill-wise Voucher Print instead.This enhancement will helps to verify and approve invoice-wise split-ups more clearly and efficiently. |  | Closed
3 |  | 2025-11566 | Subam | D Sales | Local Sales - Queries - Division wise Turn over and Outstanding Report - reg - In Local Sales Module – New Query Report Divisionwise and Month wise Turn over Quantity and Turn over Value- Division wise and Month wise Outstanding Amount with below Slab |  | Pending
4 |  |  | BlueWeaves | Wvg Prep | Sizing Yarn Stock – Implementation required |  | InProgress
|  | 2025-12061 | Subam | FA | Payment Request - Debit Note not deducted issue |  | Completed | Un Planned
1 | Annamalai | 2025-11720 | SKS | D Sales | The Job Work statement Excel abstract option is required . |  | Pending
2 |  |  | Bannari | W Sales | Despatch Entry : Feedback correction |  | Pending
3 |  | 2025-10830 | Subam | D Sales | Sales – Invoice Entry Invoice Type – to select automatically instead of user selection. |  | Pending
4 |  |  | Subam | D Sales | Sales Discounts - Reg. |  | Pending
5 |  |  | Pallavaa | QC | SR-3235 // PTL1 // QA // MIS - DAILY QUALITY REPORT // REPORT CORRECTION |  | Completed
|  |  | Pallavaa | QC | SR-3224 // SCSL3 // QC MODULE // ACTIVITY SCHEDULE |  | Completed | Un Planned
1 | Maari | 2025-11656 | Gomathi | Invy | Debit Note / Credit Note – Print correction pending for AMC collection. |  | Pending
2 |  | 2025-11846 | SSVDB | Payroll | SSVDB Payroll Module Salary Statement - Reg - 2.Setup - Petrol Allowance (New Form) |  | Pending
3 |  | 2025-12033 | BlueWeaves | Invy | COMPELED POINTS ERORR - if he returns the same item, kindly correct this. |  | Completed
4 |  | 2025-11656 | Gomathi | Invy | NO TAX BILL - WHEN I PRINT THE PURCHASE BILL IN DOT MATRIX PRINTER THERE IS NO TAX , IT SHOULD BE WITH TAX SIR THEN SERVICE BILL ALSO NO PRINT IN DOT MATRIX PRINTER |  | Pending
|  |  | SKS | Power | SKS Mills - Power - Customer CR 21042025 |  | Completed | Un Planned
1 | Udhay | 2025-11904 | Sivadharshini | Prod. | Boiler entry customisation |  | Pending
2 |  | 2025-11690 | SSVDB | RMI | SSVDB RMI_Fuel Invoice Corrections_30.04.2025 - reg - If Format Received |  | Pending
3 |  | 2025-12019 | SSVDB | Import | SSVDB Import Corrective CR_07.05.2025 - reg - 1.Transactions - Purchase Order |  | Completed
4 |  | 2025-11257 | Subam | D Sales | Sales Discounts - Reg. |  | Pending
|  | 2025-11793 | Cheran Spinner | D Sales | Invoice Print & Packing List Print. |  | Completed | Un Planned
Authorized Signatory's digital signature is not showing in the Transaction Print after MD Approval.
1 | PremKumar | 2025-12016 | SSVDB | Scrap Sales | SSVDB Scrap Sales module Corrective CR_06.05.2025 - reg - 8.Reports - Delivery Challan |  | Completed
2 |  | 2025-12026 | Blueweaves | Canteen | CANTEEN ADJUSTMENT - Canteen adjustment entry value shown stock statement report. |  | InProgress
3 |  | 2025-11478 | SSVDB | Payroll | SSVDB Payroll Module Salary Statement - Reg .Feedback correction |  | InProgress
4 |  |  | Poongodhai | Wvg Prod | Tolerance Meters option instead of % in inspection and Piece grading |  | Pending
S.No. | Name | Assigned | Completed | Pending | Remarks | UnPlanned
1 | SasiKumar | 4 |  | 4 |  | 1
2 | Annamalai | 5 | 1 | 4 |  | 1
3 | Mariyaiya | 4 | 1 | 3 |  | 1
4 | UdhayaKumar | 4 | 1 | 3 |  | 1
5 | PremKumar | 4 | 1 | 3
| Total | 21 | 4 | 17 |  | 4

## 12.05.25
Daily Action Plan - 12-05-2025
S.No. | Engg. Name | Ticket No. | Customer Name | Module | Description | Type | Status | Remarks
1 | Sasi | 2025-11725 | SKS | FA | P and L Report Reconcile
2 |  | 2025-11566 | Subam | D Sales | Local Sales - Queries - Division wise Turn over and Outstanding Report - reg - In Local Sales Module – New Query Report Divisionwise and Month wise Turn over Quantity and Turn over Value- Division wise and Month wise Outstanding Amount with below Slab
3 |  | 2024-9759 | BlueWeaves | Wvg Prep | Sizing Yarn Stock – Implementation required
4 |  | 2025-11690 | SKS | Payroll | Agent commission report
1 | Annamalai |  | Cheran | D Sales | 1.hen Invoice Manual Process and Barcode Scanning Process Discount amount difference Found Discount Amount Difference in Manual vs. Barcode Scanning Invoice Process
2 |  |  | Bannari | W Sales | Despatch Entry : Feedback correction
3 |  | 2025-10830 | Subam | D Sales | Sales – Invoice Entry Invoice Type – to select automatically instead of user selection.
4 |  |  | Subam | D Sales | Sales Discounts - Reg.
5 |  |  | SKS | D Sales | MAG integration
1 | Maari |  | SKS | PO | RCM - GST GL Mapping Option - Related to Freight Bill entry for RM
2 |  |  | SKS | RMI | Freight Bill entry for RM module
3 |  |  | SSVDB | Power | SSVDB - Power - Customer CR - 02052025 : 1.Transactions Power Consumption Make Customer ID “SSVDB” Add three Columns “Open Hour Meter”, “Close House Meter”, “Hour Meter Run” |  |  | CR to be approved
4 |  |  | SSVDB | Power | 2.Reports Reports → Periodical → HT Meter Reading section: i)Remove the “KWH” Column oPurpose: This column is to be removed to accommodate the new field “RKVAR Units.” ii)Insert a New Column – “RKVAR Units” oSource Table: PW_HTRead oFormula: RKVAR Units = (Current KVRMD – Previous KVRMD) * Multiplication Factor oNote: Use the Shift Time 07:00 AM reading for the above calculation. |  |  | CR to be approved
5 |  |  | SSVDB | Power | i) OLTC – The report should display the sum of consumed units across all three shifts as a daily total under OLTC Transformer Tab Change Reading |  |  | CR to be approved
1 | Udhay | 2025-11690 | Cheran | D Sales | Agent wise report correction
2 |  |  | JAT | Invy | JAT - Store Inventory - Customer CR 160425 - 1.TransactionsMaterial Receipt NoteMaterial Receipt With PO & Without PO transaction print to be needed same like SCMTS with Item Images
3 |  |  | SSVDB | Power | SSVDB - Power - Customer CR - 02052025: 3.Reports Periodical HT meter Reading Purpose: These values should be entered directly without applying the system-based (Current – Previous) calculation validation, to allow flexibility in capturing actual MD values
4 |  |  | Pallavaa | Power | SR-2546 // PTL2// POWER ACCOUNTING// REPORT CORRECTION |  |  | CR to be approved
5 |  |  | Subam | D Sales | Sales Discounts - Reg.
Authorized Signatory's digital signature is not showing in the Transaction Print after MD Approval.
1 | PremKumar | 2025-11947 | SRG | Scrap Sales | SRG Apparels - Knitting Division - Fabric Sales - Customer CR 02.05.2025 - Reg - 1.Transaction -> Fabric Out pass:a.The transaction print takes longer than usual to open.
2 |  | 2025-12026 | Blueweaves | Canteen | CANTEEN ADJUSTMENT - Canteen adjustment entry value shown stock statement report.
3 |  | 2025-11478 | SSVDB | Payroll | SSVDB Payroll Module Salary Statement - Reg .Feedback correction
4 |  | 2025-11846 | SSVDB | Payroll | SSVDB Payroll Module Salary Statement - Reg - 2.Setup - Petrol Allowance (New Form)
S.No. | Name | Assigned | Completed | Pending | Remarks
1 | SasiKumar | 4
2 | Annamalai | 5
3 | Mariyaiya | 5
4 | UdhayaKumar | 4
5 | PremKumar | 4
| Total | 22

## Sheet1
Daily Action Plan - 12-05-2025
S.No. | Engg. Name | Ticket No. | Customer Name | Module | Description | Type | Status | Remarks
1 | Maari |  | SCMTS | RMI | Purchase bill entry - GST selection correction for import purchase.
2 |  |  | SKS | RMI | Freight Bill entry for RM module
|  |  | SKS | Invy | Issue requisition - Value to be displayed.
3 |  |  | Bannari | Invy | JOB ORDER ENTRY SCREEN - ARTICLE SELECTION and GRN Footer correction
4 |  |  | Bannari | RMI | LOT BALE DETAILS ENTRY SCREEN - VALIDATION
5
S.No. | Name | Assigned | Completed | Pending | Remarks
1 | SasiKumar | 4
2 | Annamalai | 5
3 | Mariyaiya | 5
4 | UdhayaKumar | 4
5 | PremKumar | 4
| Total | 22