## 📋 HOW TO USE
KALSOFTE ERP · MONTHLY WORK SUMMARY TEMPLATE · TEAM USAGE GUIDE
| SUBMISSION RULE | Submit on or before the 3rd of every subsequent month to CEO (ceo@kalsofte.com).
WHO FILLS WHICH SHEET?
| PM – Project Manager | PM Saravanan
| DEV Team – Developer | TL-Dev · VB Developers · Full-Stack & Jr. Web Devs
| IST Team – Support | TL-IST · IST Members (incl. Vertical SMEs)
HOW TO FILL – SECTION B (ATTENDANCE)
| B1 | Enter total calendar days in the month (e.g., 30 for April)
| B2 | Count ALL Sundays + public/gazette holidays in that month
| B3 | AUTO-CALCULATED (B1 – B2). Do not edit.
| B4 | Enter actual days you worked (present days)
| B5 | Enter approved leaves taken (PL / CL / ML)
| B6 | Enter LOP (Loss of Pay) or unauthorised absence days
| B7 | Enter Compensatory Off availed (if any)
| B8 | AUTO-CALCULATED (B4 – B6). Salary eligible days.
| B9 | AUTO-CALCULATED (B4 ÷ B3). Attendance percentage.
| CHECK ROW | Must show ✔ OK before submitting. If ✖ MISMATCH shows, review B1–B6.
HOW TO FILL – TASK LOG
| One row per task | Each CR, ticket, support call, meeting, development item = one row
| ERP Initiative | ERP 7.4 = legacy VB6 ERP ¦ SPINRISE = web migration project ¦ SPINNOVA = AI framework ¦ Internal = HR/admin/training
| Issue Type | Use dropdown: Operational / Corrective CR / Requirement / Implementation / Testing / Documentation / Meeting
| Resolution Status | Use dropdown: Completed / In Progress / Pending / Carry Forward
| Complexity | Low = <1 hr ¦ Medium = 1–4 hrs ¦ High = >4 hrs or architectural
| AI Tool Used | Name the AI tool used (Claude / ChatGPT / Gemini etc.) or None
| SPINRISE STAGE GUIDE | FSD Draft → TL Review → CEO Approval → Dev In Progress → IST Testing → CEO Demo → Deployed
| SELF-APPRAISAL | Mandatory section. Minimum 2 lines per field. This is YOUR professional growth record.
| IMPORTANT | Do NOT break merge cells or delete rows. Add rows inside the task log table if needed.

## PM – Project Manager
KALSOFTE ERP ¦ MONTHLY WORK SUMMARY
ROLE: PROJECT MANAGER · ERP Support · Implementation · BD · SpinRise · SpinNova
SECTION A · EMPLOYEE & SUBMISSION DETAILS
Employee Name
Employee ID / Code
Designation
Vertical / Domain |  |  | Spinning ERP / Paper Mill ERP / Both
Reporting To |  |  | CEO / PM Saravanan
Year & Month |  |  | YYYY-MM
Date of Submission |  |  | DD-MMM-YYYY (due: 3rd of next month)
SECTION B · MONTHLY ATTENDANCE SUMMARY
Metric |  |  |  | Value |  |  | Notes / Auto-Calculation
(B1) Total Days in the Month | [6 empty] | e.g. 31 for March
(B2) Weekly Off Days (All Sundays + Public Holidays) | [6 empty] | Count all Sundays + gazette holidays
(B3) Office Working Days [AUTO] | [6 empty] | AUTO: B1 – B2
(B4) Days Present (Actual Days Worked) | [6 empty] | Days you physically / remotely worked
(B5) Authorised Leave Taken (PL / CL / ML) | [6 empty] | Approved leaves only
(B6) LOP Days (Loss of Pay / Unauthorised Absence) | [6 empty] | Unapproved absence or excess leave
(B7) Comp-Off Availed | [6 empty] | Compensatory off taken
(B8) Salary Eligible Days [AUTO: B4 – B6] | [6 empty] | AUTO: B4 – B6 (enter B4 & B6 first)
(B9) Attendance Rate [AUTO: B4 ÷ B3] | [6 empty] | AUTO: B4 / B3
(B10) Average Hours / Day | [6 empty] | Approx daily hours (include extra hours)
✔ CROSS-CHECK: Month Days = B3 + B2 + B5 + B6 (Must show OK) |  |  |  | Fill B1 to B6 first |  |  | This cell must show ✔ OK before you submit the summary to CEO
SECTION C · MONTHLY KPI SNAPSHOT (fill manually or carry from task log)
Total Tickets / Tasks Managed | [6 empty] | No. of On-Site Visits (Customer)
Remote Demos / Pre-Sales Meetings | [6 empty] | Offers / Proposals Sent
New Leads Generated | [6 empty] | SpinRise Coordination Tasks
SpinNova Coordination Tasks | [6 empty] | Implementation Projects Active
SECTION D · CUSTOMER SUPPORT, IMPLEMENTATION & COORDINATION LOG
S.No | Customer / Project | Module | CR / Ticket No. | Issue / Task Type | ERP Initiative | Effort (hrs) | Description of Work Done (be specific) |  |  | Resolution Status | Complexity | AI Tool Used?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
0 tasks logged ¦ 0 Completed ¦ 0 Pending | [5 empty] | 0
SECTION E · ON-SITE VISITS & FIELD ACTIVITIES
Activity Type |  | Customer / Project |  | Date(s) |  | Outcome / Key Discussions |  |  |  |  | Status
SECTION · BUSINESS DEVELOPMENT & PRE-SALES ACTIVITY LOG
Prospect / Customer |  |  | Vertical | Activity Description |  |  | Stage |  | Offer Sent? | Demo Done? | Next Action | Status
SECTION · REPORTING DISCIPLINE COMPLIANCE
Report / Deliverable Type |  |  |  | Frequency |  | Target |  | Submitted |  | On Time? | Status | Remarks
Daily Work Log (Pulse360 / Logsheet entry) |  |  |  | Daily
Weekly Task Plan |  |  |  | Weekly
Pending CR Status Report |  |  |  | Weekly
Live Implementation Project Status |  |  |  | Weekly
Project / Implementation Schedule Update |  |  |  | Weekly
Monthly Work Summary (this document) |  |  |  | Monthly
SECTION · SKILL ENHANCEMENT & PROFESSIONAL DEVELOPMENT
S.No | Learning Area |  |  | Course / Activity |  |  | Platform / Source |  | Hours Invested | Status | How Applied to Work?
1
2
3
4
5
SECTION · MONTHLY SELF-REFLECTION & PERFORMANCE APPRAISAL
Top 3 Key Accomplishments this Month
Challenges Faced & How Resolved
What I Should Have Done Better / Gaps
Support or Resources Needed from Management
My Goals for Next Month (specific & measurable)
Employee Signature & Date
CEO Review & Acknowledgement (date)

## DEV – Developer
KALSOFTE ERP ¦ MONTHLY WORK SUMMARY
ROLE: DEVELOPER (VB / Web) · ERP 7.4 · SpinRise Migration · SpinNova · Feature Enhancements
SECTION A · EMPLOYEE & SUBMISSION DETAILS
Employee Name |  |  | Abinandan
Employee ID / Code
Designation |  |  | Full-Stack Developer
Vertical / Domain |  |  | Spinrise
Reporting To |  |  | CEO
Year & Month |  |  | 2026-04
Date of Submission |  |  | 2026-05-04
SECTION B · MONTHLY ATTENDANCE SUMMARY
Metric |  |  |  | Value |  |  | Notes / Auto-Calculation
(B1) Total Days in the Month |  |  |  | 30 |  |  | e.g. 31 for March
(B2) Weekly Off Days (All Sundays + Public Holidays) |  |  |  | 7 |  |  | Count all Sundays + gazette holidays
(B3) Office Working Days [AUTO] |  |  |  | 23 |  |  | AUTO: B1 – B2
(B4) Days Present (Actual Days Worked) |  |  |  | 22.5 |  |  | Days you physically / remotely worked
(B5) Authorised Leave Taken (PL / CL / ML) |  |  |  | 0.5 |  |  | Approved leaves only
(B6) LOP Days (Loss of Pay / Unauthorised Absence) |  |  |  | 0 |  |  | Unapproved absence or excess leave
(B7) Comp-Off Availed |  |  |  | 0 |  |  | Compensatory off taken
(B8) Salary Eligible Days [AUTO: B4 – B6] |  |  |  | 22.5 |  |  | AUTO: B4 – B6 (enter B4 & B6 first)
(B9) Attendance Rate [AUTO: B4 ÷ B3] |  |  |  | 97.83% |  |  | AUTO: B4 / B3
(B10) Average Hours / Day |  |  |  | 9 |  |  | Approx daily hours (include extra hours)
✔ CROSS-CHECK: Month Days = B3 + B2 + B5 + B6 (Must show OK) |  |  |  | OK - Submit |  |  | This cell must show ✔ OK before you submit the summary to CEO
SECTION C · MONTHLY KPI SNAPSHOT (fill manually or carry from task log)
Total CRs Completed (Forms + Reports + Fixes) | [6 empty] | SpinRise Modules In Progress
Total Effort Hours | [6 empty] | FSDs Drafted / Submitted
FSDs Approved by CEO | [6 empty] | DB Scripts / Corrections
Code Reviews Done | [6 empty] | AI Tool Usages (no. of sessions)
SECTION D · DEVELOPMENT TASK LOG (CRs · FSDs · Fixes · SpinRise · SpinNova)
S.No | CR / FSD Ref | Module | Customer / Project | ERP Initiative | Task Type | Effort (hrs) | Description / Scope |  | Stage Completed | Review Status | AI Tool Used | Remarks
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
SECTION E · SPINRISE / SPINNOVA MODULE PROGRESS TRACKER
Module Ref | Module Name |  | FSD Version |  | Current Stage |  | Target Date |  | Actual / Est. Date |  | Status | Remarks
Phase-0 | SPINRISE Platform Foundation |  | Blueprint v4 |  | Deployed | [5 empty] | Complete
M01-PR | Purchase Requisition (PR Form) |  | FSD v2.4 |  | Deployed | [5 empty] | Completed
M02-PO | RMI Purchase Order |  | FSD v8 |  | Development Complete — 19 SPs, React form built; JAT DB deploy + IST pending | [5 empty] | In Progress
M01-RPT | PR Print Report (QuestPDF PDF + EPPlus Excel) |  | FSD v2.4 |  | Deployed | [5 empty] | Complete
SECTION F · INTERNAL MEETINGS & ACTIVITIES
Activity Type |  | Customer / Project |  | Date(s) |  | Outcome / Key Discussions |  |  |  |  | Status
SECTION · REPORTING DISCIPLINE COMPLIANCE
Report / Deliverable Type |  |  |  | Frequency |  | Target |  | Submitted |  | On Time? | Status | Remarks
Daily Work Log (Pulse360 / Logsheet entry) |  |  |  | Daily
Weekly Task Plan |  |  |  | Weekly
Pending CR Status Report |  |  |  | Weekly
Live Implementation Project Status |  |  |  | Weekly
Project / Implementation Schedule Update |  |  |  | Weekly
Monthly Work Summary (this document) |  |  |  | Monthly
SECTION · SKILL ENHANCEMENT & PROFESSIONAL DEVELOPMENT
S.No | Learning Area |  |  | Course / Activity |  |  | Platform / Source |  | Hours Invested | Status | How Applied to Work?
1
2
3
4
5
SECTION · MONTHLY SELF-REFLECTION & PERFORMANCE APPRAISAL
Top 3 Key Accomplishments this Month
1. SPINRISE Platform Foundation Complete — API, JWTAuth, API Integration with Frontend, Reporting Tools (Quest PDF and EPPLus)
2. Delivered M01 Purchase Requisition end-to-end (ASP.NET Core 8 API + 27 stored procedures + React 18 UI). All 14 High-severity IST bugs fixed by 2 May; on 2 May 2026 passed with 38/40 IST cases PASS.
Challenges Faced & How Resolved
1. IST revealed 57 failures in 101-step test cycle (44% pass rate). Root cause: several FSD validation rules (qtyind column, ABCFLG req type, serial-no generation) implemented against incorrect assumptions. Resolved by systematic priority sprint — all 14 High items closed by EOD 30 Apr, re-test confirmed PASS.
What I Should Have Done Better / Gaps
Written unit tests before IST handover — higher test coverage would have caught several of the 57 IST failures at development stage. Should also update task log entries daily rather than retrospectively, and validate DB column names against live schema before writing SPs.
Support or Resources Needed from Management
My Goals for Next Month (specific & measurable)
1. Close M01 IST to 40/40 PASS — resolve issues #40 and #26 once Sasi confirms design; deploy to IIS production; get customer-level sign-off.
2. Deploy M02 RMI PO to JAT DB; complete IST testing for PO form; fix PO dropdown UX (code+name combined field). 3. Begin M03 Domestic Sales FSD review and initial development; target IST handover by end June.
Employee Signature & Date
CEO Review & Acknowledgement (date)

## IST – Support & Testing
KALSOFTE ERP ¦ MONTHLY WORK SUMMARY
ROLE: IST (Implementation · Support · Testing) · ERP 7.4 · SpinRise IST · SpinNova IST
SECTION A · EMPLOYEE & SUBMISSION DETAILS
Employee Name
Employee ID / Code
Designation
Vertical / Domain |  |  | Spinning ERP / Paper Mill ERP / Both
Reporting To |  |  | CEO / PM Saravanan
Year & Month |  |  | YYYY-MM
Date of Submission |  |  | DD-MMM-YYYY (due: 3rd of next month)
SECTION B · MONTHLY ATTENDANCE SUMMARY
Metric |  |  |  | Value |  |  | Notes / Auto-Calculation
(B1) Total Days in the Month | [6 empty] | e.g. 31 for March
(B2) Weekly Off Days (All Sundays + Public Holidays) | [6 empty] | Count all Sundays + gazette holidays
(B3) Office Working Days [AUTO] | [6 empty] | AUTO: B1 – B2
(B4) Days Present (Actual Days Worked) | [6 empty] | Days you physically / remotely worked
(B5) Authorised Leave Taken (PL / CL / ML) | [6 empty] | Approved leaves only
(B6) LOP Days (Loss of Pay / Unauthorised Absence) | [6 empty] | Unapproved absence or excess leave
(B7) Comp-Off Availed | [6 empty] | Compensatory off taken
(B8) Salary Eligible Days [AUTO: B4 – B6] | [6 empty] | AUTO: B4 – B6 (enter B4 & B6 first)
(B9) Attendance Rate [AUTO: B4 ÷ B3] | [6 empty] | AUTO: B4 / B3
(B10) Average Hours / Day | [6 empty] | Approx daily hours (include extra hours)
✔ CROSS-CHECK: Month Days = B3 + B2 + B5 + B6 (Must show OK) |  |  |  | Fill B1 to B6 first |  |  | This cell must show ✔ OK before you submit the summary to CEO
SECTION C · MONTHLY KPI SNAPSHOT (fill manually or carry from task log)
Total Tickets / Tasks Handled | [6 empty] | Total Tickets Resolved (Completed)
Carry Forward / Pending | [6 empty] | Total Effort Hours (approx.)
No. of On-Site Visits | [6 empty] | SpinRise IST Tasks
SpinNova IST Tasks | [6 empty] | Customers Served
SECTION D · ERP SUPPORT & IMPLEMENTATION TASK LOG
S.No | Customer / Project | Module | CR / Ticket No. | Issue / Task Type | ERP Initiative | Effort (hrs) | Description of Work Done (be specific) |  |  | Resolution Status | Complexity | AI Tool Used?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
0 tasks logged ¦ 0 Completed ¦ 0 Pending | [5 empty] | 0
SECTION E · SPINRISE / SPINNOVA MODULE PROGRESS TRACKER
Module Ref | Module Name |  | FSD Version |  | Current Stage |  | Target Date |  | Actual / Est. Date |  | Status | Remarks
SECTION F · ON-SITE VISITS & INTERNAL ACTIVITIES
Activity Type |  | Customer / Project |  | Date(s) |  | Outcome / Key Discussions |  |  |  |  | Status
SECTION · REPORTING DISCIPLINE COMPLIANCE
Report / Deliverable Type |  |  |  | Frequency |  | Target |  | Submitted |  | On Time? | Status | Remarks
Daily Work Log (Pulse360 / Logsheet entry) |  |  |  | Daily
Weekly Task Plan |  |  |  | Weekly
Pending CR Status Report |  |  |  | Weekly
Live Implementation Project Status |  |  |  | Weekly
Project / Implementation Schedule Update |  |  |  | Weekly
Monthly Work Summary (this document) |  |  |  | Monthly
SECTION · SKILL ENHANCEMENT & PROFESSIONAL DEVELOPMENT
S.No | Learning Area |  |  | Course / Activity |  |  | Platform / Source |  | Hours Invested | Status | How Applied to Work?
1
2
3
4
5
SECTION · MONTHLY SELF-REFLECTION & PERFORMANCE APPRAISAL
Top 3 Key Accomplishments this Month
Challenges Faced & How Resolved
What I Should Have Done Better / Gaps
Support or Resources Needed from Management
My Goals for Next Month (specific & measurable)
Employee Signature & Date
CEO Review & Acknowledgement (date)