## 1 - Module Tracker
Blueprint ID | Dev ID | Module / Sub-Module | FSD Owner | Dev Owner | Phase | Target | FSD Status | FSD Approved | SPs Req. | SPs Built | SPs % | Domain | DTO | Interface | Service | Repo | Controller | Types | API | Store | List | New | Edit | IST Status | IST Pass% | Deployed? | Open Bugs | Blockers / Notes | Status
M01 | Dev-M01 | PR Form (Purchase Requisition) | Mariyaiya M | Abinandan N | Phase 1 | Jun 2026 | CEO Approved | Apr 2026 | 17 | 17 | 100% | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | In Progress | ~90% | N | 5 | Issue #40 pending qty flag (Sasi); Issue #26 Sub-Cost Centre level (Sasi); IIS deploy pending; CEO demo 06 May | Amber
M01 | Dev-M02 | RMI Purchase Order (PO Form) | Sasi (Sasikumar R) | Abinandan N | Phase 1 | Jul 2026 | CEO Approved | Apr 2026 | 19 | 19 | 100% | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Not Started | - | N | 3 | VW_rm_SupplierVariety columns unverified; dropdown UX fix pending; merged_jat.sql deploy pending | Amber
M01 | Dev-M02b | Stores Arrival / GRN | Sasi (Sasikumar R) | Abinandan N | Phase 1 | Jul 2026 | CEO Approved | Apr 2026 | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | Build not started — awaiting M02 PO IST clearance | Red
M03 | Dev-M03 | Domestic Yarn Sales | Annamalai S | Abinandan N | Phase 1 | Aug 2026 | CEO Approved | May 2026 | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | FSD CEO-approved; build starts after M01 + M02 PO deploy | Red
M04 | Dev-M04a | Attendance Download | Sathishkumar M | Abinandan N | Phase 1 | Sep 2026 | CEO Approved | May 2026 | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | FSD approved; build scheduled Jun–Sep 2026 | Red
M04 | Dev-M04b | Attendance Entry | Sathishkumar M | Abinandan N | Phase 1 | Sep 2026 | CEO Approved | May 2026 | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | FSD approved; build scheduled Jun–Sep 2026 | Red
M02 | - | Stores Purchase & Inventory | Mariyaiya M | Abinandan N | Phase 1 | Sep 2026 | In Progress | - | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | FSD Stage 0 in progress; build after CEO approval | Red
M04 | - | HR & Payroll (Leave / Payroll) | Sathishkumar M | Abinandan N | Phase 1 | Sep 2026 | In Progress | - | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | Attendance FSD approved; Payroll/Leave FSD in progress | Red
M05 | - | Accounting & Finance | Sasi / TL-Dev | Abinandan N + New Dev | Phase 1 | Sep 2026 | Not Started | - | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | Scheduled Jul–Sep 2026; React Dev hire critical | Red
M06 | - | e-Invoicing (GST IRN) | Sr Web Dev | Sr Web Dev (Jun+) | Phase 1 | Sep 2026 | Not Started | - | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | Sr Web Dev returns Jun 2026; FSD not started | Red
M07 | - | Export Yarn Sales | Sr VB Dev2 | Sr Web Dev (Jun+) | Phase 2 | Nov 2026 | Not Started | - | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | Phase 2 — out of current sprint scope | Red
M08 | - | Waste & Scrap Sales | Sr VB Dev2 | Sr Web Dev (Jun+) | Phase 2 | Nov 2026 | Not Started | - | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | Phase 2 — out of current sprint scope | Red
M09 | - | Spinning Production Systems | TL-Dev + New Dev | Abinandan N + New Dev | Phase 2 | Dec 2026 | Not Started | - | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | Core differentiator; Phase 2; requires New Dev hire | Red
M10 | - | Quality Control | SME | New Dev + SME | Phase 2 | Dec 2026 | Not Started | - | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | Phase 2 | Red
M11 | - | Power Accounting | Sr IST1 | New Dev | Phase 2 | Dec 2026 | Not Started | - | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | Phase 2 | Red
M12 | - | Machinery & Electrical Maintenance | TL-IST | New Dev | Phase 2 | Dec 2026 | Not Started | - | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | Phase 2 | Red
M13 | - | MIS & Dashboards | All IST + SME | Sr Web Dev + Jr WDs | Continuous | Ongoing | Not Started | - | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | Continuous; depends on all modules being live | Red
M14 | - | SPINNOVA AI Framework | Jr WDs + SME | Jr WDs + SME | Parallel | Ongoing | Not Started | - | TBD | 0 | N/A | N | N | N | N | N | N | N | N | N | N | N | N | Not Started | - | N | - | Parallel track; live operational data → AI KPI dashboards | Red

## 2 - Feature Gap Analysis
Module | Sub-Module | Feature / Capability | Required? | Built? | IST Tested? | Gap Description | Priority | Owner | ETA
M01 — PR Form | Create | New PR Form — all header fields (date/dept/section/iType/requester/ref/PO group/scope/sale order) | Y | Y | Y | Complete | High | Abinandan N | Done
M01 — PR Form | Create | Line items table — inline add / edit / delete rows | Y | Y | Y | Complete | High | Abinandan N | Done
M01 — PR Form | Create | Item lookup — code + name autocomplete | Y | Y | Y | Complete | High | Abinandan N | Done
M01 — PR Form | Create | UOM auto-fill on item selection | Y | Y | Y | Complete | Med | Abinandan N | Done
M01 — PR Form | Create | Required Date per line item | Y | Y | Y | Complete | Med | Abinandan N | Done
M01 — PR Form | Create | Machine No. field on line item | Y | Y | Y | Complete | Med | Abinandan N | Done
M01 — PR Form | Create | MINLEVEL warning on qty entry (non-blocking, auto-dismiss 5s) | Y | Y | N | Built post-IST — not yet re-tested by IST team | High | Abinandan N | 06 May demo
M01 — PR Form | Create | Budget validation flag — balance display (config-driven) | Y | Y | Partial | Flag wired; balance display needs CEO demo verification | High | Abinandan N | 06 May demo
M01 — PR Form | Create | Pending PO details flag (config-driven) | Y | Y | N | Flag implemented; IST not re-tested post-fix | High | Abinandan N | 06 May demo
M01 — PR Form | Create | Ref No mandatory when config enabled | Y | Y | Y | Complete | Med | Abinandan N | Done
M01 — PR Form | Create | Back-date allowed flag (config-driven) | Y | Y | Y | Complete | Med | Abinandan N | Done
M01 — PR Form | Edit / View | PR Edit page — load and save existing PR lines | Y | Y | Y | Complete | High | Abinandan N | Done
M01 — PR Form | Edit / View | PR View modal — read-only summary | Y | Y | Y | Complete | High | Abinandan N | Done
M01 — PR Form | Edit / View | Lock editing for approved / converted PRs | Y | Y | Y | Complete | High | Abinandan N | Done
M01 — PR Form | Edit / View | Approval info display (L1/L2/Final approver + date) | Y | Y | Y | Complete | Med | Abinandan N | Done
M01 — PR Form | Edit / View | Sub-Cost Centre field on line item | Y | N | N | BLOCKED — awaiting Sasi design decision: header vs line level (Issue #26) | High | Sasi (design) | Blocked
M01 — PR Form | Edit / View | Pending qty display flag on line item | Y | N | N | BLOCKED — awaiting Sasi FSD confirmation (Issue #40) | High | Sasi (design) | Blocked
M01 — PR Form | List | PR List — paginated table with full-width card | Y | Y | Y | Complete | High | Abinandan N | Done
M01 — PR Form | List | Filter bar: PR No / Date range / Dept / Status / Search / Reset | Y | Y | Y | Complete | High | Abinandan N | Done
M01 — PR Form | List | Status badges (colour per status code) | Y | Y | Y | Complete | Med | Abinandan N | Done
M01 — PR Form | List | Row actions: Edit / View / Delete | Y | Y | Y | Complete | High | Abinandan N | Done
M01 — PR Form | List | Status summary bar (count per status) | Y | Y | Y | Complete | Med | Abinandan N | Done
M01 — PR Form | List | Checkbox multi-select (currently inactive) | Y | Partial | N | Checkboxes visible but do nothing — activate with toolbar OR remove (CEO priority) | High | Abinandan N | 05 May
M01 — PR Form | List | Bell icon badge — pending PR count | Y | Partial | N | Bell exists but shows no count badge — add this week | High | Abinandan N | 05 May
M01 — PR Form | Cancel / Delete | Cancel PR with reason (soft delete) | Y | Y | Y | Complete | High | Abinandan N | Done
M01 — PR Form | Cancel / Delete | Line-level delete with reason | Y | Y | Y | Complete | High | Abinandan N | Done
M01 — PR Form | Workflow | Status flow: OPEN→L1→L2→FINAL→RECEIVED→CONVERTED | Y | Y | Y | Complete | High | Abinandan N | Done
M01 — PR Form | Workflow | Approve / Reject / Cancel transition endpoints | Y | Y | Y | Complete | High | Abinandan N | Done
M01 — PR Form | Workflow | Workflow progress bar in UI | Y | Y | Y | Complete — Vignesh flagged but CEO confirmed it exists | High | Abinandan N | Done
M01 — PR Form | Print | QuestPDF PDF — PR requisition print | Y | Y | Partial | PDF generates; minor formatting issues from IST — review post-demo | High | Abinandan N | Post-demo
M01 — PR Form | Print | Print customisation panel (section toggles / dept presets) | N | N | N | Phase 2 deferred — current QuestPDF meets FSD v2.3 | Low | Abinandan N | Phase 2
M01 — PR Form | Export | EPPlus Excel export — PR list | Y | Y | Y | Complete | Med | Abinandan N | Done
M01 — PR Form | Sprint 2 | Copy PR — 3-option modal (CEO ACCEPTED) | Y | N | N | Sprint 2 confirmed — same items/diff dept; same dept/diff items; full copy | High | Abinandan N | Sprint 2
M01 — PR Form | Sprint 2 | Bulk action toolbar (Approve / Cancel / Download) | Y | N | N | Sprint 2 confirmed — Convert to PO = Phase 2 (needs M02) | Med | Abinandan N | Sprint 2
M01 — PR Form | Sprint 2 | Compact filter bar for PR list | N | N | N | Sprint 2 quick win — CEO confirmed | Low | Abinandan N | Sprint 2
M01 — PR Form | Phase 1 Partial | Related PO link in PR view modal | N | N | N | Build when M02 PO deployed; full chain nav = Phase 2 | Med | Abinandan N | After M02 deploy
M02 — PO Form | Create | New PO — header: supplier / area / variety / payment mode / currency / GST | Y | Y | N | Built; not yet IST tested | High | Abinandan N | Post-deploy
M02 — PO Form | Create | PO line items — Pick from pending PR lines modal | Y | Y | N | Built — PRLinePickerModal implemented | High | Abinandan N | Post-deploy
M02 — PO Form | Create | PO delivery schedule (inline editable table) | Y | Y | N | Built | High | Abinandan N | Post-deploy
M02 — PO Form | Create | Discount rate table | Y | Y | N | Built | Med | Abinandan N | Post-deploy
M02 — PO Form | Create | GST auto-defaults (IGST 5% interstate / CGST+SGST 2.5% intrastate) | Y | Y | N | Built | Med | Abinandan N | Post-deploy
M02 — PO Form | Create | Candy rate auto-calc (candyRate→rateKg; ordQty→ordKgs) | Y | Y | N | Built | Med | Abinandan N | Post-deploy
M02 — PO Form | Create | Lookup dropdowns — code+name in single field (not two fields) | Y | Partial | N | PENDING — UX fix: combine code+name in single Select option label | High | Abinandan N | 06 May
M02 — PO Form | Create | CONTNO race condition prevention (CD-2 UPDLOCK+HOLDLOCK) | Y | Y | N | SP has UPDLOCK applied; concurrent load test needed before IST | High | Abinandan N | Pre-IST
M02 — PO Form | Edit / Approve | PO Edit/View — read-only header + lines + delivery | Y | Y | N | Built | High | Abinandan N | Post-deploy
M02 — PO Form | Edit / Approve | L1 / L2 / Final Approve + Reject with remarks modal | Y | Y | N | Built | High | Abinandan N | Post-deploy
M02 — PO Form | List | PO List — filter, pagination, status badges | Y | Y | N | Built | High | Abinandan N | Post-deploy
M02 — PO Form | Deploy | Deploy merged_jat.sql to JAT DB (172.16.16.52 → JAT) | Y | N | N | User action: run merged_jat.sql in SSMS on JAT DB | High | Abinandan N | This week
M02 — PO Form | Deploy | Verify VW_rm_SupplierVariety columns match SP expectations | Y | N | N | Risk: runtime SP failure if columns mismatch | High | Abinandan N | This week
M02 — PO Form | Print | QuestPDF PDF — PO print (RPT_RMI_PO) | Y | N | N | Not built — Phase 7 in plan | High | Abinandan N | May 2026
M02 — PO Form | Export | EPPlus Excel export — PO list | Y | N | N | Not built | Med | Abinandan N | May 2026

## 3 - Sprint Plan
Day | Date | Task | Module | Type | Hrs | Status | Notes
Day 1 | 05 May Mon | Submit React Developer JD to CEO (jointly with Sasi) | Admin | Admin | 1 | TODO | HARD DEADLINE EOD today
Day 1 | 05 May Mon | Submit Revised FSD Completion Schedule to CEO | Admin | Docs | 1 | TODO | HARD DEADLINE EOD today
Day 1 | 05 May Mon | Fix inactive PR list checkboxes (activate with toolbar OR remove) | Dev-M01 | Frontend | 2 | TODO | CEO priority — inactive UX is unacceptable
Day 1 | 05 May Mon | Add pending-count badge to bell icon in header | Dev-M01 | Frontend | 1.5 | TODO | CEO priority from sprint backlog
Day 1 | 05 May Mon | PR Form full UX final polish + demo rehearsal walkthrough | Dev-M01 | Frontend | 2.5 | TODO | CEO demo 06 May — must be 100% clean
Day 2 | 06 May Tue | CEO Demo — PR Form full UX walkthrough (HARD GATE) | Dev-M01 | Demo | 2 | TODO | All IST-fixed features; MINLEVEL warning; budget flag; print
Day 2 | 06 May Tue | Post-demo: capture CEO feedback as action items | Dev-M01 | Admin | 0.5 | TODO | Document and save to memory immediately
Day 2 | 06 May Tue | M02 PO — Fix lookup dropdown UX (code+name in single field, all 5 lookups) | Dev-M02 | Frontend | 3 | TODO | Change options to: { value: code, label: code + ' - ' + name }
Day 2 | 06 May Tue | M02 PO — Verify VW_rm_SupplierVariety columns in SSMS vs SP expectations | Dev-M02 | Backend | 1.5 | TODO | Risk: runtime SP failure; check JAT DB view definition
Day 3 | 07 May Wed | M01 — IST bug fixes batch (CEO demo feedback first) | Dev-M01 | Bug | 4 | TODO | Update merged.sql for every SP change
Day 3 | 07 May Wed | M02 PO — Deploy merged_jat.sql to JAT DB via SSMS | Dev-M02 | Deploy | 1 | TODO | Stop pool, run merged_jat.sql on JAT DB, verify SPs exist
Day 3 | 07 May Wed | M02 PO — Smoke test all 19 SP endpoints via Swagger on JAT DB | Dev-M02 | Backend | 2 | TODO | Test create / list / approve / cancel paths
Day 3 | 07 May Wed | FSD-to-ASP.NET Core conversion steps document (draft) | Admin | Docs | 1.5 | TODO | Submit to CEO this week
Day 4 | 08 May Thu | M01 — IST bug fixes continued + merged.sql update | Dev-M01 | Bug | 3.5 | TODO | Target: zero High-severity open bugs before deploy
Day 4 | 08 May Thu | M02 PO — QuestPDF print template start (RPT_RMI_PO) | Dev-M02 | Backend | 3 | TODO | Follow M01 QuestPDF architecture exactly
Day 4 | 08 May Thu | Submit FSD-to-ASP.NET Core conversion doc to CEO | Admin | Docs | 0.5 | TODO | Due this week
Day 5 | 09 May Sat | Saturday Review Meeting (PM Saravanan conducting) | All | Meeting | 2.5 | TODO | Prepare progress update; demo M02 PO if ready
Day 5 | 09 May Sat | Submit baseline code (version snapshot) for all modules to CEO | Admin | Admin | 1 | TODO | Package Dev-M01 + Dev-M02 git snapshot
Day 5 | 09 May Sat | Post-meeting: update sprint backlog and gap analysis from CEO feedback | Admin | Admin | 0.5 | TODO | Update this Excel file with actuals
Day 6 | 12 May Mon | M01 — Reconcile merged.sql with all post-IST SP changes | Dev-M01 | Deploy | 1.5 | TODO | SP merge rule: every change must be in merged.sql before deploy
Day 6 | 12 May Mon | M01 — Backend publish: stop pool, dotnet publish, copy to IIS 5001 | Dev-M01 | Deploy | 1.5 | TODO | IIS path: 172.16.16.40:5001
Day 6 | 12 May Mon | M01 — Frontend build: npm run build, copy dist/ to IIS port 3000 | Dev-M01 | Deploy | 1 | TODO | Uses .env.production; verify VITE_BACKEND_ORIGIN
Day 6 | 12 May Mon | M02 PO — Complete QuestPDF print template + test PDF output | Dev-M02 | Backend | 3.5 | TODO
Day 7 | 13 May Tue | M01 — Run merged.sql in SSMS on SpinRiseSaranya DB | Dev-M01 | Deploy | 0.5 | TODO | DB first always before backend
Day 7 | 13 May Tue | M01 — Post-deploy smoke test on 172.16.16.40:3000 | Dev-M01 | Deploy | 2 | TODO | Test: Login, PR List, Create PR, Edit PR, PDF print, Excel export
Day 7 | 13 May Tue | M02 PO — EPPlus Excel export for PO list | Dev-M02 | Backend | 2 | TODO | Follow M01 EPPlus pattern
Day 7 | 13 May Tue | M02 PO — End-to-end test: Create PO, Pick PR lines, Approve, Print | Dev-M02 | Frontend | 2 | TODO
Day 8 | 14 May Wed | M01 — Fix any post-deploy issues (keep merged.sql updated) | Dev-M01 | Bug | 2 | TODO
Day 8 | 14 May Wed | M02 PO — IIS deploy: merged_jat.sql to JAT DB, backend, frontend | Dev-M02 | Deploy | 2.5 | TODO | JAT DB specific — use merged_jat.sql NOT merged.sql
Day 8 | 14 May Wed | M02b Stores Arrival — read FSD, draft SP list | Dev-M02b | Backend | 2 | TODO | Start planning next module after M02 PO is deployed
Day 9 | 15 May Thu | M02 PO — Post-deploy smoke test + concurrent load test (CD-2 race) | Dev-M02 | Deploy | 2 | TODO | 2x simultaneous Create-PO to verify CONTNO uniqueness
Day 9 | 15 May Thu | M02b Stores Arrival — begin SP development (ksp_Arrival_GetPendingPOs) | Dev-M02b | Backend | 4 | TODO
Day 10 | 16 May Fri | M02b Stores Arrival — SP-02: ksp_Arrival_Create + ksp_Arrival_GetById | Dev-M02b | Backend | 4 | TODO
Day 10 | 16 May Fri | Weekly retro + update Gap Analysis Excel with actual completion | Admin | Admin | 1 | TODO | Fill in actual hrs + status for each task
Day 10 | 16 May Fri | Git commit and push all changes to master | All | Admin | 0.5 | TODO | Co-authored-by: Claude Sonnet 4.6
TOTAL — 35 tasks over 10 working days (05–16 May 2026) |  |  |  |  | 66.5

## 4 - Scorecard
SPINRISE — Developer Requirements Scorecard (04 May 2026)
Metric | Value | Notes | FSD Status | Count | Module | Completion %
Total modules in scope — Phase 1 | 10 | M01-PR, M01-PO, M01-Arrival, M02-Stores, M03-Sales, M04-Attend x2, M04-Payroll, M05-Acctg, M06-eInv | CEO Approved | 6 | M01 PR Form | 100%
FSDs CEO-approved | 6 | PR Form, PO, Stores Arrival, Sale Order, Attendance Download, Attendance Entry | In Progress | 2 | M02 PO Form | 95%
FSDs in progress | 2 | Stores Purchase (Mariyaiya, Stage 0), HR Full Payroll (Sathish) | Not Started | 2 | M02 Arrival | 5%
FSDs not started | 2 | Accounting & Finance (M05), e-Invoicing (M06) |  |  | M03 Sales | 5%
Modules with build started | 2 | Dev-M01 PR Form, Dev-M02 PO |  |  | M04 Attend. | 5%
Modules build complete (all layers) | 2 | Dev-M01 + Dev-M02; pending IST + IIS deploy |  |  | Phase 1 Avg | 18%
Modules IST completed and passing | 0 | Dev-M01 IST ~90% est post-fix; Dev-M02 IST not started
Modules deployed to IIS | 0 | M01 + M02 deploy pending — target this week
Total features identified (M01+M02) | 50 | Based on FSD feature checklist — see Sheet 2
Features built | 38 | Backend + frontend implemented
Features IST-tested (cleared) | 25 | M01 first-pass; post-fix batch not re-tested yet
Features with open bugs | 8 | M01: 5 minor + 2 blocked; M02: 1 deploy-risk
Features blocked (design pending) | 2 | Issue #26 Sub-Cost Centre; Issue #40 Pending Qty
M01 PR Form — build completion | 100% | All 17 SPs + all backend layers + all frontend pages
M01 PR Form — IST pass rate | ~90% | First pass 44%; post-fix sprint est. 90%+
M01 PR Form — deploy status | 0% | Pending — target 13 May 2026
M02 PO Form — build completion | 95% | Dropdown UX fix pending; all other layers done
M02 PO Form — IST pass rate | 0% | IST not started — starts after deploy
Phase 1 overall completion % | 18% | 2 of 10 modules built; 0 deployed; 8 not started
Phase 1 go-live target | 30 Sep 2026 | 6 core modules live — covers 80%+ of daily mill ops
New customer onboarding from | Oct 2026 | Write to all 50+ customers; invite top-10 for live demo
CEO demo (PR Form UX) | 06 May 2026 | HARD GATE — tomorrow
Next weekly review | 09 May 2026 | PM Saravanan conducting

## 5 - Blocker Log
ID | Module | Feature | Blocker Description | Waiting On | Raised | Impact | Resolution Path | Status
BLK-01 | Dev-M01 | Issue #40 — Pending Qty Display | Config flag exists in preCheckResult but UI column not wired. Pending design decision on whether to show pending qty as a separate column in the line items table. | Sasi (TL-Dev) — design decision | 29 Apr 2026 | High | Sasi to confirm: separate column Y/N. Once confirmed Abinandan wires in approx 1 hour. | Open
BLK-02 | Dev-M01 | Issue #26 — Sub-Cost Centre level | FSD unclear: Sub-Cost Centre at header level (one per PR) or line level (per item). Currently at line level. If header-level, significant refactor needed to move field to PRHeaderCards. | Sasi (TL-Dev) — design decision | 25 Apr 2026 | High | Sasi to confirm: header or line. If header: move to PRHeaderCards + remove from table. If line: no change. | Open
BLK-03 | Admin | React Developer Recruitment | Abinandan is sole Fullstack Dev (ASP.NET Core + React). Phase 1 has 10 modules. Parallel React work is blocked without a second developer. Phase 1 timeline at risk. | CEO — JD approval and posting | 03 May 2026 (MOM) | High | Abinandan + Sasi submit JD to CEO by Mon 05 May. CEO posts on recruitment channels. | Action Due 05 May
BLK-04 | Dev-M01 | IIS Production Deploy | Build complete; IST ~90%+ post-fix. But merged.sql + backend + frontend not pushed to IIS (172.16.16.40). IST re-test must happen on production URL. | Abinandan N — execution | 01 May 2026 | High | 1. Stop IIS pool. 2. Run merged.sql on SpinRiseSaranya. 3. dotnet publish. 4. npm run build, copy dist/ to IIS:3000. 5. Start pool. 6. Smoke test. | Pending — 12-13 May
BLK-05 | Dev-M02 | CD-2 Race Condition — CONTNO | CONTNO generation SP uses UPDLOCK+HOLDLOCK but not tested under concurrent load. Two simultaneous Create-PO requests could generate duplicate CONTNO. | Concurrent load test | 25 Apr 2026 | High | Open 2 Swagger tabs simultaneously, execute Create-PO on both, verify CONTNO values are unique. Must pass before IST begins. | Pending — before IST
BLK-06 | Dev-M02 | VW_rm_SupplierVariety Column Mismatch | GetPendingPRLines and FilterPRLines SPs SELECT from VW_rm_SupplierVariety. Column names assumed but not verified against live JAT DB. Mismatch = SP runtime failure. | Abinandan N — SSMS verification | 29 Apr 2026 | High | SSMS: JAT DB, Views, VW_rm_SupplierVariety, Script View. Compare column list with SP SELECT list. Fix any that differ. | Pending — 07 May
BLK-07 | Dev-M02 | Lookup Dropdown UX | All 5 lookup fields show code in one Select + name in separate read-only field. FSD requires single combined field showing CODE - Name. | Abinandan N — frontend fix | 29 Apr 2026 | Med | Change Select options to { value: code, label: code + ' - ' + name }. Remove 5 separate name display fields. | Pending — 06 May
BLK-08 | Dev-M02b | Stores Arrival Build Not Started | FSD CEO-approved but build has not started. Arrival depends on a PO existing in JAT DB, so M02 PO must be deployed first. | M02 PO IST clearance and deploy | 04 May 2026 | Med | Start Arrival SP planning from FSD after M02 PO is deployed. Target build start: 14 May 2026. | Planned — 14 May
BLK-09 | Dev-M03 | Sale Order Build — Capacity | FSD CEO-approved but Abinandan cannot start M03 build until M01 + M02 are IST-cleared and deployed. Single Fullstack Dev is the bottleneck for all modules. | M01 + M02 deploy and IST clearance | 04 May 2026 | Med | M03 build planned Jun 2026. New React Dev hire will allow parallel frontend work. | Planned — Jun 2026