SPINRISE Kalpatharu Software Ltd — ERP Platform Migration Blueprint ────────────────────────────── From Spindle to Cloud — The Next Revolution Version 4.0 · April 2026 · FY 2026–27 Internal Circulation · Team & Management Kalpatharu Software Ltd · Coimbatore, Tamil Nadu, India

| Document | Version | Date | Status |
| --- | --- | --- | --- |
| SPINRISE Migration Blueprint | 4.0 — Internal | 28 March 2026 | Internal Circulation |
| Prepared by | Audience | Classification | Distribution |
| CEO | Full SPINRISE Team | Internal Confidential | Team Only — Do Not Forward |

## Table of Contents

1.  About Kalpatharu Software Ltd & Project SPINRISE

2.  Why We Are Migrating Now

3.  Current System Architecture

4.  Target Technology Platform

5.  Team Structure & Role Assignments

6.  Module Ownership Matrix

7.  12-Month Delivery Roadmap  —  FY 2026–27

8.  AI-Assisted Development Workflow

9.  Risk Register & Mitigation Plan

10.  Saturday Cadence — How We Deliver Together

11.  Immediate Action Plan  —  This Week

1. About Kalpatharu Software Ltd & Project SPINRISE

## 1.1  Who We Are

Kalpatharu Software Ltd, headquartered in Coimbatore, Tamil Nadu, is a specialist ERP software product company serving the spinning and textile industry. The Kalsofte ERP was architected and released in 2004 and has been market-tested for 22 years. The product addresses 100% of the end-to-end operational, managerial, and statutory requirements of a spinning mill — from raw cotton to dispatch, from wage computation to financial reporting.

| Metric | Detail | What It Means for SPINRISE |
| --- | --- | --- |
| ERP Product Released | 2004 (Kalsofte ERP v1) | 22 years of live market validation. Every workflow and rule in the system has been tested by real mills. |
| Active Customers | 50+ spinning mills, pan-India | Includes Paper mills, Weaving, Home Textiles verticals |
| AMC Retention | 95% Year-on-Year | Customers stay because the product works. Our task is to make it available on the web — same product, new platform. |
| Revenue Split | Spinning 70–75% · Others 25–30% | Paper mills, Weaving, Home Textiles will be the next vertical targets post-SPINRISE. |
| International Track | Indonesia, Philippines — IndoERP (2010–2017) | Demonstrated that the product adapts to different markets. SaaS will reopen this opportunity. |
| Current Web Layer | ASP.NET reports, MIS dashboards, approvals, auto-mails already live | We already have a proven web foundation. SPINRISE completes the journey. |

## 1.2  What Project SPINRISE Is

SPINRISE is the internal project name for the migration of the Kalsofte ERP from its current VB6 Windows client to a fully modern, browser-native web platform. It is not a rebuild. It is not a redesign. It is a faithful re-expression of 22 years of proven domain logic on the technology surface that today’s market expects.

|  | “What customers need is 1 litre of milk. They don’t care whether it came from a brown cow, white cow, or black cow. That is our problem — and we solve it completely.” — CEO, Kalpatharu |
| --- | --- |

The product is proven. The domain is documented. The team carries the knowledge. SPINRISE’s job is to give this proven product a browser-native interface — so that every customer and every prospect experiences the same depth of functionality from any device, any browser, anywhere.

## 1.3  SPINNOVA — Our AI Product Layer

Running in parallel with SPINRISE is SPINNOVA — our in-house AI-based KPI framework currently under active development by the junior web developer team, guided by the SME as the primary use-case owner. SPINNOVA is already receiving positive market reception. When integrated with SPINRISE live operational data, it will deliver real-time mill intelligence to management — something no competitor currently offers.

SPINRISE + SPINNOVA together = An AI-native, domain-deep Spinning ERP. Our goal is to complete both in FY 2026–27 — SPINRISE as the platform, SPINNOVA as the intelligence layer.

## 1.4  Leadership Team

| Role | Summary |
| --- | --- |
| CEO & Product Owner | Founder of Kalpatharu Software Ltd. Architect of the Kalsofte ERP. 45+ years in IT, over 40 in spinning and textile ERP. Drives the AI-first strategy and shares learnings with the full team every Saturday. |
| PM | 20+ years within Kalpatharu — from support engineer to PM. Deep technical empathy and customer-side knowledge. Accountable for the 12-month delivery commitment. |
| SME | Masters in Textile Technology. 3 years textile industry experience + 2 years as Kalpatharu’s full-time Subject Matter Expert. IST and QA authority for Spinning, Weaving, and Home Textiles modules. Primary SPINNOVA use-case owner. |

2. Why We Are Migrating Now

## 2.1  Two Forces Driving Migration

| Force | What Is Happening | SPINRISE Response |
| --- | --- | --- |
| Customer Push | Younger management at existing customer sites increasingly prefer browser-based access. This is creating a manpower retention challenge for customers on the Windows platform. | SPINRISE delivers a full web interface without disrupting the existing system. Customers upgrade at their pace. |
| Competitive Pull | New ERP prospects now evaluate platform modernity before domain depth. A web-first interface is a qualifying criterion in competitive evaluations — even when our product is functionally superior. | From October 2026, all new prospects are onboarded directly on SPINRISE. |

We continue to close new orders on the legacy ERP because customers choose us for domain depth, integration, and reliability — not the technology stack. SPINRISE does not fix a broken product. It extends a proven product onto the platform the market now expects.

## 2.2  Why AI Tools Make the 12-Month Timeline Achievable

An earlier web migration attempt (2022–2023) with a senior consultant and 2 dedicated web developers demonstrated how slow and costly traditional migration is for a product of this complexity. The availability of AI development tools has fundamentally changed this:

- Claude Code (Anthropic) generates React and C# code from plain English descriptions or directly from VB6 code — 60–70% of UI and API code is auto-generated

- GitHub Copilot provides real-time code completion inside Visual Studio and VS Code

- ChatGPT (paid) is used for VB6 bug analysis, SQL query optimisation, and technical problem-solving

- The entire team already uses these tools in production — Supplier Portal, Centralised Sales Management System for a 5-mill textile group, SPINNOVA development

The AI advantage is already proven within our team. What previously required 2 dedicated web developers + a senior consultant over 2 years can now be delivered by our existing team in 12 months — because AI handles 60–70% of code generation, leaving our developers free to apply their domain knowledge to review and validate.

3. Current System Architecture

## 3.1  Where We Are Today — April 2026

| Layer | Current Technology | Status | SPINRISE Action |
| --- | --- | --- | --- |
| Front-End Client | Visual Basic 6.0 Windows Forms. Runs under Windows 11 for all recent deployments. | Functional and stable. Continues to run alongside SPINRISE during transition. | Replace with React.js 18 + Ant Design Pro. Module by module. |
| Database | SQL Server 2012 (most sites) → SQL Server 2019 for recent deployments. SQL Server 2008 R2 fully phased out. | SQL 2019 fully supported. Zero data migration required. Both systems share the same database during transition. | Retain as-is. No changes to existing schema or stored procedures. |
| Web Reports | ASP.NET — all module reports already browser-accessible | Live and in active daily use by management. | Migrate to FastReport .NET / RDLC. Sr Web Dev leads from June 2026. |
| MIS & Dashboards | ASP.NET web platform. Maintained by Sr Web Dev + Jr Web Dev team. | Operational. Continuously maintained and enhanced. | Continuously enhance as new modules come online. |
| Workflow & Approvals | Web-based ASP.NET transaction approval & auto-mail system. | Fully operational. Proven with all customers. | Port to ASP.NET Core 8. Logic fully reused. |
| SPINNOVA | AI-based KPI framework. Active development by Jr Web Dev team + SME as use-case owner. | In active development. Positive market reception. | Parallel development track. Integration with live SPINRISE data in Phase 3. |

## 3.2  Our Parallel-Running Migration Strategy

SPINRISE uses a parallel-running strategy throughout the entire transition. This means:

- The existing VB6 system continues running without any interruption for all live customers

- Both the VB6 system and SPINRISE web system connect to the same SQL Server database — same data, same truth, zero duplication

- There is no forced cutover for any customer — each customer migrates when they are ready and tested

- New customers from October 2026 onwards are onboarded directly on SPINRISE

- Data risk is zero: if SPINRISE has an issue, the VB6 system is unaffected and continues

Architecture safeguard for VB6 clients during parallel run: SPINRISE accesses the database exclusively through existing stored procedures via Dapper ORM. No changes are made to existing table schemas. New tables use a separate namespace. The VB6 application is architecturally unaffected throughout the entire migration.

4. Target Technology Platform

Architecture principle: Maximise reuse of existing SQL Server assets. Leverage the team’s existing ASP.NET knowledge. Use AI tools to close the gap between current skills and the target stack at 3–5x the speed of traditional learning.

## 4.1  Full Technology Stack

| Layer | Technology | Why We Chose This | Migration Complexity |
| --- | --- | --- | --- |
| Front-End UI | React.js 18 + Ant Design Pro | Enterprise-grade component library with rich data grids, forms, dashboards, and charts out of the box. Largest AI code-generation dataset — best Claude Code support for our team. | New development. 60–70% AI-generated. Jr Web Dev team leads with Sr VB Dev review. |
| Back-End API | ASP.NET Core 8 Web API (C#) | Our team already has ASP.NET knowledge from the existing web layer. Microsoft-strategic, best enterprise performance, direct path from VB6 business logic via C#. | Port from VB6 logic. Claude Code accelerated. Sr VB Devs own this layer. |
| Database | MS SQL Server 2019 / 2022 | All stored procedures, business rules, and 22 years of customer data are intact. Zero data migration. Zero risk. | Retain entirely. No effort. No changes. |
| Data Access | Dapper Micro-ORM | Wraps existing SQL stored procedures without any rewrite. Every SQL optimisation we have done over 22 years is preserved and reused. | Low. Wrap existing SQL calls in C# method. Well-supported by Claude Code. |
| Reports | FastReport .NET Web / RDLC | Browser-native replacement for Crystal Reports. Supports PDF, Excel, HTML export. Familiar paradigm for the reports team. | Redesign in new engine. Sr Web Dev leads from June. Jr Devs support. |
| Authentication | ASP.NET Identity + JWT Bearer Tokens | Stateless, secure, mobile-ready. Role-based access control mirrors existing user permissions. Single sign-on ready. | One-time setup. AI-assisted scaffolding. TL-Dev owns. |
| State Management | React Context API + Zustand | Lightweight alternatives to Redux. Appropriate for ERP module complexity. Lower learning curve for our Jr Web Dev team. | Jr Web Dev team. AI-assisted patterns. |
| Deployment | IIS on-premise (existing customers) + Azure App Service (new SaaS) | Existing customers continue on-premise — no change to their infrastructure. New customers get cloud-hosted SaaS. Both use the same application build. | Configuration only. No development effort. |
| AI Dev Tools | Claude Code + GitHub Copilot + ChatGPT | All three are already active and paid. Claude Code is the primary code generation tool. 3–5x productivity multiplier over manual development. | Already active. No setup lag. |
| Dev Repository | Azure DevOps / GitHub (Git) | Version control, branch management, pull request review. Full audit trail of every code change. | Setup in Week 1 of Phase 0. |
| Project Tracking | PULSE 360 (in-house) | Daily logsheets, effort tracking, phase progress. Project IDs: SPINRISE Dev and SPINRISE IST. | Active. All team members logging from Day 1. |

## 4.2  Development Environment Setup — Every Developer’s Machine

| Tool | Purpose | Who |
| --- | --- | --- |
| Visual Studio 2022 | ASP.NET Core 8 Web API development. C# coding, debugging, SQL connection. | TL-Dev + all Sr VB Devs |
| VS Code + Node.js 20 LTS | React.js development. Component building, testing, hot reload. | Jr Web Dev team + all |
| React Vite Scaffold | Project bootstrap for React front-end. Fast build tool. | Jr Web Dev team |
| Claude Code (Anthropic) | Primary AI pair-programmer. Code generation, VB6 conversion, test case writing. | All developers |
| GitHub Copilot | In-editor AI code completion inside Visual Studio and VS Code. | All developers |
| SQL Server Management Studio (SSMS) | Database query testing, stored procedure review, schema browsing. | All developers |
| Postman | API endpoint testing during development and UAT. | All developers + IST team |
| Azure DevOps / GitHub | Source control, sprint boards, CI/CD pipelines. | TL-Dev sets up. All commit. |

5. Team Structure & Role Assignments

## 5.1  Team Overview — April 2026

| 4 VB Dev Team | 3 Web Dev Team | 4 IST + SME | 7* Active Now | 9+ From Jun 2026 |
| --- | --- | --- | --- | --- |

* 7 active now. Sr Web Dev on maternity leave, returns June 2026. With new hire (interview in progress) and Sr Web Dev return: 9 from June. Additional 2–3 resources planned for Q1 using AMC receivables.

## 5.2  Full Team Role Table

| Role ID | Title | Track | Exp. | Status | Key SPINRISE Responsibility | Module(s) |
| --- | --- | --- | --- | --- | --- | --- |
| CEO | Chief Executive Officer | Leadership | 45+ yrs | Active | Product owner, strategic direction, AI programme catalyst, Saturday AI knowledge sessions | All |
| PM | Project Manager | Delivery | 20+ yrs | Active | End-to-end delivery accountability, sprint planning, risk management, PULSE 360 tracking, customer communication | All |
| TL-Dev | Tech Lead — Dev | SPINRISE Dev | 10+ yrs | Active | Overall development coordination, RM Purchase & Inventory module owner, architecture governance, API framework | M01 + M05 |
| Sr VB Dev1 | Senior VB Developer 1 | SPINRISE Dev | 8+ yrs | Active | Stores Purchase & Inventory module owner. Deep procurement workflow knowledge. Business logic validation. | M02 |
| Sr VB Dev2 | Senior VB Developer 2 | SPINRISE Dev | 8+ yrs | Active | Domestic Yarn Sales module owner. Sales cycle, GST compliance, credit management expertise. | M03 |
| Sr VB Dev3 | Senior VB Developer 3 | SPINRISE Dev | 8+ yrs | Active | HR & Payroll module owner. Statutory compliance: PF, ESI, TDS, PT, leave, attendance. | M04 |
| Sr Web Dev | Senior Web Developer | SPINRISE Dev | 8+ yrs | On Leave Returns Jun’26 | Export Sales, Waste & Scrap Sales, e-Invoicing module leader. MIS & Dashboards co-owner. Leads Supplier Portal and CSM projects. | M06–M08 |
| Jr Web Dev1 | Junior Web Developer 1 | SPINRISE Dev | 1+ yr | Active | React UI development, API integration. Coordinates with Sr VB Devs on module UI screens. SPINNOVA co-development. | UI Support |
| Jr Web Dev2 | Junior Web Developer 2 | SPINRISE Dev | 1+ yr | Active | React UI development. Web module maintenance. MIS dashboards. SPINNOVA co-development. | UI Support |
| TL-IST | IST Team Lead | SPINRISE IST | Senior | Active | RM Purchase & Payroll domain, UAT leadership, customer site deployment coordination. | M01+M04 |
| Sr IST1 | Senior IST 1 | SPINRISE IST | Senior | Active | Stores Purchase & Inventory domain, functional testing, customer changeover support. | M02 |
| Sr IST2 | Senior IST 2 | SPINRISE IST | Senior | Active | Domestic Sales domain, UAT, customer training, changeover assistance. | M03 |
| SME | Subject Matter Expert | IST+QA+SPINNOVA | 5 yrs* | Active | M.Sc. Textile Technology. IST & QA for Spinning, Weaving, HT Production & Quality. SPINNOVA use-case owner. | QC+Production SPINNOVA |

* SME: 3 years textile industry + 2 years Kalpatharu full-time.

## 5.3  Additional Resources — Q1 FY 26-27 Plan

To meet the 30 September 2026 Phase 1 target, 2–3 additional resources will be onboarded in April–May 2026, funded from AMC quarterly receivables:

- Mid-level React.js Developer (2–4 years, ASP.NET Core preferred) — accelerates UI delivery for Production, Quality, and Power modules in Phase 2

- ASP.NET Core / C# Backend Developer (2–3 years, SQL Server proficient) — supports Financial Accounting and Production API development

- QA / Test Engineer (functional testing, ERP domain preferred) — structured test execution support alongside IST team

Candidate pipeline: A full-stack developer (React + ASP.NET Core + SQL Server, 4+ years, Tirupur) has been assessed today. If outcome is positive, onboarding is targeted for April 2026. Projected total team: 11–12 by May 2026.

6. Module Ownership Matrix

## 6.1  Every Module Has a Named Owner

Each module is owned by a specific developer who is responsible for that module’s business logic accuracy, API correctness, and delivery timeline. The IST member provides domain validation and UAT. The Jr Web Dev provides React UI implementation.

| ID | Module Name | Dev Owner | IST / SME | Web UI | Phase | Target |
| --- | --- | --- | --- | --- | --- | --- |
| M01 | Raw Material Purchase & Inventory | TL-Dev | TL-IST / SME | Jr WD1 / WD2 | Phase 1 | Sep 2026 |
| M02 | Stores Purchase & Inventory | Sr VB Dev1 | Sr IST1 / SME | Jr WD1 / WD2 | Phase 1 | Sep 2026 |
| M03 | Domestic Yarn Sales | Sr VB Dev2 | Sr IST2 / SME | Jr WD1 / WD2 | Phase 1 | Sep 2026 |
| M04 | HR & Payroll | Sr VB Dev3 | TL-IST / SME | Jr WD1 / WD2 | Phase 1 | Sep 2026 |
| M05 | Accounting & Finance | TL-Dev + New Dev | TL-IST | Jr WD1 | Phase 1 | Sep 2026 |
| M06 | e-Invoicing (GST IRN) | Sr Web Dev (Jun+) | Sr IST1 / SME | Jr WD1 | Phase 1 | Sep 2026 |
| M07 | Export Yarn Sales | Sr Web Dev (Jun+) | Sr IST2 / SME | Jr WD2 | Phase 2 | Nov 2026 |
| M08 | Waste & Scrap Sales | Sr Web Dev (Jun+) | Sr IST1 | Jr WD2 | Phase 2 | Nov 2026 |
| M09 | Spinning Production Systems | TL-Dev + New Dev | All IST + SME | Jr WD1/WD2 | Phase 2 | Dec 2026 |
| M10 | Quality Control | New Dev + SME | SME (QA lead) | Jr WD1 | Phase 2 | Dec 2026 |
| M11 | Power Accounting | New Dev | Sr IST1 | Jr WD2 | Phase 2 | Dec 2026 |
| M12 | Machinery & Electrical Maintenance | New Dev | TL-IST / SME | Jr WD2 | Phase 2 | Dec 2026 |
| M13 | MIS & Dashboards (ongoing) | Sr Web Dev + Jr WDs | All IST + SME | Jr WD1/WD2 | Continuous | Ongoing |
| M14 | SPINNOVA AI Framework | Jr WDs + SME | SME (use-case owner) | Jr WD1/WD2 | Parallel | Ongoing |

7. 12-Month Delivery Roadmap — FY 2026–27

Our commitment to every customer: By 31 March 2027, every Kalpatharu customer will have the option to migrate to the full web-based SPINRISE platform, seamlessly, with minimal upgrade cost. The legacy system continues running throughout — both systems share the same SQL Server database, ensuring zero data risk.

## Phase 0 — Foundation & Setup   |   April 2026   (4 Weeks)

The first month establishes the full development environment, upskills the team on the new stack using AI tools, and delivers the first working end-to-end module as proof of concept.

| Week | Activity | Owner |
| --- | --- | --- |
| Week 1 | Install: Visual Studio 2022, VS Code, Node.js 20 LTS, React Vite, Azure DevOps / GitHub. Activate Claude Code + GitHub Copilot + ChatGPT for all developers. | PM + TL-Dev + Jr WD team |
| Week 1–2 | ASP.NET Core 8 Web API fundamentals for VB Dev team (TL-Dev, Sr VB Dev1–3) — using Claude Code as the learning accelerator. C#, REST API, Dapper. | TL-Dev leads all Sr VB Devs |
| Week 1–2 | React.js 18 + Ant Design Pro deep dive for Jr Web Dev team. Build application shell: login, JWT authentication, role-based menu, responsive layout. | Jr WD1 + Jr WD2 |
| Week 3–4 | Build first full module end-to-end: Stores Purchase API (ASP.NET Core 8) + React UI. IST validates business logic. Full stack proven. | Sr VB Dev1 + Jr WD1 + Sr IST1 |
| Week 4 | Saturday all-team demo of Phase 0 deliverable. CEO review. PM sets Phase 1 sprint plan and PULSE 360 baseline. | All Team + CEO + PM |

## Phase 1 — Core Operational Modules   |   May – September 2026

Target by 30 September 2026: 6 core modules live on web. Covers 80%+ of daily mill operations. Full prospect demo ready. New customer onboarding begins.

| Period | Module | Lead | Key Screens & Features | Go-Live Milestone |
| --- | --- | --- | --- | --- |
| Apr–Jun | M01: RM Purchase & Inventory | TL-Dev + TL-IST | Purchase order, GRN, quality linkage, stock ledger, mixing issue to production, reorder alerts, transaction approvals, vendor master | First live web module. Demo to 3 key customers. |
| May–Jul | M02: Stores Purchase & Inventory | Sr VB Dev1 + Sr IST1 | Indent, PO, GRN, bin card, stock statement, slow-moving items, vendor management, material return | Two modules live. Customer confidence builds. |
| Jun–Aug | M03: Domestic Yarn Sales | Sr VB Dev2 + Sr IST2 | Sales order, delivery order, GST invoice, credit limit, outstanding, dispatch planning, party ledger | Sales cycle on web. First full prospect demo. |
| Jun–Sep | M04: HR & Payroll | Sr VB Dev3 + TL-IST | Employee master, attendance, leave, shift management, PF/ESI/TDS/PT computation, pay slips (PDF), loan & advance | Monthly payroll on web. High internal visibility. |
| Jul–Sep | M05: Accounting & Finance | TL-Dev + New Dev | Vouchers (receipt/payment/journal), BRS, AP/AR, GST registers, GSTR-1 / GSTR-3B, P&L, Balance Sheet | Full financial cycle on web. Management-level demo. |
| Jul–Sep | M06: e-Invoicing (GST IRN) | Sr Web Dev (Jun+) | IRN generation (IRP API), e-way bill, credit/debit note, amendment, cancellation, GSTN compliance | Statutory compliance on web. Critical customer trust milestone. |

30 September 2026 — Customer Communication: Write to all 50+ customers confirming web upgrade is on track. Invite top-10 revenue customers for a live demonstration. Begin formal migration scheduling. Announce SPINRISE onboarding for new customers from October 2026.

## Phase 2 — Production, Sales Completion & Supporting Modules   |   October – December 2026

From October 2026: New customers onboarded directly on SPINRISE. This is our market entry gate.

| Period | Module | Lead | Key Screens & Features | Go-Live Milestone |
| --- | --- | --- | --- | --- |
| Oct–Dec | M09: Spinning Production | TL-Dev + New Dev | Blow room to autoconer production entries, ring frame efficiency & end breakage, shift-wise summary, count-wise production, input-output reconciliation | Core differentiator on web. Strongest competitive demo. |
| Oct–Nov | M07: Export Yarn Sales | Sr Web Dev + Sr IST2 | Export SO, shipping bill, LC management, forex handling, export registers, invoice | Full sales cycle (domestic + export) complete. |
| Nov–Dec | M10: Quality Control | New Dev + SME | RM incoming quality (fibre parameters), in-process quality, finished yarn testing, quality hold/release workflow, customer sample tracking | Quality-production loop closed on web. |
| Nov–Dec | M11: Power Accounting | New Dev + Sr IST1 | Section-wise meter readings, consumption per kg/spindle-shift, power bill entry, section cost allocation to production | Operational costing module live. |
| Nov | M08: Waste & Scrap Sales | Sr Web Dev + Sr IST1 | Waste category master, daily generation entry, sale order, weighment, invoice, reconciliation report | Revenue cycle 100% on web. |
| Dec | M12: Machinery & Elec. Maint. | New Dev + TL-IST | PM schedule, breakdown log, root cause, spares used, annual overhaul, motor history, insulation test records | All 12 modules web-ready. SPINRISE complete. |

## Phase 3 — Customer Migration & Vertical Expansion   |   January – March 2027

From January 2027: Full 12-module SPINRISE live. Customer migration begins systematically. Vertical expansion to Paper mills, Weaving, Home Textiles commences.

| Period | Activity | Details | Outcome |
| --- | --- | --- | --- |
| Jan–Mar 27 | Customer migration — top revenue accounts | Top-10 spinning mill customers migrated with IST + SME support, on-site deployment, parallel running, user training, formal cutover sign-off | Customers live on SPINRISE. Upgrade cost revenue. |
| Jan–Mar 27 | SPINNOVA + SPINRISE integration | SPINNOVA AI KPIs integrated with live SPINRISE operational data. Real-time mill efficiency dashboards. Management intelligence layer complete. | AI-native product pair complete. Unique market differentiation. |
| Jan–Mar 27 | Vertical expansion | SPINRISE framework adapted for Paper mills, Weaving, and Home Textiles. These verticals contribute 25–30% of company revenue today. | Revenue base broadened. New customer segment opened. |
| Ongoing | MIS & SPINNOVA enhancements | Cross-module analytics, plant KPI dashboards, production efficiency trends, quality index, SPINNOVA AI-driven recommendations. | Management value continuously increasing. |

8. AI-Assisted Development Workflow

## 8.1  How Each Module Is Built — The SPINRISE Development Loop

Every module follows a structured 5-step workflow. The VB developer (domain knowledge), the AI tool (code generation speed), and the Jr Web developer (UI implementation) work in a defined loop:

| # | Step | What Happens | Why It Matters |
| --- | --- | --- | --- |
| 1 | Document | VB Developer (module owner) describes all screens, business rules, calculations, and validations to Claude Code in plain English — or pastes the actual VB6 form code. Every edge case is discussed. | Domain knowledge is formally captured in structured text for the first time. This becomes the definitive module specification. |
| 2 | Generate | Claude Code generates: React component (Ant Design Pro form/grid), ASP.NET Core 8 API controller (C#), Dapper data access layer (calling existing stored procedures). Approximately 60–70% of code is auto-generated. | 3–5x development speed. The 12-month timeline is only possible because of this step. Developers accelerate, not replace, the process. |
| 3 | Review | The same VB Developer reviews every line of generated code for domain logic accuracy. Business rules validated. Edge cases tested. Corrections applied before any testing begins. | The developer’s 8–10 years of domain knowledge is the quality gate. AI generates; the domain expert approves. |
| 4 | Test | IST member + SME run User Acceptance Testing against live customer data on the parallel test instance. Claude Code assists in generating test cases. Defects logged in PULSE 360. | Real-world domain validation before any customer sees the module. Zero surprises at go-live. |
| 5 | Deploy | Module released to staging for customer preview (selected pilot customers). Feedback incorporated. Production deployment approved by TL-Dev + PM. | Controlled release. Customer confidence built module by module. |

## 8.2  AI Tools — Active Stack

| Tool | Subscription | Primary Use in SPINRISE | Already Proven At Kalpatharu |
| --- | --- | --- | --- |
| Claude Code (Anthropic) | Pro / Team — all devs | Primary code generation: React components, C# APIs, Dapper wrappers. VB6-to-C# conversion. Test case drafting. | VB6 bug analysis, SQL optimisation, Supplier Portal, CSM project |
| GitHub Copilot | Business — all devs | Real-time code completion inside Visual Studio 2022 and VS Code during active development. | Active across all current project development |
| ChatGPT (OpenAI) | Paid — team | Technical problem-solving, SQL query design, domain documentation drafting, test scenario generation. | VB6 bug fixing, SQL tuning, CSM development |
| PULSE 360 | In-house — Kalpatharu | Daily logsheets, effort tracking, phase progress monitoring. Project IDs: SPINRISE Dev and SPINRISE IST. | Active from Day 1. All team members log daily. |

9. Risk Register & Mitigation Plan

| Risk | Prob. | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| VB Dev team C# / React learning curve slower than expected | Medium | High | Claude Code generates 60–70% of code. Devs validate domain logic. 4-week structured ramp-up in April before live module work. CEO monitors Saturday. | TL-Dev + CEO Saturday review |
| Sr Web Dev return delayed beyond May 2026 | Low | Medium | e-Invoicing prep work (schema, API docs, test cases) done by Jr WD team in Apr–May. Sr Web Dev picks up from June with full specs ready. | PM + Jr WD team |
| Additional resource hiring delayed beyond April | Medium | Medium | Production/Quality/Power are Phase 2 (Oct+). Buffer built in. Jr WDs absorb additional UI with Claude Code. Saturday upskilling sessions. | PM + CEO — sourcing starts now |
| Existing customer resistance to web migration | Low | Low | No forced cutover. Parallel running on same database. Web is a value-add upgrade, not a replacement. Minor upgrade pricing. | IST Team + PM |
| Spinning Production module complexity exceeds Phase 2 timeline | Medium | Medium | Module assigned to TL-Dev (most experienced) from October. SME provides continuous domain input. All IST members on UAT. October start gives 3 months. | TL-Dev + SME + All IST |
| SPINNOVA bandwidth competes with SPINRISE Jr WD time | Low | Low | Explicit time allocation in PULSE 360. Saturday sessions used for SPINNOVA knowledge sharing. New web resource reduces dependency. | PM — PULSE 360 allocation |
| VB6 client affected by database changes during parallel run | Very Low | High | SPINRISE uses only existing stored procedures via Dapper. No schema changes to existing tables. New tables use a separate namespace. VB6 fully isolated. | TL-Dev — architecture governance |

10. Saturday Cadence — How We Deliver Together

## 10.1  What Happens Every Saturday

The Saturday session is not a routine meeting. It is the weekly delivery heartbeat of Project SPINRISE. It has four functions that collectively make the 12-month timeline credible:

| Function | What Happens | Why It Matters for SPINRISE |
| --- | --- | --- |
| Skill Upgradation | Hands-on learning: React patterns, ASP.NET Core techniques, Claude Code prompting strategies, SQL optimisation. Shared by whoever learned something useful that week. Everyone teaches. | Every developer gains skills faster than self-study alone. The whole team rises together. |
| Weekly Review | TL-Dev and PM review sprint progress. Blockers surfaced. PULSE 360 metrics reviewed. Module delivery status vs roadmap checked. Decisions escalated to CEO. | Delivery accountability is enforced weekly. No month-end surprises. Issues resolved while they are small. |
| Sprint Planning | Next week’s tasks confirmed. Ownership assigned. Claude Code prompts prepared for complex screens. IST members briefed on upcoming UAT schedules. | Team enters every week with clear, scoped, AI-ready tasks. No ambiguity on Monday morning. |
| CEO AI Session | CEO shares learnings from the week’s AI coaching programme. New tools demonstrated. SPINNOVA use cases explored. Team challenges discussed with AI lens. | The team stays at the AI frontier without each person attending expensive courses. Organisational capability compounds weekly. |

|  | “We were late to the internet and web wave. We will not make that mistake with AI. SPINNOVA is our proof that we are early adopters this time.” — CEO, Kalpatharu |
| --- | --- |

The CEO’s personal AI learning programme — 9 hours per week with one of India’s leading AI coaches — is the organisational energy behind both SPINRISE and SPINNOVA. Every learning reaches the full team every Saturday. That is why our AI tool proficiency is not aspirational — it is demonstrated, current, and growing. That is what makes the 12-month SPINRISE commitment real.

11. Immediate Action Plan — This Week

| When | Action | Owner | By |
| --- | --- | --- | --- |
| Fri 27 AM | Internal team session (AN): Share this Blueprint. Discuss roadmap. Confirm module ownership per role ID. Align on Phase 0 start. | CEO + PM + All Team | Today |
| Sat 28 | Saturday brainstorming: Team reviews roadmap in detail. TL-Dev estimates screen counts per module (critical for sprint planning). PM finalises Week 1 sprint. CEO AI session. | All Team + CEO | Tomorrow |
| Sat 28 | Interview decision: Confirm offer to today’s candidate. | CEO | Tomorrow |
| Mon 30 | Procure Claude Code (Pro/Team) + GitHub Copilot Business subscriptions for all active team members. | Admin / CEO | 30 Mar |
| Mon 30 | Set up Azure DevOps / GitHub. Create SPINRISE Dev repository. First commit: ASP.NET Core 8 Web API solution + React Vite project scaffold. | TL-Dev + Jr WD1 | 30 Mar |
| Mon 30 | Post JDs for 2–3 additional resources (React Dev, .NET Dev, QA Engineer) on Naukri and LinkedIn. | PM / CEO | 30 Mar |
| Tue 31 | PULSE 360: Activate SPINRISE Dev + SPINRISE IST project IDs. Confirm with all team members. Daily logging begins 1 April. | PM | 31 Mar |
| 1 Apr 2026 | Project SPINRISE officially commences. Phase 0 begins. First daily standup 9:00 AM sharp. First PULSE 360 logsheet entries. | All Team | Day 1 |

SPINRISE “From Spindle to Cloud — The Next Revolution” ────────────────────────────── Kalpatharu Software Ltd · Coimbatore, Tamil Nadu, India SPINRISE Blueprint v4.0 · Internal Circulation · 28 March 2026 Internal & Confidential — Kalpatharu Team Only — Do Not Forward